# Uncovering the Structure Complexity of Stakeholder Interactions with Process and Product Innovation in Oil and Gas EPC Projects

كشف التعقيد البنيوي لتفاعلات أصحاب المصلحة مع ابتكار العمليات والمنتجات في مشاريع الهندسة و التوريد و الإنشاء في مجال صناعة النفط والغاز

by

NASSER MOHAMED IBRAHIM ALHAMMADI

A thesis Submitted in fulfilment

of the requirements for the degree of

DOCTOR OF PHILOSOPHY IN PROJECT MANAGEMENT

at

The British University in Dubai

March 2021

DECLARATION

I warrant that the content of this research is the direct result of my own work and that any use made in it of published or unpublished copyright material falls within the limits permitted by international copyright conventions.

I understand that a copy of my research will be deposited in the University Library for permanent retention.

I hereby agree that the material mentioned above for which I am author and copyright holder may be copied and distributed by The British University in Dubai for the purposes of research, private study or education and that The British University in Dubai may recover from purchasers the costs incurred in such copying and distribution, where appropriate.

I understand that The British University in Dubai may make a digital copy available in the institutional repository.

I understand that I may apply to the University to retain the right to withhold or to restrict access to my thesis for a period which shall not normally exceed four calendar years from the congregation at which the degree is conferred, the length of the period to be specified in the application, together with the precise reasons for making that application.

_______________________

Signature of the student

# COPYRIGHT AND INFORMATION TO USERS

The author whose copyright is declared on the title page of the work has granted to the British University in Dubai the right to lend his/her research work to users of its library and to make partial or single copies for educational and research use.

The author has also granted permission to the University to keep or make a digital copy for similar use and for the purpose of preservation of the work digitally.

Multiple copying of this work for scholarly purposes may be granted by either the author, the Registrar or the Dean only.

Copying for financial gain shall only be allowed with the author’s express permission.

Any use of this work in whole or in part shall respect the moral rights of the author to be acknowledged and to reflect in good faith and without detriment the meaning of the content, and the original authorship.

Abstract

Using Social Network Analysis framework to analyse the influence of project stakeholders on process and product innovation, this study set out to understand the stakeholders and activities that can lead to process and product innovation in a Greenfield, Downstream Oil and Gas EPC project. Deriving their position from having a high number of interactions and occupying a central position in social network, the Engineering Manager, the Cost Control Manager/ Procurement Engineer, and the Senior Construction Engineer were identified as the most influential stakeholders in Process Innovation in the Engineering, Procurement and Construction Phases respectively. For the same reasons, the Engineering Manager, Cost Control Manager/Procurement Engineer, and Senior Quality Assurance/ Quality Control Engineer were identified as the most influential stakeholders on product innovation in the Engineering, Procurement and Construction Phases, respectively. Based on being the most senior decision maker in the whole EPC project, Engineering Manager was found to have the highest level of influence on process innovation. For the same reasons, the Project Manager was identified as most influential stakeholder on product innovation.

In terms of activity nodes, the most influential on both process and product innovation were identified as those having many connections with other nodes giving them access to important information flows. The most influential activity nodes on process innovation were identified as “IPF (SIL Review)” for Engineering, “Weekly Procurement expediting meetings with Contractor and Vendors” for Procurement, and “Fire water Tank – Final Testing” for the Construction Phase. Also based on the number of node connections, the most influential activities on product innovation were identified as: IPF (SIL Review) for Engineering, “Suction K.O. drum – prepare and Issue MR” for Procurement, and “Mechanical (Equipment) – HIPS Installation” for the Construction Phase. Because of its high number of connections, highly central Network position, and ranking higher in the hierarchy in terms of decision making, “IPF (SIL Review)” was identified as the most influential activity on both Process and Product innovation for the entire EPC project.

ملخص البحث العلمي

باستخدام نظام تحليل الشبكة الاجتماعية لتحليل تأثير أصحاب المصلحة في المشروع على الإبتكار في العمليات والمنتجات ، تمت هذه الدراسة لفهم تأثيرأصحاب المصلحة والأنشطة على الإبتكار في العمليات والمنتجات في المشاريع  المستحدثة المتعلقة بالهندسة و التوريد و الإنشاء في عمليات المصب في قطاع النفط و الغاز  .

نظرا لموقعهم الحيوي نتيجة وجود عدد كبير من التفاعلات وإحتلال منصب مركزي في الشبكة الاجتماعية ، تم تحديد المدير الهندسي و مهندس المشتريات ومهندس الإنشاءات كأكثر أصحاب المصلحة تأثيرًا في عملية الإبتكار في الهندسة ومراحل التوريد والبناء على التوالي. وللأسباب نفسها ، تم تحديد مدير الهندسة و مهندس المشتريات وكبير مهندسي ضمان و مراقبة الجودة كأصحاب المصلحة الأكثر تأثيرًا على إبتكار المنتجات في مراحل الهندسة والمشتريات والبناء  على التوالي.

نظرا لكونه صانع قرار مؤثر في مشاريع الهندسة و التوريد و الانشاء ، فقد وجد أن مدير الهندسة يتمتع بأعلى مستوى من التأثير على الإبتكار في العمليات. وللأسباب نفسها ، تم تحديد مدير المشروع باعتباره صاحب المصلحة الأكثر تأثيرًا على إبتكار المنتجات.

في حين تم  تحديد الأنشطة الأكثر تأثيرًا في عمليات الإبتكارعلى أنها تلك التي لها العديد من الروابط مع الأنشطة الأخرى مما يتيح لها الوصول إلى تدفق المعلومات الهامة.

لقد تم تحديد النشاط الأكثر تأثيرًا على الإبتكار في العمليات على أنها عملية مراجعة مستوى الامان و السلامة في مرحلة التصميم الهندسي. كما أن عمليات تسريع عمليات الشراء كان لها الأثر الأكبر في الإبتكار في عمليات التوريد . في حين ان الإختبارات النهائية كان لها التأثير الأكبر في عمليات الإبتكار أثناء تنفيذ المشروع.

بالإضافة إلى ذلك كان لعمليات مراجعة شراء المعدات و نظام حماية السلامة العالي الأثر الأكبر في الإبتكار الفني خلال عمليات الانشاء ، في حين أن عملية مراجعة مستوى الأمان كان لها التأثير الأكبر في إبتكار المنتجات أثناء جميع مراحل المشروع .

Dedication

To My Family

Acknowledgment

I would like to thank my supervisors, Professor Halim Boussabaine and Dr. Maria Papadaki, for their guidance and support during my Ph.D. Journey. They have been a great source of inspiration for me and I sincerely appreciate their encouragement which helped me to bring this research to a fruitful end.

I would like to express my deepest appreciation to my family for their continued support throughout my journey. Their endless love inspired me to do great things and I could not have done this without their backing and inspiration.

Table of Contents

Abstract

ملخص البحث العلمي

Dedication

Acknowledgment

Table of Contents	i

List of Figures	v

List of Tables	xix

Chapter 1:	Introduction	1

1.1	Introduction	1

1.2	Background	1

1.3	Context	2

1.4	Aim, Objectives, Research Questions, and Hypothesis	5

1.5	Significance and Scope	7

1.6	Definition of Terms	9

1.7	Thesis Outline	10

Chapter 2:	Downstream Oil and Gas Sector	13

2.1	Introduction	13

2.2	Characteristics of the Oil and Gas Sector	13

2.3	Life Cycle of Projects	22

2.4	Downstream Oil and Gas Sector Projects	26

2.5	Summary	29

Chapter 3:	Innovation	31

3.1	Introduction	31

3.2	Innovation as a Concept	31

3.3	Forms of Innovation	33

3.4	Incremental Innovation and Transformational Innovation	37

3.5	Open and Closed Innovation	39

3.6	Innovation Process	40

3.7	Innovation within Oil and Gas Industry	41

3.8	Innovation and EPC Projects	42

3.9	Drivers and Enablers of the Innovation Process	42

3.10	Measures of Innovation	47

3.11	Summary	51

Chapter 4:	Project Stakeholders	53

4.1	Introduction	53

4.2	Project Stakeholders	53

4.3	Stakeholder Theory	54

4.4	Stakeholder Analysis Process – Identification and Classification	56

4.5	Stakeholder Management	60

4.6	Stakeholder Influence on Project Innovation	63

4.7	Measuring Stakeholder Influence	65

4.8	Summary	67

Chapter 5:	Theoretical Framework	69

5.1	Introduction	69

5.2	Social Network Theory	70

5.3	Engineering WBS	71

5.4	Procurement WBS	73

5.5	Construction WBS	74

5.6	Interface of EPC Phases	74

5.7	Stakeholder Value Network	78

5.8	Design Structure Matrix	79

5.9	Summary	81

Chapter 6:	Methodology	83

6.1	Introduction	83

6.2	Research Philosophy Paradigms	83

6.3	Research Design – Social Network Analysis	87

6.4	Data Collection Methods	89

6.5	Data Analysis	100

6.6	Summary Data Collection and Analysis Procedure	104

6.7	Ethical Issues	105

6.8	Summary	107

Chapter 7:	Results - Engineering	109

7.1	Introduction	109

7.2	Engineering Phase Overview	109

7.3	Study of Process Innovation Outcomes	137

7.4	Stude of Product Innovation Outcomes	170

7.5	Summary	198

Chapter 8:	Results – Procurement	199

8.1	Introduction	199

8.2	Procurement Phase Overview	199

8.3	Study of Process Innovation Outcomes	217

8.4	Study of Product Innovation Outcomes	246

8.5	Summary	275

Chapter 9:	Results - Construction	277

9.1	Introduction	277

9.2	Construction Phase Overview	277

9.3	Study of Process Innovation Outcomes	296

9.4	Study of Product Innovation Outcomes	318

9.5	Summary	346

Chapter 10:	Results - EPC	347

10.1	Introduction	347

10.2	EPC Social Network Overview	347

10.3	Study of Process Innovation Outcomes	368

10.4	Study of Product Innovation Outcomes	397

10.5	Results Triangulation	426

10.6	Summary	427

Chapter 11:	Discussion	429

11.1	Introduction	429

11.2	Research Question 1	429

11.3	Research Question 2	439

11.4	Research Question 3	449

11.5	Research Question 4	459

11.6	Research Question 5	468

11.7	Research Question 6	470

11.8	Research Question 7	470

11.9	Summary	471

Chapter 12:	Conclusion	473

12.1	Introduction	473

12.2	Achievement of Research Objectives	474

12.3	Study Generalizability	477

12.4	Research Limitations	479

12.5	Theoritical Contribution	480

12.6	Practice Contribution	482

12.7	Recommendations for Further Research	482

References	485

Appendices	517

Appendix A Activities Distribution Matrix - Engineering	517

Appendix B Activities Distribution Matrix - Procurement	533

Appendix C Activities Distribution Matrix - Construction	541

Appendix D Questionnaire	547

List of Figures

Figure ‎1.1: Thesis Outline	12

Figure ‎2.1: Oil and Gas Industry Sectors (Davcheva, 2019)	14

Figure ‎2.2: Downstream petroleum supply chain (Fernandes et al, 2013)	15

Figure ‎2.3: Oil and Gas Value Chain (The World Bank, 2009)	15

Figure ‎2.4: EPC Structure (Schramm et al, 2010)	28

Figure ‎5.1: EPC information flow Knowledge Breakdown Structure (Baron 2010, p.11)	75

Figure ‎5.2: The correspondence between Project Knowledge Network and Stakeholder Network (Zhu, Sun, Xu and Haider, 2014)	76

Figure ‎5.3: Evolution cycle of within phases Stakeholder Knowledge Network	77

Figure ‎5.4: Innovation model based on KBS based on WBS of EPC project and resultant spiral evolution of knowledge integration (Zhu, Sun, Xu and Haider, 2014)	78

Figure ‎5.5: Developing a DSM	80

Figure ‎5.6: Stakeholders DSM	81

Figure ‎6.1: Conceptualisation of research. Saunders et al. (2012)	84

Figure ‎6.2: Sequential relationship	93

Figure ‎6.3: Stakeholder influence on innovation	99

Figure ‎6.4: Research methodology flow diagram	105

Figure ‎7.1: Engineering Phase Social Network	110

Figure ‎7.2: Detail of Engineering Phase Social Network	111

Figure ‎7.3: Distribution of Node Types in the Engineering Phase Social Network	112

Figure ‎7.4: Degree a), In-Degree b) and Out-Degree c) Centrality in the Engineering Phase Social Network	116

Figure ‎7.5: Degree a) and Out-Degree b) Centrality in the Engineering Phase Social Network for nodes with less than 100 value	117

Figure ‎7.6: Degree Centrality (III) in the Engineering Phase according to node type	118

Figure ‎7.7: Degree a), In-Degree b) and Out-Degree Centrality c) in the Engineering Phase Social Network	121

Figure ‎7.8: Engineering Phase Social Network summary of Degree Centrality values	122

Figure ‎7.9: Betweenness Centrality in the Engineering Phase Social Network	128

Figure ‎7.10: Betweenness Centrality in the Engineering Phase Social Network for nodes with less than 500 value	128

Figure ‎7.11: Betweenness Centrality in the Engineering Phase according to node type	129

Figure ‎7.12: Engineering Phase Social Network affected by Betweenness Centrality	130

Figure ‎7.13: Closeness Centrality in the Engineering Phase Social Network	133

Figure ‎7.14: Closeness Centrality in the Engineering Phase according to node type	134

Figure ‎7.15: Engineering Phase Social Network affected by Closeness Centrality	135

Figure ‎7.16: Engineering Phase Social Network summary of Centrality metrics	137

Figure ‎7.17: Distribution of Node Types for Process Innovation Outcomes’ Ego Networks	138

Figure ‎7.18: Ego Networks of Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	139

Figure ‎7.19: Degree (I), In-Degree (II) and Out-Degree Centrality (III) of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	140

Figure ‎7.20: Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	142

Figure ‎7.21: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” a), “Improved Procurement Activities” b) and “Reduced Operational Cost” c)	144

Figure ‎7.22: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	145

Figure ‎7.23: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	147

Figure ‎7.24: Out-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	148

Figure ‎7.25: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	150

Figure ‎7.26: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c))	151

Figure ‎7.27: Betweenness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	155

Figure ‎7.28: Betweenness Centrality for “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	157

Figure ‎7.29: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	159

Figure ‎7.30: Closeness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	161

Figure ‎7.31: Closeness Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	162

Figure ‎7.32: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	164

Figure ‎7.33: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	167

Figure ‎7.34: Distribution of Node Types for Product Innovation Outcomes	171

Figure ‎7.35: Ego Networks of Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	171

Figure ‎7.36: Degree, In-Degree and Out-Degree Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	172

Figure ‎7.37: Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	174

Figure ‎7.38: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	176

Figure ‎7.39: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node types	177

Figure ‎7.40: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	179

Figure ‎7.41: Out-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	180

Figure ‎7.42: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	181

Figure ‎7.43: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c))	182

Figure ‎7.44: Betweenness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	185

Figure ‎7.45: Betweenness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	186

Figure ‎7.46: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	188

Figure ‎7.47: Closeness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Improved Procurement Activities” (b) and “Achieved Industrial Standards” (c)	190

Figure ‎7.48: Closeness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	191

Figure ‎7.49: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	193

Figure ‎7.50: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	195

Figure ‎8.1:  Procurement Phase Social Network	200

Figure ‎8.2: Distribution of Node Types in the Procurement Phase Social Network	201

Figure ‎8.3: Degree a), In-Degree b) and Out-Degree c) Centrality in the Procurement Phase Social Network	203

Figure ‎8.4: Degree a) and Out-Degree b) Centrality in the Procurement Phase Social Network for nodes with less than 100 value	203

Figure ‎8.5: Degree (I), In-Degree (II) and Out-Degree Centrality (III) in the Procurement Phase Social Network according to node type	204

Figure ‎8.6: Degree a), In-Degree b) and Out-Degree Centrality c) in the Procurement Phase Social Network	206

Figure ‎8.7: Procurement Phase Social Network summary of Degree Centrality values	207

Figure ‎8.8: Betweenness Centrality in the Procurement Phase Social Network.	210

Figure ‎8.9: Betweenness Centrality in the Procurement Phase Social Network according to node type	211

Figure ‎8.10: Procurement Phase Social Network affected by Betweenness Centrality	212

Figure ‎8.11: Closeness Centrality in the Procurement Phase Social Network	213

Figure ‎8.12: Closeness Centrality in the Procurement Phase Social Network according to node type	214

Figure ‎8.13: Procurement Phase Social Network affected by Closeness Centrality	215

Figure ‎8.14: Procurement Phase Social Network summary of Centrality metrics	216

Figure ‎8.15: Distribution of Node Types for Process Innovation Outcomes’ Ego Networks	218

Figure ‎8.16: Ego Networks of Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	219

Figure ‎8.17: Degree (I), In-Degree (II) and Out-Degree Centrality (III) of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	220

Figure ‎8.18: Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	221

Figure ‎8.19: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” a), “Improved Procurement Activities” b) and “Reduced Operational Cost” c)	223

Figure ‎8.20: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	224

Figure ‎8.21: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	226

Figure ‎8.22: Out-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	227

Figure ‎8.23: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	229

Figure ‎8.24: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c))	230

Figure ‎8.25: Betweenness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	233

Figure ‎8.26: Betweenness Centrality for “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	234

Figure ‎8.27: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	236

Figure ‎8.28: Closeness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	238

Figure ‎8.29: Closeness Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	239

Figure ‎8.30: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	241

Figure ‎8.31: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	243

Figure ‎8.32: Distribution of Node Types for Product Innovation Outcomes’ Ego Networks	247

Figure ‎8.33: Ego Networks of Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	248

Figure ‎8.34: Degree, In-Degree and Out-Degree Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	249

Figure ‎8.35: Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	250

Figure ‎8.36: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	252

Figure ‎8.37: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	253

Figure ‎8.38: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	255

Figure ‎8.39: Out-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	256

Figure ‎8.40: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	258

Figure ‎8.41: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c))	259

Figure ‎8.42: Betweenness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	262

Figure ‎8.43: Betweenness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	263

Figure ‎8.44: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	265

Figure ‎8.45: Closeness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Improved Procurement Activities” (b) and “Achieved Industrial Standards” (c)	267

Figure ‎8.46: Closeness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node types (Activity (a), Innovation Outcome (b) and Stakeholder (c))	268

Figure ‎8.47: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	270

Figure ‎8.48: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	272

Figure ‎9.1: Construction Phase Social Network	278

Figure ‎9.2: Distribution of Node Types in the Construction Phase Social Network	279

Figure ‎9.3: Degree a), In-Degree b) and Out-Degree c) Centrality in the Construction Phase Social Network.	280

Figure ‎9.4: Degree a) and Out-Degree b) Centrality in the Construction Phase Social Network for nodes with less than 100 value	281

Figure ‎9.5: Degree (I), In-Degree (II) and Out-Degree Centrality (III) in the Construction Phase Social Network according to node type	282

Figure ‎9.6: Degree a), In-Degree b) and Out-Degree Centrality c) in the Construction Phase Social Network	284

Figure ‎9.7: Construction Phase Social Network summary of Degree Centrality values	285

Figure ‎9.8: Betweenness Centrality in the Construction Phase Social Network	289

Figure ‎9.9: Betweenness Centrality in the Procurement Phase Social Network according to node type	290

Figure ‎9.10: Construction Phase Social Network affected by Betweenness Centrality	291

Figure ‎9.11: Closeness Centrality in the Construction Phase Social Network	292

Figure ‎9.12: Closeness Centrality in the Construction Phase Social Network according to node type	293

Figure ‎9.13: Construction Phase Social Network affected by Closeness Centrality	294

Figure ‎9.14: Construction Phase Social Network summary of Centrality metrics	295

Figure ‎9.15: Distribution of Node Types for Process Innovation Outcomes’ Ego Networks	297

Figure ‎9.16: Ego Networks of Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	297

Figure ‎9.17: Degree (I), In-Degree (II) and Out-Degree Centrality (III) of Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)	298

Figure ‎9.18: Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I) and “Improved Procurement Activities” (II) according to node type	299

Figure ‎9.19: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” a) and “Improved Procurement Activities” b)	300

Figure ‎9.20: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I) and “Improved Procurement Activities” (II) according to node type	301

Figure ‎9.21: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)	302

Figure ‎9.22: Out-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I) and “Improved Procurement Activities” (II) according to node type	303

Figure ‎9.23: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)	304

Figure ‎9.24: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b))	305

Figure ‎9.25: Betweenness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)	307

Figure ‎9.26: Betweenness Centrality for “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) according to node type	308

Figure ‎9.27: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)	309

Figure ‎9.28: Closeness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)	311

Figure ‎9.29: Closeness Centrality for Innovation Outcome “Reduced Project Implementation Time” (I) and “Improved Procurement Activities” (II) according to node type	312

Figure ‎9.30: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b)	313

Figure ‎9.31: Ego Networks of Centrality metrics: Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)	315

Figure ‎9.32: Distribution of Node Types for Product Innovation Outcomes’ Ego Networks	318

Figure ‎9.33: Ego Networks of Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	319

Figure ‎9.34: Degree, In-Degree and Out-Degree Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	320

Figure ‎9.35: Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	322

Figure ‎9.36: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	323

Figure ‎9.37: In-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	324

Figure ‎9.38: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	326

Figure ‎9.39: Out-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	327

Figure ‎9.40: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	329

Figure ‎9.41: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c))	330

Figure ‎9.42: Betweenness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	333

Figure ‎9.43: Betweenness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	334

Figure ‎9.44: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	336

Figure ‎9.45: Closeness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Improved Procurement Activities” (b) and “Achieved Industrial Standards” (c)	338

Figure ‎9.46: Closeness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	339

Figure ‎9.47: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	341

Figure ‎9.48: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	343

Figure ‎10.1: EPC Project Social Network	348

Figure ‎10.2: Distribution of Node Types in the EPC Social Network	349

Figure ‎10.3: Degree a), In-Degree b) and Out-Degree c) Centrality in the EPC Social Network	351

Figure ‎10.4: Degree a) and Out-Degree b) Centrality in the EPC Social Network for nodes with less than 100 value	352

Figure ‎10.5: Degree (I), In-Degree (II) and Out-Degree Centrality (III) in the EPC Social Network according to node type	353

Figure ‎10.6: Degree a), In-Degree b) and Out-Degree Centrality c) in the EPC Social Network	356

Figure ‎10.7: EPC Social Network summary of Degree Centrality values	357

Figure ‎10.8: Betweenness Centrality in the EPC Social Network	361

Figure ‎10.9: Betweenness Centrality in the EPC Social Network for nodes with less than 100 value	362

Figure ‎10.10: Betweenness Centrality in the EPC Social Network according to node type	362

Figure ‎10.11: EPC Social Network affected by Betweenness Centrality	363

Figure ‎10.12: Closeness Centrality in the EPC Social Network	365

Figure ‎10.13: Closeness Centrality in the EPC Social Network according to node types	365

Figure ‎10.14: EPC Social Network affected by Closeness Centrality	366

Figure ‎10.15: EPC Social Network summary of Centrality metrics	368

Figure ‎10.16: Distribution of Node Types for Process Innovation Outcomes’ Ego Networks	369

Figure ‎10.17: Ego Networks of Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	370

Figure ‎10.18: Degree (I), In-Degree (II) and Out-Degree Centrality (III) of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	371

Figure ‎10.19: Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	372

Figure ‎10.20: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	374

Figure ‎10.21: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	375

Figure ‎10.22: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	377

Figure ‎10.23: Out-Degree Centrality for Innovation Outcome ““Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	378

Figure ‎10.24: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	380

Figure ‎10.25: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c))	381

Figure ‎10.26: Betweenness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	383

Figure ‎10.27: Betweenness Centrality for “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	384

Figure ‎10.28: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	386

Figure ‎10.29: Closeness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	388

Figure ‎10.30: Closeness Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type	389

Figure ‎10.31: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	391

Figure ‎10.32: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)	394

Figure ‎10.33: Distribution of Node Types for Product Innovation Outcomes’ Ego Networks	398

Figure ‎10.34: Ego Networks of Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	399

Figure ‎10.35: Degree, In-Degree and Out-Degree Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	400

Figure ‎10.36: Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	401

Figure ‎10.37: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	403

Figure ‎10.38: In-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	404

Figure ‎10.39: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	406

Figure ‎10.40: Out-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	407

Figure ‎10.41: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	409

Figure ‎10.42: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c))	410

Figure ‎10.43: Betweenness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	413

Figure ‎10.44: Betweenness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	414

Figure ‎10.45: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	416

Figure ‎10.46: Closeness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Improved Procurement Activities” (b) and “Achieved Industrial Standards” (c)	417

Figure ‎10.47: Closeness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type	418

Figure ‎10.48: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	420

Figure ‎10.49: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)	423

Figure ‎10.50 Stakeholders ranked highest in terms of contribution to Product and Process Innovation	427

List of Tables

Table ‎3.1: Table summarising selected forms of innovation	36

Table ‎3.2:  Closed innovation and Open innovation	39

Table ‎5.1: Main disciplines at the Engineering Stage of EPC (Baron, 2010)	72

Table ‎6.1: Extract from Engineering ADM	91

Table ‎6.2: Extract from Procurement phase ADM	92

Table ‎6.3: Extract from Construction phase ADM	92

Table ‎6.4: Activities relationships matrix	93

Table ‎6.5: Activities Dependency Matrix	93

Table ‎6.6: Difference between product and process innovation (Asakawa, 2015)	94

Table ‎6.7: Innovation measures used in the study	97

Table ‎6.8: Observed innovation by activity	98

Table ‎6.9: Stakeholder influence on innovation data captured in DSM	99

Table ‎6.10: Network centrality measures applicable to the study (Cheliotis, 2010)	103

Table ‎6.11: Addressing ethical issues	106

Table ‎7.1: General Characteristics of the Engineering Phase Social Network	111

Table ‎7.2: Social Network Metrics of the Engineering Phase Social Network	113

Table ‎7.3: Degree Centrality Interpretation	114

Table ‎7.4: Degree Centrality relevant values of the Engineering Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	120

Table ‎7.5: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Engineering Phase Social Network	123

Table ‎7.6: Ten Nodes with Lower Degree, In-Degree and Out-Degree Centrality in the Engineering Phase Social Network	125

Table ‎7.7: Betweenness Centrality Interpretation	127

Table ‎7.8: Betweenness Centrality relevant values of the Engineering Phase Social Network according to node types	130

Table ‎7.9: Ten Nodes with Higher Betweenness Centrality in the Engineering Phase Social Network	131

Table ‎7.10: Closeness Centrality Interpretation	132

Table ‎7.11: Closeness Centrality relevant values of the Engineering Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	134

Table ‎7.12: Ten Nodes with Higher Closeness Centrality in the Engineering Phase Social Network	135

Table ‎7.13: Process Innovation Outcomes’ Information	138

Table ‎7.14: Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	143

Table ‎7.15: In-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	146

Table ‎7.16: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	149

Table ‎7.17: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Networks	152

Table ‎7.18: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	158

Table ‎7.19: Five Nodes with Higher Betweenness Centrality for each Process Innovation Outcome	160

Table ‎7.20: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	163

Table ‎7.21: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks	165

Table ‎7.22: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost” Ego Networks	168

Table ‎7.23: Five Activity nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost” Ego Networks	169

Table ‎7.24: Product Innovation Outcomes’ Information	170

Table ‎7.25: Degree Centrality relevant values of the Product Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	175

Table ‎7.26: In-Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	178

Table ‎7.27: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	180

Table ‎7.28: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Network	183

Table ‎7.29: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	187

Table ‎7.30: Five Nodes with Higher Betweenness Centrality for each Product Innovation Outcome	189

Table ‎7.31: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	192

Table ‎7.32: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks	194

Table ‎7.33: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards” Ego Networks	196

Table ‎7.34: High Betweenness, high Closeness and high Degree	197

Table ‎8.1: General Characteristics of the Procurement Phase Social Network	200

Table ‎8.2: Social Network Metrics of the Procurement Phase Social Network	202

Table ‎8.3: Degree Centrality relevant values of the Procurement Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	205

Table ‎8.4: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Procurement Phase Social Network	207

Table ‎8.5: Ten Nodes with Lower Degree, In-Degree and Out-Degree Centrality in the Procurement Phase Social Network	209

Table ‎8.6: Betweenness Centrality relevant values of the Procurement Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	211

Table ‎8.7: Ten Nodes with Higher Betweenness Centrality in the Procurement Phase Social Network	212

Table ‎8.8: Closeness Centrality relevant values of the Procurement Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	214

Table ‎8.9: Ten Nodes with Higher Closeness Centrality in the Procurement Phase	215

Table ‎8.10: Process Innovation Outcomes’ Information for the Procurement Phase of the EPC Project	217

Table ‎8.11: Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	222

Table ‎8.12: In-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	225

Table ‎8.13: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	228

Table ‎8.14: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Networks	231

Table ‎8.15: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	235

Table ‎8.16: Five Nodes with Higher Betweenness Centrality for each Process Innovation Outcome	237

Table ‎8.17: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	240

Table ‎8.18: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks	242

Table ‎8.19: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost’s Ego Networks	244

Table ‎8.20: Five Activity nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost’s Ego Networks	245

Table ‎8.21: Product Innovation Outcomes’ Information	247

Table ‎8.22: Degree Centrality relevant values of the Product Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	251

Table ‎8.23: In-Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	254

Table ‎8.24: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	257

Table ‎8.25: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Network	260

Table ‎8.26: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	264

Table ‎8.27: Five Nodes with Higher Betweenness Centrality for each Product Innovation Outcome	266

Table ‎8.28: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	269

Table ‎8.29: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks	271

Table ‎8.30: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standard’s Ego Networks	273

Table ‎8.31: Five Activity nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial standards’ Ego Networks	274

Table ‎9.1: General Characteristics of the Construction Phase Social Network.	278

Table ‎9.2: Social Network Metrics of the Construction Phase Social Network	280

Table ‎9.3: Degree Centrality relevant values of the Construction Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	283

Table ‎9.4: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Construction Phase Social Network	286

Table ‎9.5: Ten Nodes with Lower Degree, In-Degree and Out-Degree Centrality in the Construction Phase Social Network	288

Table ‎9.6: Betweenness Centrality relevant values of the Construction Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	290

Table ‎9.7: Ten Nodes with Higher Betweenness Centrality in the Construction Phase Social Network	291

Table ‎9.8: Closeness Centrality relevant values of the Construction Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	293

Table ‎9.9: Ten Nodes with Higher Closeness Centrality in the Construction Phase Social Network	294

Table ‎9.10: Process Innovation Outcomes’ Information for the Construction Phase of the EPC Project	296

Table ‎9.11: Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types	300

Table ‎9.12: In-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	302

Table ‎9.13: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	304

Table ‎9.14: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Networks	306

Table ‎9.15: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	309

Table ‎9.16: Five Nodes with Higher Betweenness Centrality for each Process Innovation Outcome	310

Table ‎9.17: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	313

Table ‎9.18: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks	314

Table ‎9.19: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time” and “Improved Procurement Activities’ Ego Networks	316

Table ‎9.20: Five Activity nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time” and “Improved Procurement Activities’ Ego Networks	317

Table ‎9.21: Product Innovation Outcomes’ Information	318

Table ‎9.22: Degree Centrality relevant values of the Product Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	322

Table ‎9.23: In-Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	325

Table ‎9.24: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	328

Table ‎9.25: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Network	331

Table ‎9.26: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	335

Table ‎9.27: Five Nodes with Higher Betweenness Centrality for each Product Innovation Outcome	337

Table ‎9.28: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	340

Table ‎9.29: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks	342

Table ‎9.30: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards’ Ego Networks	344

Table ‎9.31: Five Activity nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards’ Ego Networks	345

Table ‎10.1: General Characteristics of the EPC Social Network	348

Table ‎10.2: Social Network Metrics of the EPC Social Network	350

Table ‎10.3: Comparison of Social Network Metrics	351

Table ‎10.4: Degree Centrality relevant values of the EPC Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	354

Table ‎10.5: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the EPC Social Network	358

Table ‎10.6: Ten Nodes with Lower Degree, In-Degree and Out-Degree Centrality in the EPC Social Network	360

Table ‎10.7: Betweenness Centrality relevant values of the EPC Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	363

Table ‎10.8: Ten Nodes with Higher Betweenness Centrality in the EPC Social Network	364

Table ‎10.9: Closeness Centrality relevant values of the EPC Social Network according to node types (Activity, Innovation Outcome and Stakeholder)	366

Table ‎10.10: Ten Nodes with Higher Closeness Centrality in the EPC Social Network	367

Table ‎10.11: Process Innovation Outcomes’ Information for EPC Project	369

Table ‎10.12: Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	373

Table ‎10.13: In-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	376

Table ‎10.14: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	379

Table ‎10.15: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Networks	382

Table ‎10.16: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	385

Table ‎10.17: Five Nodes with Higher Betweenness Centrality for each Process Innovation Outcome	387

Table ‎10.18: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	390

Table ‎10.19: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks	392

Table ‎10.20: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time” and “Improved Procurement Activities’ Ego Networks	395

Table ‎10.21: Five Activity nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost’s Ego Networks	396

Table ‎10.22: Product Innovation Outcomes’ Information.	398

Table ‎10.23: Degree Centrality relevant values of the Product Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	402

Table ‎10.24: In-Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	405

Table ‎10.25: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	408

Table ‎10.26: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Network	411

Table ‎10.27: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	415

Table ‎10.28: Five Nodes with Higher Betweenness Centrality for each Product Innovation Outcome	416

Table ‎10.29: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)	419

Table ‎10.30: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks	421

Table ‎10.31: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards’ Ego Networks	424

Table ‎10.32: Five Activity nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards’ Ego Networks	425

Table ‎11.1: Top Ten Most Influential Stakeholders on Process Innovation in the Engineering Phase	431

Table ‎11.2: Top Ten Most Influential Stakeholders on Process Innovation in the Engineering Phase - Summary	431

Table ‎11.3: Top Ten Most Influential Stakeholders on Process Innovation in the Procurement Phase	433

Table ‎11.4: Top Ten Most Influential Stakeholders on Process Innovation in the Procurement Phase - Summary	433

Table ‎11.5: Top Ten Most Influential Stakeholders on Process Innovation in the Construction Phase	435

Table ‎11.6: Top Ten Most Influential Stakeholders on Process Innovation in the Construction Phase - Summary	436

Table ‎11.7: Top Ten Most Influential Stakeholders on Process Innovation in the EPC Project	437

Table ‎11.8: Top Ten Most Influential Stakeholders on Process Innovation in the EPC Project - Summary	438

Table ‎11.9: Top Ten Most Influential Stakeholders on Product Innovation in the Engineering Phase	441

Table ‎11.10: Top Ten Most Influential Stakeholders on Product Innovation in the Engineering Phase - Summary	441

Table ‎11.11: Top Ten Most Influential Stakeholders on Product Innovation in the Procurement Phase	443

Table ‎11.12: Top Ten Most Influential Stakeholders on Product Innovation in the Procurement Phase - Summary	444

Table ‎11.13: Top Ten Most Influential Stakeholders on Product Innovation in the Construction Phase	445

Table ‎11.14: Top Ten Most Influential Stakeholders on Product Innovation in the Construction Phase - Summary	446

Table ‎11.15: Top Ten Most Influential Stakeholders on Product Innovation in the EPC Project	447

Table ‎11.16: Top Ten Most Influential Stakeholders on Product Innovation in the EPC Project - Summary	448

Table ‎11.17: Top Ten Most Influential Activities on Process Innovation in the Engineering Phase	451

Table ‎11.18: Top Ten Most Influential Activity on Process Innovation in the Engineering Phase - Summary	452

Table ‎11.19: Top Ten Most Influential Activities on Process Innovation in the Procurement Phase	453

Table ‎11.20: Top Ten Most Influential Activity on Process Innovation in the Procurement Phase - Summary	454

Table ‎11.21: Top Ten Most Influential Activities on Process Innovation in the Construction Phase	455

Table ‎11.22: Top Ten Most Influential Activity on Process Innovation in the Construction Phase - Summary	456

Table ‎11.23: Top Ten Most Influential Activities on Process Innovation in the EPC Project	457

Table ‎11.24: Top Ten Most Influential Activity on Process Innovation in the EPC Project - Summary	458

Table ‎11.25: Top Ten Most Influential Activities on Product Innovation in the Engineering Phase	460

Table ‎11.26: Top Ten Most Influential Activity on Product Innovation in the Engineering Phase - Summary	460

Table ‎11.27: Top Ten Most Influential Activities on Process Innovation in the Procurement Phase	462

Table ‎11.28: Top Ten Most Influential Activity on Product Innovation in the Procurement Phase - Summary	462

Table ‎11.29: Top Ten Most Influential Activities on Product Innovation in the Construction Phase	464

Table ‎11.30: Top Ten Most Influential Activity on Product Innovation in the Construction Phase - Summary	465

Table ‎11.31: Top Ten Most Influential Activities on Product Innovation in the EPC Project	466

Table ‎11.32: Top Ten Most Influential Activities on Product Innovation in the EPC Project - Summary	467

Table ‎11.33: Social Network Analysis Interpretation for Stakeholder nodes	469

Table ‎11.34: Ensemble of Social Network Analysis Metrics	471

# Introduction

## Introduction

This introductory chapter outlines the research background in section 1.2, context in section 1.3, research questions in section 1.4 and purpose in section 1.5. Additionally, this chapter lists the significance and scope of the research in section 1.6 and definitions of terms in section 1.7. Finally, section 1.8 outlines the thesis chapters.

## Background

The oil and gas industry  is divided into the upstream activities involving exploration, production and crude oil transportation to refineries; midstream activities involving refinery and transportation of refined products; and downstream activities dealing with the primary distribution and storage of product, its secondary distribution, marketing and selling (Sahebi et al., 2014; Kazemi and Szmerekovsky, 2015; Lima et al., 2016).  Division between the midstream and downstream activities tend to get blurred as there is some overlap in some of the aspects hence some authorities divide the industry into two broad categories: upstream and downstream (Milza, 2016) with midstream activities being categorised as downstream.

The oil and gas sector as a whole is in a state of continuous change as players seek to balance operational efficiency and the need to reduce environmental footprint.  Changes in the sector call for increased innovation as it is currently dealing with an unfolding reality that has challenged industry traditional practices raising questions on industry players’ ability to envisage an alternative future and to pursue business models that address customer demands (Bryant and Rao, 2017) in order to remain competitive (Hassani, Silva and Al Kaabi, 2017). Projects in the downstream sector of the industry are largely implemented through Engineering Procurement and Construction (EPC) project contracts. An  EPC Project is ‘‘… a complex transaction involving a set of products, services and construction works designed specifically to complete a specific asset for a customer within a certain period of time: a building, a turnkey factory, a power plant, a weapons system, or the like’’ (Cova and Hoskins, 1997 cited in Mahmoud – Jouinin et al., 2004, p.261).

Although EPC projects are known for faster delivery using cross-functional teams and presenting opportunities for innovation (Singh and Tiwari, 2015), in the construction industry, which is a part of EPC projects, they have been associated with low levels of innovation (Construction Industry Institute, 2010).  This has been attributed to focusing more on maximising the current value system, not having mechanisms for implementing new ideas, and the absence of economies of scale among EPC project participants (Construction Industry Institute, 2010 citing Hamel, 2006; Sawhney and Walcott, 2004; LePatner, 2007 respectively). This is despite EPCs having parallel activities involving multiple specialists within the same project (Mahmoud-Jouini, Midler and Garel, 2004), a situation that has been found to influence innovation in a project given that among drivers of innovation is relationships-based knowledge sharing.

While this is the general view, innovation has been associated with organisational context (Biscotti, D’Amico and Monge, 2018) and in that regard it can be expected that some context specific factors could influence innovation within an EPC project. This study explores a single EPC project to allow for full understanding of the organisational context issues (systems, processes, and beliefs) that influence the behaviour of individuals within it (Gibson and Birkinshaw, 2004).  Within this context, focus is on the relational aspects as reflected in stakeholder relations in view of Alhaj’s (2016) finding that organisational context influences innovation through its influence on social capital and knowledge sharing, both of which relate to stakeholders.

## Context

This study focuses on EPC projects in the oil and gas downstream sector which is operationalised as referring to secondary transportation involving distribution infrastructure for moving the product from the refineries to the end users, storage facilities and the selling of products to wholesale and retail customers (Sahebi et al., 2014; Lima et al. 2016 citing Fernandes et al., 2013). The projects have more complex infrastructure, technology and operations compared to what is found in upstream projects. Downstream projects usually have more stakeholder groupings than upstream projects a situation that is likely to present opportunities for stakeholder influence on projects.

Projects in the oil and gas industry are capital intensive and have long lifecycles characterised by detailed planning during the early stages involving project conceptualisation, feasibility, and definition as a way of reducing the project’s risk exposure. This is followed by the end user engaging a contractor to handle the engineering, procurement and construction (Wolf, 2010) phases of the project to deliver an asset in an operational state. The EPC project phase is a multipart, multi specialist service providers transaction that involves “a set of products, services and construction works designed specifically to complete a specific asset for a customer within a certain period of time’’ (Cova and Hoskins, 1997 cited in Mahmoud – Jouinin et al., 2004, p.261). The project organisation of an EPC project consists of the project manager and their team as the internal organisation and multiple other service providers coordinate by the main contractor being the external organisation (Ritsche, 2014). The project manager is responsible for managing the interface of the internal organisation and the external organisation.  Interfaces among members of the project organisation (both internal and external) influence the outcome of the project and therefore also influence the levels of innovation in the project.

Downstream projects are characterised by more complex infrastructure, technology and operations compared to what is found in upstream projects. Further in downstream projects the products are multiple and involving many technology suppliers. The products’ customers are also multiple. In that regard downstream projects usually have more stakeholder groupings than upstream projects a situation that is likely to present opportunities for stakeholder influence on projects.

The Construction Industry Institute (2010) identified enablers of innovation in that sector which include human resources, leadership, learning, collaboration and customers. Persaud (2007 citing Teece, 1986) also highlighted collaboration as a critical driver of innovation. Also confirming the importance of collaboration, Inkinen (2015) found social capital to be an important factor in the achievement of high levels of innovativeness through generation of productive ideas and collaboration within an organisation. The highest impact on product innovation has been found to be from external social capital while that for process innovation has been found to be from internal social capital (Prester et al., 2016). Social capital resides in project stakeholders and according to Rogers (2003 cited in Hassan Al-Ali, 2017), innovation depends on individuals within the network of stakeholders in the project sharing information. This could be through communication, coordination, information exchange, and conflict resolution (Shen et al., 2018). Since interface management has been positively associated with EPCs (Shokri et al., 2015), stakeholder influence on innovation in a project can be expected to be related to the state of relationships as reflected by communication, coordination and collaboration. Where interface management includes engagement of stakeholders as part of building trust among them, it can be expected that there is flow of information and therefore relevant knowledge, and that project decisions are arrived at in a manner that facilitates innovation.

Given the multiple phases of an EPC project and the different internal and external stakeholders in each, engagement of specific stakeholders varies over time so that relevance, mutual influence and participation are important explanatory factors of the relationship between a project organisation and its stakeholders (Wagner Mainardes, Alves and Raposo, 2012). Along the same vein, stakeholder involvement and therefore influence on a project can also be expected to fluctuate in line with their level of engagement as determined by relevance issues (Jonas et al., 2018) or the value they are perceived to be adding. Watson et al. (2017) found that formal organisational structures and processes developed for managing stakeholder interactions explicate how companies engage their stakeholders for sustainability innovation. Formal project organisation structure is more likely to promote the transfer of formal or explicit knowledge. However, Wang and Wang (2012) found that innovation was facilitated by sharing both tacit (informal) and explicit knowledge with tacit knowledge having more influence on the quality of innovation and explicit knowledge having more influence on the speed of innovation and performance. Formal or explicit knowledge is codified institutional knowledge within the organisation and is transmitted through formal channels.  Tacit knowledge resides in individuals and is transmitted through trust based voluntary interactions as it resides in people (Bakker et al. 2006; Kucharska and Kowalczyk, 2016).  It can therefore be expected that where there are high levels of trust among project stakeholders, knowledge sharing is facilitated resulting in higher innovation performance. In that regard, within project innovation value is derived from the network of relationships among stakeholders. This positions Social Network Analysis as a suitable method for tracing the extent of the influence of various experts (stakeholders) on process and product innovation during the different phases of an EPC project (Wu and Chiclana, 2014).

From the perspective of an EPC project and basing on Social Network Analysis, stakeholders constitute a value network consisting of a focal organisation (represented by the main contractor) and its stakeholders who include the various actors in the EPC phases. Social and economic exchanges take place among the stakeholders represented by value flows that may vary indicating the differences in knowledge flows and therefore in levels of influence on innovation. Although it has been noted that innovation involves people experiencing social processes that remodel the way they think, act and interact and in the process leading to knowledge sharing (Andersson, 2007; Hau et al., 2013), and that changes in the oil and gas sector are making innovation an imperative for sustaining competitive advantage (Bryant and Rao (2017), no study was found using Social Network Analysis to analyse stakeholder relationships in the phases of downstream oil and gas EPC projects for purposes of assessing interaction of stakeholders and product and process innovation.

## Aim, Objectives, Research Questions, and Hypothesis

The aim of this research is to uncover the complexity of interactions among project stakeholders, and product and process innovation in Oil and Gas EPC Projects. This study is utilizing Social Network Analysis to develop a framework for analysing the complexity of interactions among project stakeholders and product and process innovation in the downstream oil and gas sector in the United Arab Emirates (UAE). By utilizing the social network analysis, we will be able to model the complexity of interactions. It is anticipated that better understanding of the complexity of these interactions, will reveal most influential stakeholders on process and product innovation during each phase in Downstream Oil and Gas EPC projects.

To achieve its aim, the study has the following objectives:

1.	To identify the most influential stakeholders on process innovation in EPC project during each phase of the project and during the entire project.

2.	To identify the most influential stakeholders on product innovation in EPC project during each phase of the project during the entire project.

3.	To identify the most influential activities on process innovation in EPC project during each phase of the project and during the entire project.

4.	To identify the most influential activities on product innovation in EPC project during each phase of the project and during the entire project.

5.	To determine how to model stakeholders’ interaction of process innovation in EPC project.

6.	To determine how to model stakeholders’ interaction of product innovation in EPC project.

7.	To determine whether network measures can be used to better understand the complexity of the EPC project.

This study employs Social Network Analysis method to derive an understanding of stakeholder interactions, and process and product innovation in a downstream oil and gas EPC project in the United Arab Emirates (UAE) through conducting a case study of Alpha Gas Compressor Station. The study seeks to answer the main research question:

How does social network analysis lead to better understanding of the nexus of stakeholder interactions and process and product innovation in a Downstream Oil and Gas EPC project?

The research aims to answer the following questions:

1.	Who are the most influential stakeholders on process innovation in the EPC project during the entire project as well as each phase of the project?

2.	Who are the most influential stakeholders on product innovation in the EPC project during the entire project as well as each phase of the project?

3.	What are the most influential activities for each phase of the EPC project as well as during the entire project on process innovation?

4.	What are the most influential activities for each phase of the EPC project as well as during the entire project on product innovation?

5.	How can the stakeholders’ interaction of process innovation in the EPC project be modelled?

6.	How can the stakeholders’ interaction of product innovation in the EPC project be modelled?

7.	Can the network measures be used to better understand the EPC project complexity?

The study’s hypothesis is that using social network analysis to map out the complex stakeholder interactions in a downstream oil and gas EPC project facilitates an enhanced understanding of process and product innovation occurring during the various phases of the project and throughout the project.  By using complexity science tools, it is anticipated that there is a significant improvement in the understanding of the stakeholders’ interactions. This understanding will improve our knowledge of stakeholders’ engagement toward product and process innovation in Oil and Gas EPC project.  By uncovering the complexity of these interactions through the analysis of the case study, we will be able to achieve the aim and objectives of the research and improve our knowledge in process and product innovation. Similar studies have used complexity science tools to gain a better understanding of the relationships among different actors to enhance resilience and knowledge of organizational systems (Binsarra, 2016).

## Significance and Scope

### Significance

The significance of this study lies in the methods used and their resultant practical contribution towards understanding the role of specific stakeholders to process and product innovation within the Greenfield downstream oil and gas sector in the United Arab Emirates. The study contributes towards closing gaps in EPC projects innovation related literature in five areas: extending application of social network theory to the EPC domain; focused single project dissection of stakeholder interaction at individual EPC phase level; building institutional innovation memory; establishment of lessons grounded in real-life project experience; and leveraging formal documents as sources for tracing innovation;

Extending application of social network theory to the EPC domain: The temporary nature of EPC projects and their involvement of multiple actors in a short-term target focused relationship has been noted to present opportunities for collaboration, knowledge sharing and therefore innovation. The significance of this study in that regard is in its extending the application of social network theory, to map out the complex multi actors’ relations and activities in a manner that captures their interaction with process and product innovation outcomes in an EPC project.

Focused single project dissection of stakeholder influence: Since innovation is associated with organisational context (Biscotti, D’Amico and Monge, 2018), this study’s focus on a single project is significant in as far as the approach lends itself to full understanding of organisational relational aspects given that organisational context has been found to influence innovation through its influence on social capital and knowledge sharing (Alhaj, 2016).  Single project focus facilitates dissecting of stakeholder networks at each phase of the EPC project to identify parts of the project with high stakeholder interaction and innovation. This is significant as it can enable project organisations to leverage aspects of stakeholder interactions or relations that are most associated process and product innovation outcomes.

Building institutional innovation memory: Problems of low margins, volatility of prices and changes in the downstream oil and gas sector mean innovation is critical for business survival (Bryant and Rao, 2017). Yet, because projects in the downstream sector are generally implemented in the form of EPC contracts, they tend to focus more on on-time project completion without much regard for preservation of innovation data as part of the contracting organisation’s institutional memory for future projects. The significance of this study is in its retrospective analysis of a completed project to derive data on areas and sources of process and product innovation that can be used in future related projects.

Lessons grounded in real-life experience: Use of multiple cross functional and cross organisational teams in EPC projects lends itself to innovation (Singh and Tiwari, 2015), the speed with which the projects are implemented however precludes identification and harnessing of emerging innovations as the focus is timely project delivery (Construction Industry Institute, 2010). This study is premised on analysing stakeholder and activities linkages, post project completion. Such an approach is significant in two ways. First, the data collected is not based on suppositions or assumptions but is grounded in what actually transpired. Second, the data is collected when the actors or providers of the data are no longer in a pressured environment and can assess documented evidence of innovation in a dispassionate manner.

Use of formal data based on lived experiences: The study uses formal data created during the subsistence of the project as opposed to being entirely based on memory. Identified product and process innovations and their origins are grounded in formally documented data.  Use of formal data enables the study to contribute context sensitive lessons for future projects that can be cross checked with the data from which they are derived.

### Scope

Realising that EPC projects are complex, the scope of this study is limited to a single EPC project. Focusing on a single case has been accepted as a valid form of inquiry when exploring complex issues where social interactions are at the centre of an investigation (Harrison et al., 2017).  Further the study will limit itself to those stakeholders who would have been identified through the EPC project’s Activity Distribution Matrix.

## Definition of Terms

For purposes of this study the following definitions will be used for the key concepts:

Downstream oil and gas sector: “… network of petroleum companies, which acts over a system comprised by refineries, distribution depots, transportation modes and routes that cumulatively satisfy the retail customer demands.” The “ … network comprises the refining, logistics and commercialization of the petroleum products importation and exportation activities, refining operations, primary distribution, storage activities, secondary distribution and local distribution.” Fernandes et al. (2013, p. 1559).

Stakeholder: a person, a group or an institution, internal or external, that may be affected or may affect the planned actions of the project (Bjugn and Casati, 2012 citing Jepsen and Eskerod, 2009).

Innovation:  “… the implementation of a new organisational method in the firm’s business practices, workplace organisation or external relations” (Oslo Manual OECD, 2005, p. 51) resulting in “the creation of substantial new value for customers and the firm by creatively changing one or more dimensions of the business system” (Sawhney, Wolcott and Arrowniz, 2006, p.76).

Process innovation: introducing new technological or organisational ways of producing goods or services that yield positive changes giving the implementing organisation a competitive advantage in dynamic sectors (Reichstein and Salter, 2006; Meeus and Edquist, 2006).

Product innovation: making available a new product or one with significantly changed characteristics to potential users; product improvements; line extensions; new markets; new uses; new category entries; and new to the world products (Kahn, 2018).

Social network: a set of ‘entities’ that are distinct, are uniquely identifiable and their number is known and therefore fixed that are linked through relationships designated as lines, paths or ties which may show the direction of information flow (Woodland, Barry and Roohr, 2014; Butts, 2008).

Social Network Analysis: Methods used to measure, represent and analyse the structure of social relationships.

## Thesis Outline

This chapter introduced the study by discussing its background and context and its purpose and significance. The rest of the study flows as follows: Chapter 2 provides background information on the downstream oil and gas sector. The chapter discusses relevant literature on characteristics of the sector, the general nature of projects in the sector and their project life cycle management with most of the focus being on the EPC project phase. Chapter 3 discusses literature on innovation within a project life cycle. It is noted that there are multiple definitions of innovation with the general consensus being that it results in the introduction of something new and valuable as determined by the major stakeholders. Chapter 4 reviews literature on project stakeholders. The concept of project stakeholders is defined noting that at its core is that of individuals affecting or being affected by organisational activities as it seeks to attain its objectives. This is followed by a discussion of   perspectives of stakeholder theory, the process of identifying and classifying stakeholders and stakeholder power and influence. Stakeholder management is discussed from the perspective of interface, engagement, and implications for innovation. It is noted that the relationship between a project and its stakeholders is one of continuously influencing each other. The chapter concludes by discussing methods of measuring stakeholder influence in a project. Chapter 5 discusses stakeholder analysis within the context of Social Network Theory based on the premise that project stakeholders constitute a social network.  Stakeholder networks are discussed through analysing the WBS at each phase of an EPC project and mapping out the flow of knowledge and information as proxies of possible levels of product and process innovation within an EPC project. Engineering’s central role of translating functional requirements into detailed drawings and specifications that reflect all aspects of the project deliverables is discussed. In view of the complexity of relationships within EPC projects, Design Structure Matrix (DSM) is discussed as a tool for mapping stakeholder relationships to facilitate understanding the interaction of stakeholders and innovation in an EPC project. Chapter 5 concludes the study’s literature review section. The subsequent chapters focus on: Methodology and methods (Chapter 6); findings presented in four chapters focusing on Engineering (Chapter 7), Procurement (Chapter 8), Construction (Chapter 9) and the whole EPC project (Chapter 10); Discussion of the findings (Chapter 11); and Conclusion (Chapter 12). Figure 1.1 illustrates the research outline.

Introduction

Methodology

Data Analysis

Discussion

Conclusion

Engineering

Procurement

Construction

EPC

Theoretical Background

Downstream Oil and Gas

Innovation

Project Stakeholders

Theoritical Framework

Figure 1.1: Thesis Outline

# Downstream Oil and Gas Sector

## Introduction

This chapter reviews relevant literature on characteristics of the oil and gas sector, challenges in the downstream part of the sector, general life cycle of projects and characteristics of EPC projects in the sector.  Characteristics of the oil and gas sector are discussed in Section 2.2 covering  a discussion of the downstream oil and gas sector, its key drivers, activities and products, industry traditional practices, and challenges (2.2.1 – 2.2.5), and characteristics of the sector in UAE (2.2.6). Further the chapter discusses approaches to Project Life Cycle specifically straight forward, control oriented, quality oriented, risk oriented and fractal approaches and the consensus on the characteristics of effective Project Life Cycle Management (2.3) It concludes by focusing on projects in the downstream oil and gas sector (2.4 – 2.5).

## Characteristics of the Oil and Gas Sector

The oil and gas supply chain has three distinct sectors: the upstream, midstream and downstream. The upstream sector activities include exploration, production, and crude oil transportation to refineries. Midstream sector encompasses refinery and transportation of refined product. Downstream sector activities deal with the primary distribution, product storage, secondary distribution, marketing and selling (Sahebi et al., 2014; Kazemi and Szmerekovsky, 2015; Lima et al., 2016). The three sectors are discussed in more detail in sub-sections 2.2.1 – 2.2.3.

Lima et al. (2016) identified the following characteristics of the oil and gas sector: The inventory is a fungible commodity that cannot be identified individually. It can be traded several times before it is sold to the final end-use. Because of the longer life cycle of oil products, the product mix is stable and so is the product demand in a specific market. Future demand can therefore be forecast based on historical data and is not necessarily influenced by product innovation and or consumer tastes. Compared to other industries, there are fewer products to be monitored.  Challenges are largely in the planning, scheduling and cost effective distribution of the products (Kazemi and Szmerekovsky, 2015). Those are the areas that present opportunities for added value through innovation in, for example, supply chain optimisation (Dal Mas, Giarola, Zamboni and Bezzo, 2010; Kong, 2002). Improvements in supply chain management have been associated with significant positive economic outcomes (Marcel, 2012; Magalhaes and Shah, 2003). Figure 2.1 illustrates the three sectors of the oil and gas industry.

Figure 2.1: Oil and Gas Industry Sectors (Davcheva, 2019)

There is some overlap between aspects of what is considered as midstream and downstream. Some (for example Milza, 2016) divide the oil and gas industry into two: upstream and downstream combining what is defined elsewhere as midstream with the downstream sector.  In the case of gas, purification of the natural gas to get natural gas liquids and elemental sulphur can be classified as midstream.  For the purposes of this study midstream and downstream will be treated as two distinct sectors.

### Downstream Oil and Gas Sector

The downstream sector includes varied activities such as refining petrochemicals, distribution, wholesale, and retail marketing. Lima et al. (2018) summarise the downstream oil supply chain as involving importation and exportation activities, refining operations, primary distribution, storage activities, secondary distribution, and local distribution. Fernandes et al. (2013 p. 1559) define what they term the downstream petroleum supply chain as:

“Network of petroleum companies, which acts over a system comprised by refineries, distribution depots, transportation modes and routes that cumulatively satisfy the retail customer demands … . The downstream PSC network comprises the refining, logistics and commercialization of the petroleum products…”

Sahebi et al.’s (2014) define downstream activities as encompassing secondary transport, storage depot, wholesale and retail marketing of oil and gas products. Secondary transportation involves the distribution infrastructure for moving the product from the refineries to the end users including appropriate storage facilities while marketing involves the selling of products to wholesale and retail customers (Lima et al. 2016 citing Fernandes et al., 2013). Figure 2.2 illustrates downstream activities.

Figure 2.2: Downstream petroleum supply chain (Fernandes et al, 2013)

Oil and Gas Downstream sector’s value chain and players are as illustrated in Figure 2.3.

Figure 2.3: Oil and Gas Value Chain (The World Bank, 2009)

The downstream sector is a complex margin business that requires participating companies to have a global perspective involving working with marketing and delivery of the product to the end user.  The main players in the downstream sector are integrated companies and independents. Integrated companies have business operations across all the sectors of the oil gas chain; upstream, midstream, and downstream segments of the oil and gas supply chain. Independents are companies that do not have upstream operations (Davcheva, 2019).

### Downstream Activities and Products

The downstream sector has complex and diverse activities involving refining and marketing and getting the products to the end users. The main participants are global integrated refiners, independent refiners that usually have a chain of service stations to market their products and end user consumers of, for example, gasoline, diesel, jet fuel and marine fuel.

#### 2.2.4.1 Refining process

The oil refining process comprises multiple complicated processes within which planning and maximisation of scheduling play an important part in boosting a refinery’s profitability. Studies have called for the revolutionization of production refineries in line with technological changes and new analytical techniques to reap associated economic benefits (Marcel and Miyake, 2017; Feital et al., 2013). The refining process involves separation, conversion and treatment resulting in light, medium and heavy products. Heavy products are fuel and lubricating oils and petroleum cake. Middle products include jet aircraft fuels, diesel fuel and kerosene. Light products include Liquid Petroleum Gas (LPG), gasoline and naphtha. The gas processing part involves extraction of impurities from the gas and resultant products include piped natural gas, liquefied natural gas (LNG) and natural gas liquids (NGLs). Utility companies are usually responsible for distributing the piped gas to the end users who are mainly commercial, residential, and industrial. Gas also serves as process feedstock for ammonia and methanol among other products.

#### 2.2.4.2 Oil and gas marketing, distribution, transportation and storage

Marketing activities involve promoting, identifying, and delivering product to customers who require refined fuel products or who operate wholesale networks distributing products to retailers (Davcheva, 2019). A common marketing form of oil and gas products is therefore through retail outlets and directly to bulk consumers such as airports, power stations and the military. Transportation of product from refinery to end user is through established modes of transportation which are: pipeline, road tankers, rail tankers and sea tankers. Because the product is a commodity it is also distributed through virtual exchange, a process that involves using competitors’ depot to reach the target customer.

### Key drivers in the Oil and Gas Downstream Sector

Key drivers in the oil and gas downstream sector are movements in crude oil prices, evolving regulations, and expansion of Asian economies (www.mckinseyenergyinsights.com).  On the refining and manufacturing side key drivers are revenues’ dependence on margins; location; configuration; technical skills and high capital requirements. On the distribution, sales, and marketing side are revenues susceptibility to changes in the product supply and demand; location; marketing skills; economies of scale and low capital compared to other segments.

Neale (2016) noted that the refining and petrochemical sector was facing challenges brought about by new marketing conditions. This has forced industry players to adopt a longer-term view and to invest in new performance improving strategies such as worker upskilling and innovative ways of implementing projects. Among these are petrochemical owners adopting a partnering approach where they partner with international independent and smaller players in the downstream industries. Concomitant to this approach is also collaboration of, or partnering between petrochemical owners and smaller players from the project conceptualisation stage, during front-end loading, right through to the rest of its cycle. Also focusing on challenges facing downstream sector, Pillai (2015) noted that the complex nature of downstream infrastructure implied low profit margins because of stringent requirements so that when implementing projects there tends to be a disparity between the planned and the executed project. The disparities together with continuing changes in the sector present opportunities for innovative solutions that close the gap between what is planned and what is delivered.

### Debunked industry traditional practices

Bryant and Rao (2017) observed that the oil and gas industry is currently dealing with an emerging reality that has debunked industry traditional practices leading to questions on the ability of industry players to envision a different future and to adopt business models that are aligned to customer demand. In a survey of more than 20 main organisations in the oil and gas sector Bryant and Rao (2017)  observed five major trends in the sector namely: the industry being shaped by market forces; businesses migrating from the traditional high cost and complex systems to simplified ones; the industry ecosystem’s primary operating system being under threat; industry players accelerating their “idea to adoption” process through their speed of innovation; and the criticality of maximising asset productivity. Although these changes are largely up-stream, they are bound to have trickle effects on the downstream sector raising the need for innovative responses.

Rui et al. (2017) investigated the cost performance of upstream and midstream oil and gas projects and found that the average overrun cost of the projects was 18% with underestimation being the most common error. While studies have been conducted on projects in the up and midstream oil and gas sector, studies focusing on downstream projects are scant. Downstream projects are characterised by more complex infrastructure, technology and operations compared to what is found in upstream projects. Further in downstream projects the products are multiple and involving many technology suppliers. The products’ customers are also multiple. In that regard downstream projects usually have more stakeholder groupings than upstream projects, a situation that is likely to present opportunities for stakeholder – innovation interaction within projects.

### Challenges in the oil and gas downstream sector

Challenges in the oil and gas downstream sector largely relate to transportation and distribution which is the process of moving refined oil from refineries to storage depots and onward transportation to retailing outlets (Lima, Relvas, and Barbosa-Povoa, 2018). In that regard, extant literature on the sector generally focuses on supply chain management (Castro and Mulama, 2018; Lima, Relvas, and Barbosa-Povoa, 2018; Lima, Relvas, Barbosa-Póvoa and Morales, 2018; Fernandes, Sampaio, Sameiro and Truong, 2017.; Lima, Relvas and Barbosa-Póvoa, 2016; Yousefi-Babadi et al., 2017; Azadeh et al., 2017;  Zulkafli and Kopanos, 2018;  Kazemi and Szmerekovsky, 2016; Zhao and Li, 2015; Garcia and You, 2015;  Fernandes, Relvas and Barbosa-Póvoa, 2014; Kazemi, 2016;  Yu, Solvang and Li, 2014).  Hence innovations in the downstream sector focus on addressing challenges of cost effectively getting the product to the consumer.

Castro and Mulama (2018) investigated the factors to be considered when locating new gas stations in a manner that exploits the benefits of combining product pricing and transportation costs. Using Linear Optimization model and Monte-Carlo simulation they found that 7% higher profits could be achieved from locating retail facilities with due consideration of the transportation network and optimising truck utilisation and route topography. They concluded that since fuel types have different carbon footprint, and optimum price levels influence sales volume of each fuel type, there may be need to evaluate the sustainability of whatever optimum pricing is adopted and to achieve a balance between level of profit and the carbon footprint. This implies the need to satisfy expectations of different stakeholders.

Lima, Relvas and Barbosa-Povoa (2018) studied various sources of uncertainty in the downstream oil supply chain and developed a multi-stage model for optimal tactical planning. They investigated downstream oil supply chain tactical distribution planning under ambiguous market conditions and proposed use of a robust optimisation model. Fernandes et al. (2017) investigated the integration of quality management and supply chain management using practices that are common to both concepts. Their findings indicate that there are synergies between the two which if combined could result in benefits for the organisation. For example, the two have continuous improvement and information sharing and flow as shared practices. The link is further confirmed by Bastas and Liyanage (2018) who, based on a review of literature, noted significant benefits that can be derived from integrating supply chain management and quality management to achieve sustainable management of both.

Other challenges relate to operating capacity of refineries; dealing with heavier and sourer crude oil; stricter environmental regulations that are tightening product specifications; volatile crude oil prices; shrinking margins as a result of new entrants; lack of information knowledge management; increase in global refining capacity; and skills shortages. CGI summarised the challenges as:

“Economic uncertainty, volatile demand, increasing regulation, sustainability pressures and changing consumer patterns are leading downstream gas companies to rethink their business models and operations. Industry leaders are seeking high performance and profitability through differentiators such as technology, which is driving better strategies, management and results.” (www.cgi.com/en/utilities/downstream-gas).

Noting challenges related to having to process heavier crude, Marafi (2017) highlighted the need for refinery operations to change to be able to meet increasing demand for high quality fuels and satisfaction of strict environmental regulations,

In dealing with the multiple challenges, organisations are increasingly using project management as a strategy for remaining competitive and creating additional value in their businesses. Successful projects have been associated with increase in sales, reduction of costs, enhanced quality and customer satisfaction (Salazar-Aramayo et al., 2013 citing Lewis, 2000). Lima et al. (2016) identified a number of possible future research streams relevant to the downstream sector among which is information sharing through collaboration; new incentive schemes; merit-based benefits; new performance measures; and a non- competitive supply chain with a cooperative environment. Ghaithan et al. (2017) researched medium-term tactical decision making for the oil and gas downstream supply chain and proposed an integrated multi-objective optimisation model focusing on total revenue maximisation, total cost minimisation and maximisation of service levels.

Notwithstanding challenges associated with the downstream oil and gas sector, market pressure in the oil and gas industry and the desire to maximise value from crude oil production has seen producers increasing investment in the downstream sector, UAE being a case in point.

### UAE Downstream Oil and Gas Sector

Major players in the oil and gas sector in UAE are national oil companies, Mubadala Petroleum which is a wholly owned subsidiary of Mubadala Investment Company owned by the Government of Abu Dhabi and Crescent Group which is privately owned. National oil companies include Abu Dhabi National Oil Company (ADNOC), Emirates National Oil Company (ENOC), Dubai’s NOC; Sharjah National Oil Company (SNOC); and RAK Gas (U.S.-U.A.E. Business Council, 2019). Also involved in the downstream sector are some international oil companies such as Chevron (storage, aviation fuel and distribution of lubricants); OMV; Compañía Española de Petróleos; S.A.U. (Cepsa); India’s Oil and Natural Gas Corporation (ONGC); China National Petroleum Corporation (CNPC) and China ZhenHua Oil Company (U.S.-U.A.E. Business Council, 2019). Occidental Petroleum, BP, Eni, ExxonMobil, Royal Dutch Shell, and Total are involved in both exploration and production.

As a matter of policy, UAE, especially Abu Dhabi, has undertaken to invest heavily in midstream and downstream infrastructure as part of the strategy to align domestic producers with the Emirates’ 2021 national development goals (U.S.-U.A.E. Business Council, 2019). This is to be achieved through increasing emphasis on refined high value-added petrochemical products.  ADNOC has increased focus on the downstream oil and gas sector as it repositions itself as a downstream player with plans underway to build an integrated refining and chemicals facility earmarked to be the largest in the world (Gnana, 2018). Planned activities include increasing refining capacity and adding new business lines. With specific reference to gas there is a focus on better utilisation of sour gas and forming joint ventures in natural gas processing (U.S.-U.A.E. Business Council, 2019).  Despite its possessing massive proven gas reserves, UAE imports gas largely from Qatar, but also exports, a situation that has made it both a nett importer and exporter of pipeline natural gas (Garcia and Hawes, 2019; World Energy Council, 2014).

With the new thrust towards downstream oil and gas, there has been a proliferation of projects within that sector to an extent that the development is expected to create 15000 jobs by 2025 (Gnana, 2018). Projects include the recently completed ADNOC’s Taweelah gas compressor station whose aim is to set up a gas network compressor in Taweelah. This is to result in uninterrupted gas supplies to Abu Dhabi and the Northern Emirates (Pipeline Oil and Gas News, 2018). Another is the Shah gas development sour gas plant expansion which aims as expanding the plant capacity by 50% consisting of a gas plant, facilities for gathering gas, product pipelines, plant for sulphur granulation plant, and ancillary facilities and utilities (Protenders, 2019).

The next section discusses characteristics of projects in the oil and gas downstream sector. It however starts with a general discussion of the life cycle of projects.

## Life Cycle of Projects

Kerzner and Kerzner (2017) define a project as a series of tasks with a clearly stated objective(s) that need to be performed within a given start and finish timeframe, budget, human and other resources, and involves people from different functions. Salazar-Aramayo et al. (2013, p. 590) define a project as “a complex effort involving interconnected activities, with the purpose of achieving an objective, and a temporary, non-repetitive process.”  Its management involves five standard phases which are initiation, planning, execution, monitoring and closure.  Each of the phases has within it, distinct stages. Each phase has multiple stakeholders who influence the project. The form and level of influence is partly influenced by the nature of the project whether it is a Greenfield or a brownfield project, whether it is upstream, medium stream or down-stream and the industry sector in which it is being implemented. Bonnal, Gourc and Lacoste (2002) identify five project life cycle approaches namely straight forward, control oriented, quality oriented, risk oriented and fractal approach.

### Straight forward approach

The straightforward approach (Bonnal et al., 2002) is the most basic format regardless of industry and involves four main phases – initiation, planning, execution and closing. The initiation and planning phases of a project (also referred to as the front-end stage) incorporates activities from idea generation to detailed planning (Aaltonen, et al., 2015). Bonnal et al. (2002) term these ‘pre-project phases’.  It includes project structure, criteria for success, and major deliverables. The stage has high levels of ‘uncertainty, ambiguity, and dynamic stakeholder interactions’ (Aaltone et al. 2015, p.28).  It is at this stage that stakeholders choose the preferred or best design for the actual execution of the project. According to Aaltone et al. (2015) this is the stage at which the positions of stakeholders are shaped and when they have the highest influence on the project compared to later phases.  These early stages of a project are characterised by many strong stakeholders who seek to influence and participate in the project’s decision-making processes. The implementation or execution stage involves putting into action the project’s plan. Bonnal et al. (2002) term this ‘the project phase’. In the petroleum industry this phase is divided into three sub phases, basic design, detailed design, and post project phase. The basic design phase culminates in the award of Engineering, Procurement and Construction (EPC) contracts. The detailed design phase includes construction and commissioning of the deliverable. The post project phase involves the transfer of the deliverables from the engineers to the project owners. This research of the interaction of stakeholder engagement and product and process innovation in projects focuses on the post basic design phase of a project.

### Control oriented approach

The Control oriented approach has three main phases: planning, execution, and operation (Bonnal et al., 2002). Planning includes conceptualisation, feasibility, and definition at the end of which a decision is made whether to proceed with the project. The conceptualisation phase takes into cognisance technological innovation, economics, and customer needs. The feasibility assesses the concepts with due consideration of the objectives or desired outcomes leading to deciding the concepts to be taken on to the execution phase where procurement and implementation occurs leading to the operation phase.

### Quality oriented approach

Phases of the quality-oriented approach are conceptualisation, materialisation and turnover or transition phase (Bonnal et al., 2002). During conceptualisation, the project objectives are broken down into smaller readily achievable batches. Materialisation stage is when the most achievable part of the concept is created.  During the transition phase more, achievable parts of the project concept are identified and implemented, and the process continues until all the achievable components of a project are completed. Disintegrating the project into achievable batches ensures that at any given time the project has usable output. Further, components of a project that are not functioning at the required level can be removed without upsetting the rest of the project. The Quality Oriented Approach project life cycle is ideal for technical projects as it allows for changes as the project progresses.

### Risk oriented approach

The approach has two basic phases: pre-project focusing on the requirements and project phase focusing on planning, execution, and close-out (Bonnal et al., 2002 citing Lacoste, 1999).  The project phase has three sub-phases: planning, execution, and close-out. The approach has a scenario phase that is between the feasibility phase and project implementation.  The scenario phase deals with risk assessment and planning risk responses.

### Fractal approach

In a fractal approach, activities of phases overlap. It addresses situations that are difficult to model. Projects are broken down into sub-projects that all comply with having a pre-project phase focusing on feasibility, and a project implementation phase focusing on execution, and in between a phase for making the decision to proceed or to stop. In this approach decisions are made at several levels and dimensions: at project level they are made by owners of the project’s deliverables, at sub-project level by project managers and at lower levels they are made by managers responsible for work packages (Bonnal et al., 2002).

### Consensus on Project Life Cycle Management

Notwithstanding the multiple project life cycle approaches, there is consensus that effective Project Life Cycle Management incorporates understanding life cycles within a project and how they interact. This makes it possible to relate roles and responsibilities within the project with its core activities involving planning, estimating, scheduling, monitoring, and control mechanisms (Windapo, Oyewobi and Zwane, 2014). In a study focusing on inherently safer design principles, Windapo et al. (2014) found that project stakeholders within the PLC had different levels of awareness of safety. This implies that the influence or contribution of such stakeholders to that aspect of the project at that stage of the project life cycle would be limited.

According to Jansson and Ljung (2010) projects implemented in organisations are based on the intended goals and purpose guided by the organisation’s strategic intentions.  In this regard five project archetypes are identified: Product development, Marketing, Internal improvement, Customer order and Event projects. The first three archetypes apply to the oil and gas downstream value chain given its focus on product development (through the refinery process), marketing and internal improvement through the marketing and distribution part of the value chain. Each project archetype has phases associated with it.

Product development archetype results from identifying a product need in the market. Its phases are preparation of the implementation proposal and product life cycle estimates, product development and internal product hand-over. Key decisions during product development relate to the product design strategy and at what point to handover to other internal functions such as production and marketing. This project archetype involves many internal stakeholders and its organising guiding principle is that stakeholders must be involved early-on in the project (Jansson and Ljung, 2013).

Marketing projects come from having identified an opportunity that could be exploited. In a marketing project the phases are assessing market interests; iteratively refining the project strategy and executing marketing activities. Key decisions made are iterative relating to refining the project strategy and whether to continue with the project. Project organising involves top management and managing relations between the delivering organisation and marketing and sales. The iterative process involves project stakeholders (Jansson and Ljung, 2013).

Internal improvement results from realising a need to change the way work is done. Internal improvement project phases are creating commitment; iteratively assessing commitment to the change; refining the project strategy; implementing activities necessary for the change; and transferring to the new work processes. Organising relates to creating commitment, managing resistance to change and priority conflicts.   Decision making is iterative relating to investing required resources for the change to occur and to discard old processes to embrace the new (Jansson and Ljung, 2013).

In all the project archetypes, there is stakeholder interactions which presents opportunities for innovation. Henriksen (2018) avers that where innovation processes are included, project management principles must focus on people management in terms of tasks, stakeholder objectives, project team and leadership, and empowerment.

## Downstream Oil and Gas Sector Projects

Downstream oil and gas sector projects take the form of Greenfield projects and brownfield projects. Greenfield projects involve totally new projects built on unutilised ground and therefore having no constraints originating from prior work (Stretton, 2017). Brownfield projects are implemented in already existing facilities and involve expansion, revamping, servicing, demolishing, or renovating of existing structures. In that regard the projects interact with extant operating facilities and therefore raise the need for interaction and management of relationships and legacy issues (Stretton, 2017).

Oil and Gas Industry projects are highly capital intensive and have long lifecycles. They are characterised by detailed planning during the early stages of the life cycle (Front-end loading) as a way of reducing project risk at a time when making changes to the project is less costly. Front End Loading (FEL) has three phases: conceptualisation, feasibility, and definition. After each phase there are stage gates where decisions are made on whether to continue with the project in view of information at hand. The third phase is followed by the EPC phase followed by the operate phase (Wolf, 2010). This research focuses on the EPC project phase.

### EPC project characteristic

Cova and Hoskins (1997 cited in Mahmoud - Jouinin et al., 2004, p.261) define an EPC project as:

‘‘A complex transaction involving a set of products, services and construction works designed specifically to complete a specific asset for a customer within a certain period of time: a building, a turnkey factory, a power plant, a weapons system, or the like.’’

EPC models of project management are widely used in oil and gas projects. In an EPC model the end user or principal engages a contractor to deliver an asset in an operational state having been given a general scope detailing the expected functionality and performance of the final product (www.constructionlawmadeeasy.com/EPCandEPCM).  The project starts at the point of signing of the agreement on contractual terms and ends at Start-Up which is the full production run (Homer, et al., 1993). The contractor is responsible for completing the project design, constructing, and delivering the asset for use. EPC overlaps the design, procurement, and construction stages of a project, described by Helper (n.d.) as interlocking relationships in the project phases, resulting in reduced total project duration while addressing client’s amendments during the project life cycle. The general sequence of an EPC project is: process and equipment design; construction design; procurement; construction; functionality check-out; operational check-out and finally start-up (Homer et al., 1993).

According to Ritsche (2014) the project organisation of EPC projects is not just the project manager and their team but involves the external and the internal project organisation. The external organisation relates to multiple companies or entities (sub-contractors) involved in a project coordinated by a main contractor. The internal organisation in its simplest form has the project manager and their team with the former responsible for the interface with the external organisation, in larger projects the project manager reports to a steering committee that has representatives of organisations involved in the project. Interfaces among members of the project organisation influence the outcome of the project and therefore also have a bearing on the levels of innovation in the project.

Du and El-Gafy (2014) investigated the impact of stakeholder goal incongruence on the proposal development stage of an EPC project and posited that a comprehensive and systematic investigation of human behaviours is necessary in order to understand problems of goal incongruence during project proposal development. Underlining the importance of stakeholder engagement in EPC construction projects Wolf (2010, p.15 citing The Construction Industry Institute (CII) 1987) states that:

“The pressures and mistakes associated with extreme fast-tracking can easily strain the relationships among owner, engineer, and contractor and destroy the team atmosphere so essential to success. To the workers, rework and waiting for materials translates into incompetent project management – a major demotivator. In an atmosphere of tension and demoralized workers, quality inevitably suffers.”

Arain (2011) found that oil and gas construction projects experienced significant changes because of inadequate design, owner changing scope and specifications, and unforeseen eventualities. This suggests that the problems could be addressed through, among other factors, involvement of the owner at design phase and teamwork, which imply stakeholder involvement. In EPC model the team responsible for delivering the project includes designers, constructors, procurement staff, estimators, and project controls specialists. In such a multi-stakeholder situation success depends on the level of integration in the team (Carlson et al., 2007). Integration brings with it challenges associated with coordinating different project stakeholders (Tang et al., 2008; Du and El-Gafy, 2014). Further the fact that most EPC projects are based on conceptual designs without detailed requirements and specifications, creates the need to manage the interface of various actors within independent but interacting entities (Öztas and Ökmen 2004; Shen et al., 2017) in order to derive innovative value for the project.

In EPC projects design and construction activities occur concurrently, a situation that results or depends on high levels of interaction, exchange of information, and resolving technological conflicts among participants (Shen et al., 2018). As illustrated in Figure 2.3 and explained by Schramm et al. (2010) interface within the EPC project is at multiple points and is both direct and indirect. This presents opportunities for knowledge sharing and therefore innovation. Underlining the importance of knowledge sharing in a project, Du and El-Gafy (2015) found that conceptual estimating can benefit from a combination of artificial and human intelligence derived from tapping into the knowledge resident in experienced estimators.

Figure 2.4: EPC Structure (Schramm et al, 2010)

A project is considered successful when it is completed within the specified time, within budget, at an acceptable level of quality, and satisfying the expectations of its primary stakeholders (Salazar-Aramayo et al., 2013). The element of satisfying primary stakeholder expectations is the value adding part of a project. According to Salazar-Aramayo et al. (2013) a project can report successful project management even when the project itself was not a success, meaning it would have failed to satisfy stakeholder expectations. Projects are meant to bring about change that translates to added value for stakeholders. Added value has been associated with innovation or doing different things or doing things differently. Value creation comes about through either reduction of transactional costs or through leveraging relations and using collaboration with parties outside the firm to bring about added value (Rojas, 2018). The nature of EPC projects presents opportunities for deriving value from the multiple interface points that are both direct and indirect among various stakeholders. Managing such interfaces in a manner that facilitates knowledge sharing can be expected to result in innovation at the various stages of the project.

## Summary

This chapter discussed literature on characteristics of the downstream oil and gas sector and noted that the projects in the sector are generally either Greenfield or Brownfield with both presenting opportunities for stakeholder interactions with implications for within project innovation. Different approaches to the project life cycle were discussed and it was observed that despite the many approaches it is generally agreed that project life cycle management involves having an appreciation of within project life cycles and how they interface to be able to relate roles and responsibilities within the project.  The complexity and capital-intensive nature of oil and gas sector projects and their characteristic of involving initial detailed planning during the FEL phase were discussed. In the interest of focusing the study, the discussion progressed by concentrating on the post FEL phases, which is the EPC project phase. Given its wide association with downstream oil and gas projects, the EPC model was discussed. Its characteristic of involving multiple actors from the internal and external organisation and the need to manage the interface and sharing of knowledge was deemed to present opportunities for understanding stakeholders’ knowledge sharing which could have implications for within project innovation. The next chapter discusses innovation within a project life cycle.

# Innovation

## Introduction

The oil and gas industry is dynamic as it seeks to balance operational efficiency and the need to reduce environmental footprint.  Innovation is therefore an integral part of remaining competitive (Hassani, Silva and Al Kaabi, 2017). Projects in the downstream sector of the industry are largely implemented through the EPC approach yet the EPC industry has been found to be lagging behind others in innovation (Construction Industry Institute, 2010). Reasons for this state have been cited as: over focusing on maximising the current value system; absence of mechanisms for implementing new ideas, and absence of economies of scale among the firms that are part of an EPC project (Construction Industry Institute, 2010 citing Hamel, 2006; Sawhney and Walcott, 2004; LePatner, 2007 respectively). This chapter discusses innovation as a concept (Section 3.2); forms of innovation (Section 3.3); incremental and transformational innovation (Section 3.4); open and closed innovation (Section 3.5); the innovation process (Section 3.6); innovation within the downstream oil and gas sector (Section 3.7) and in EPC projects (Section 3.8); drivers of innovation (Section 3.9) and concludes by discussing innovation measures (Section 3.10).

## Innovation as a Concept

Definitions of innovation vary. Schumpeter (1934 cited in Alhaj, 2016) is recognised as the first researcher to define innovation as constituting new products or processes or sources of supply or markets or ways of organising business. For Drucker (1985) innovation is a tool that can be learnt and practiced that is used by entrepreneurs to exploit opportunities. The element of it being learnt suggests some form of interaction in the learning process.  In that regard innovation can be implemented across all organisational activities. Wallace (1995 cited in Lohmuller, 2003, p.11) defines innovation as encompassing “any form of change in technology, production process or organisational and managerial structure and techniques.”  Whether every change constitutes innovation is however disputable as Van de ven (1986) defined innovation as a process (implying that it has stages) involving the generating, adopting, and implementing of novel ideas and practices. The definition has novelty or newness as an integral part.

Vaccaro et al. (2012) defined innovation as a product, or a process, or a distribution method that is viewed as new by the affected organisation. The newness is therefore specific to the organisation experiencing or implementing the innovation. This implies that it could be something copied from another organisation that becomes new when it gets to the organisation that will need to change to embrace the innovation. The view of specificity to an organisation is backed by Assink (2006) who defines innovation as the adoption of new ideas by a specific company. Alhaj (2016, p.26) defines innovation in terms of both the product, the process and the methods as: “accepting, developing, and implementing new products and processes by developing and using new technology, good financial management, and the continuous improvement of skills.” Focus of the definitions is that the newness of what is adopted is specific to an organisation. This suggests that, that the practices may have been adopted elsewhere does not take-away its qualifying to be termed as innovation when applied in a different company. Kim et al. (2012) define innovation as new applications of knowledge or ideas or methods or skills to give an organisation unique capability. According to this definition, that something is new or has been imported into an organisation does not make it qualify as innovation unless if it results in inimitable capabilities.  This definition seems to differ from that of Wallace (1995) where any form of change is regarded as innovation or even with Palangkaraya et al. (2011) who define innovation as the introduction of new forms of production in an organisation. Also adhering to the newness script, Jiménez-Jiménez and Sanz-Valle (2011) define innovation as the adoption of new ideas and or behaviours. The Oslo Manual (OECD, 2005, p. 51) defines innovation as “the implementation of a new organisational method in the firm’s business practices, workplace organisation or external relations.” This definition is close to that given by Sawhney, Wolcott and Arrowniz (2011, p.29) that innovation is “the creation of substantial new value for customers and the firm by creatively changing one or more dimensions of the business system.”

## Forms of Innovation

Different forms of innovation have been cited in literature. Schumpeter (1983 cited in Alhaj, 2016) classified innovation into five categories: introducing new products which consumers were not aware of; introducing a new method of production; opening up of new markets; establishing new sources for raw materials or inputs; and setting up or spinning off new businesses. Other forms of innovation are in technology; production processes or organisational and managerial structure and techniques (Wallace, 1995);  technological and administrative (Jaskyte, 2011; Damanpour et al., 2009); ancillary (Damanpour et al., 2009; Gonzalez et al. 2013); product and process (Damanpour et al., 2009; Tidd and Bessant, 2011);  position and paradigm (Tidd and Bessant, 2011); incremental and radical (Zhou and Li, 2012); organisation, management and commercial (Wang and Ahmed, 2004; Trott, 2008); product, process or organisation (Camisón and López, 2010; Jiménez-Jiménez and Sanz-Valle, 2011); market, behavioural and strategic (Liao et al., 2012; Ellonen et al., 2008).

Notwithstanding the various forms identified in literature, they can be summarised into product, process, organisational and marketing.  Schmidt and Rammer (2007) observed that product and process (technological innovation) and organisational and marketing (non-technological innovation) were linked to the extent that marketing innovations go hand in hand with product innovation while technological process innovations go hand in hand with organisational innovation.

### Product innovation

Product innovation involves introducing new goods and or services. It is used by organisations as a way of renewing their product portfolios and also enables them to extend their technical capabilities (Wang and Chen, 2018). Studies have emphasised the importance of product innovation crediting it with having the most impact on organisational performance (Lohmuller, 2003). Overtime, this has changed as it has been found that product innovation can be matched or complimented by processes and service innovation. Product innovation is covered in most innovation literature with process innovation receiving less attention (Marzi et al., 2017). Types of product innovation include cost reduction; product improvements; line extensions; new markets; new uses; new category entries; and new to the world products. Product innovation is linked to an organisation’s marketing strategy since eventually the products must reach the market, hence product innovation focuses on product effectiveness (Kahn, 2018). Using a model with five dimensions: experimentation, risk taking, interaction with the external environment, dialogue, and participative decision making, Alegre and Chiva (2008) studied how an organisation’s product innovation is affected by its learning capability suggesting the importance of knowledge which would include that of market expectations.

### Process innovation

Process innovation relates to new ways of producing goods and or services that result in positive changes such as reduction of production costs and enhancement of the product or service (Reichstein and Salter, 2006). Process innovation is systemic and interdependent in that it affects both the technological and the organisational aspects of an organisation and requires multi-unit collaboration (Scafuto et al., 2018).  Its aim is to create competitive advantage derived from minimising operational and or manufacturing costs. Other benefits associated with process innovation include serving as a  method for understanding the inputs – outputs relationship;  facilitating the identification of problems, solving them, and preventing their future occurrence;  minimising time spent on processes; facilitating effective and systematic measurement of work; improvement of customer service; providing a mechanism for having an overview or complete view of company operations;  and enhancing  teamwork across different functional areas of a company (Scafuto et al., 2018).

Focusing on the internal aspects of the organisation, process innovation may be technological or organisational seeking to enhance the efficiency and effectiveness of processes (Scafuto et al., 2018). Fynes et al. (2015) define technological process innovation as an organisational phenomenon involving communal adaptation; technological and organisational change and total impact.  Europa (https//ec.europa.eu) defines it as the adoption of new or improved technological production methods. Also picking on the aspect of adoption of new technology, Zelbst et al. (2012 cited in Fynes et al., 2015) perceive technological process innovation as involving introduction of hardware and software technology. Scafuto et al. (2018) described it as involving enhancement of goods or material or products once sold as commodities, through technical changes making them more productive. It is apparent from literature that technological process innovation involves change in technology whether in the form of enhanced or new technology. Because of the element of change, Fynes et al. (2015) highlight the need for mutual adaptation in the form of congruency between the organisation and the technology. They further highlight the systemic nature of technological process innovation which makes it impact the rest of the organisation. This implies that once such innovation occurs it reverberates throughout the organisation necessitating further innovation. With specific reference to oil and gas, technological process innovation can be expected in the downstream sector where refining and extraction of products presents opportunities for using technological innovation to reduce unit costs of production while increasing quality. Such changes would have implications for the organisation of work throughout the downstream activities.

Organisational innovation as part of process innovation refers to more productive ways of organising work. Some perceive it as part of or linked to technological process innovation since the former depends on technological and organisational changes (Fynes et al., 2015). OECD (2005) defines organisational innovation as the process of implementing novel organisational methods in the practices of an organisation.  It includes using knowledge management, workplace organisation and management of external relations in a manner that has not been previously used by the firm. The new methods are implemented as a result or part of management’s strategic decisions. It includes internal structures, external structures, and information transfer (Lohmuller, 2003).  Various organisational practices are inputs for the organisation’s innovation process and capacity (Mothe and Thi, 2014). These practices include management, production, and external relations. Management incorporates aspects such as knowledge management systems, work arrangements and configuration of work teams. Production approaches include changes to the way work is organised, quality management and business re-engineering. External relations cover issues relating to outsourcing, networking, and customer relations. Organisational innovation has been linked to employee creativity (Ouakouak and Ouedraogo, 2017) and therefore to the ability of management to create an environment that facilitates the creativity.

According to Weiss, Hoegl and Gibbert (2011) innovation in organisations occurs at project level and thus implying that projects and by implication project management presents opportunities for innovation, but it is organisational and individual level factors that facilitate or inhibit innovation. Among these are the capabilities of the project manager in integrating various stakeholder interests and the power structure within the organisation (Hassani, Silva, and Al Kaabi, 2017).

### Marketing innovation

Marketing innovation involves implementation of novel marketing methods that involve major changes in the design of the product or its packaging, placement, promotion, or pricing (Mothe and Thi, 2010 citing OECD, 2005). Schmidt and Rammer (2007) observed that technological (product and process) and non-technological innovation (organisational and marketing) were linked to the extent that marketing innovations go hand in hand with product innovation while technological process innovations go hand in hand with organisational innovation.

Table 3.1: Table summarising selected forms of innovation

| Authority | Form of Innovation |
| --- | --- |
| Schumpeter, 1983 | New products; New method of production; New markets; New sources for inputs; Spinning off new businesses |
| Jaskyte, 2011; Damanpour et al., 2009 | Technological and administrative |
| Damanpour et al., 2009; Gonzalez et al. 2013 | Ancillary |
| Damanpour et al., 2009; Tidd and Bessant, 2011; Camisón and López, 2010; Jiménez-Jiménez and Sanz-Valle, 2011 | Product; process; organisation |
| Tidd and Bessant, 2011 | Position and paradigm |
| Wang and Ahmed, 2004; Trott, 2008 | Organisation, management and commercial; |
| Liao et al., 2012; Ellonen et al., 2008 | Market, behavioural and strategic |

### Innovation as output, process and mind-set

Kahn (2018) posits that there are three ways of looking at innovation: as output; as process, and as mind-set.  As output innovation focuses on the end product, and the strategic question is what you want to see happening. It considers innovation in product, process, marketing, business model, supply chain and organisational. Innovation as process focuses on ways and means of achieving innovation. The strategic question is how innovation is going to be made to happen. It includes adoption of new approaches to developing strategy; structuring activities; organising units; adjusting management and administrative processes and systems; motivating and rewarding staff; and organisational flexibility (Damanpour and Aravind, 2011). Innovation as a mind-set focuses on the state and the strategic question is: what practices and or behaviours must be embraced in order to prepare for the what and the how of innovation? Issues considered in this instance are individuals’ mind-sets and organisational culture. Kuczmarski (1996) views innovation as a mind-set as meaning having a novel way of thinking about a business’ strategies and practices. In a study of a project at Volvo cars, Börjesson and Elmquist (2011) found that the mind-set aspect of innovation was addressed through developing a language used for spreading the knowledge needed to promote innovation; creating an awareness through presentations; internal networking through ‘knowledge nodes;’ developing bridges to facilitate collaboration; and considering the political implications of the project. In an EPC project environment where the actors are from different backgrounds and or organisations, there are opportunities for knowledge transfer and sharing through interfacing different mind-sets and therefore ways of thinking about project strategies and practices.

## Incremental Innovation and Transformational Innovation

Regardless of form, innovation can be gradual and therefore incremental or involve major changes to the point of being transformational or fundamental to the point of being radical (Zhou and Li, 2012).  It can also be perceived as closed or open (Chesbrough, 2011).

Transformational or radical innovation involves adoption of new technology for product, process or service provision resulting in something completely new. It provides radical solutions to a problem which may be disruptive of the market as it previously existed resulting in the transformation of the market and society (Erna, et al. 2019).  An innovation is considered radical when it meets three criteria: is new and different from previous inventions, is unique and therefore different from other current inventions, and has been adopted so that it can influence the future of other inventions (Norman and Verganti, 2014 citing Dahlin and Behrens, 2005). Incremental innovations build on existing knowledge to refine existing processes, products, services, or technologies (Erna et al., 2019) to make them more cost effective and desirable (Norman and Verganti, 2014). It is therefore usually a follow up to some radical innovation through capturing the potential presented by radical innovation and in that regard the two forms of innovation are mutually reinforcing (Norman and Verganti, 2014). Nguyen (2018) found that both forms of innovation are influenced by human capital, top-down knowledge flows and dynamic managerial capabilities. Along the same vein, Erna et al. (2019) found that there was a positive relationship between an organisation’s collaboration with suppliers, customers, and other external partners and both radical and incremental innovation. Nguyen (2018) also found that social capital and bottom-up knowledge flows do not seem to have the same influence while organisational capital was found to have a positive effect on incremental innovation. This suggests that incremental innovation can benefit from management’s exploitation of internal human capital-based knowledge.

With specific reference to the oil industry, Yin (1994) found that incremental innovation in petroleum refinery gave higher returns than those derived from initial radical innovation. Further given the definitions of radical innovation, innovations that occur in downstream oil and gas projects are more likely to be incremental given that radical innovation does not occur frequently, yet that sector is already noted for its low levels of innovation.  Such innovations (incremental) in an EPC project environment would involve multiple players and, in that way, fit in the mould of open innovation.

## Open and Closed Innovation

Innovation used to occur in a closed environment within a company based on its strength in research and development. In this instance, competitive advantage depended on being first to get the innovation to market while protecting intellectual property to prevent competitors from benefiting from it. With increase in knowledge workers and the porousness of borders between an organisation and its environment, innovation has become more open as companies involve external stakeholders as they leverage external knowledge in the process of driving internal growth (Chesbrough, 2011; Gronlund, Sjodin and Frishammar, 2010). Open innovation involves collaboration among complementary partners who are all active participants as they co-create innovation for purposes of achieving shared goals (Kobarg, Stumpf-Wollersheim and Welpe, 2019).  Open innovation’s involvement of external collaboration fits EPC type project environments where the main contractor works with several other specialist providers to deliver a client’s project outcome.  A summary of the difference between closed and open innovation is presented in Table 3.2 adapted from Chesbrough (2011).

Table 3.2:  Closed innovation and Open innovation

| Principles of Closed Innovation | Principles of Open Innovation |
| --- | --- |
| Intelligent people or specialist in the company’s line of business are all within the company | Some people who know about the company’s line of business are outside the company, the company needs to find them and tap into their knowledge |
| To benefit from it its research and development the company must discover, develop and ship value | External research and development can create significant value. The company should use its internal R&D to tap into some of that value |
| If the company discovers the innovation, then they can be the first to get it to market | The company does not need to originate the research in order to benefit from it |
| If the company is the first to commercialise the innovation, they will win | It is more important to build a better business model than getting to market first |
| The company’s winning depends on it creating the most and best ideas in its industry | The company’s winning depends on it making the best use of both internal and external ideas |
| The company must control and protect its intellectual property to prevent competitors from benefiting from it | The company must benefit from others’ use of its intellectual property and must buy others’ when it advances the company’s business interest |

## Innovation Process

Innovation is generally presented as a linear process with feedback loops (Penide et al., 2013 citing Galanakis 2006; Boly 2008; and MacGregor et al., 2006).  The process starts from ideation and ends at product launch (Ben Rejeb, 2008 cited in Penide et al. 2013).  Penide et al. (2013) however posits that innovation is a non-linear knowledge transformation process consisting of three main activities namely: sourcing for knowledge relevant to a problem; transforming the knowledge into an innovative physical product or process; new knowledge or intellectual property shared among stakeholders; and finally, exploitation of the innovation. The knowledge transformation process involves use of resources such as internal and external stakeholders, specialised equipment, and knowledge management tools (Penide et al., 2013).  The process operates or functions within the context of a set of objectives relating to maintenance of an innovation culture and management of the innovation project portfolios. Activities in the innovation process are interconnected by information flows, are executed as per availability of relevant information and have feedback loops.  According to Penide et al. (2013) innovative projects are in fact a special case of classical projects and to that extent the process management part of the innovation process involves classical activities of project management which are planning; managing stakeholders; managing the project portfolio; and strategy formulation, communication and updating.

Extant literature has pointed to similarities between the characteristics of project-based organisations and organisations that support innovation particularly in terms of professionalism, decentralised decision-making, and internal - external stakeholders’ interaction (Rahimi, Kenworthy and Balakrishnan, 2018). Others have posited that innovation is delivered through projects and by implication project management and that the innovation depends on adoption of a stakeholder approach as opposed to process approach to project implementation (Murphy, Heaney and Perera, 2011). The suggestion that the innovation process is part of or is an integral part of a project implies that stakeholders in a project may influence the process.

## Innovation within Oil and Gas Industry

Within the oil and gas sector Swart (2016 citing Doblin Inc. 2008) identified ten types of innovation spread across three categories namely: configuration, offering, and experience innovations. Within the configuration category is talent and assets alignment (structure) in line with how the organisation intends to make money (profit model), the network connections for creating value (network), and the methods used to do the work outside operations (processes). Within the offering category is product performance and product system. The former relates to optimising the effective extraction of core products and the later to innovating the product system in terms of production and use of both product and by-products. The experience category incorporates services that either support or enhance the core operations, the channels that determine interaction with stakeholders and creation of new markets, presentation of the business’ brand, and engagement with customers and stakeholders. Swart (2016) found that 65% of innovation in the oil and gas upstream industry in Canada was focused on the offering (product performance and product system), 29% on configuration and only 6% on experience.

In the downstream oil and gas sector, innovation would largely relate to experience (service, channel, brand and stakeholder engagement.  Thus, for purposes of this study a combination of Alhaj’s (2016) and Sawhney et al. (2011) definitions will be adopted as they go beyond just the products to include processes and methods and, in that way, offering better understanding and giving measurability of the innovation process within downstream oil and gas sector. Innovation in this instance is therefore defined as applying new methods to improve product and service delivery processes (channel) within a business or sector in a way that creates new value for customers. According to this proposed definition, it is not enough that new methods are applied if their application does not translate to added value or new value to the end user. In downstream EPC projects the end user or customer is the organisation that commissioned the project or that contracted the EPC provider.

## Innovation and EPC Projects

Although one of the advantages of EPC projects has been cited as opportunity for innovation and faster delivery of projects (Singh and Tiwari, 2015), in the construction industry they have been associated with low levels of innovation (Construction Industry Institute, 2010).  EPC projects are lauded for faster delivery of project deliverables through use of cross-functional teams and having parallel activities within the same project (Mahmoud-Jouini, Midler and Garel, 2004). However, this may influence innovation in a project given that among drivers of innovation is relationships-based knowledge sharing. How to balance on-time delivery of project outputs while promoting innovation inducing learning among project actors within an EPC project becomes a challenge.

## Drivers and Enablers of the Innovation Process

In a study of innovation in the construction industry, and in the context of EPC projects, the Construction Industry Institute (2010) identified enablers of innovation in that sector as having a supportive culture; allocation of both financial and human resources; supportive processes; adoption of a new risk perspective that focuses on its management than aversion; leadership learning; collaboration; and customers. These enablers have been highlighted elsewhere in literature, for example Persaud (2007 citing Teece 1986; Nakamura, et al., 1997) emphasized collaboration as a critical driver of innovation.

### Organizational context

Innovation has been associated with organisational context (Biscotti, D’Amico and Monge, 2018). Organisational context refers to its systems, processes, and beliefs that influence the behaviour of individuals within it (Gibson and Birkinshaw, 2004).  Brion, Mothe and Sabatier (2010) posited that an organisation’s context is made up of its performance management systems, formalisation, level of creativity, appetite for risk, and whether combining these leaves it with a short-term or long-term focus. They aver that innovation is better served by having a long-term focus. Also emphasizing the importance of organisational context, Alhaj (2016) found that in both the public and private sector, organisational context influenced innovation through its influence on social capital and knowledge sharing.  Noting that project-based organisations provide a unique context for innovation, Keegan and Turner (2002) investigated, among other things, whether project-based organisations provide a context that is supportive of innovation, whether they view innovation as always desirable, and whether they are cautious in implementing innovation strategies. They concluded that a company’s environment or context can have contradictory influence on its innovation orientation in that while it may exert pressure to be more innovative, government and other regulatory authorities’ guidelines may forestall any risk taking and therefore any innovation. Another context issue relates to time constraints within the project being implemented. Keegan and Turner (2002) concluded that the need for a project’s adherence to short-term deliverables within set time, cost and quality controls may compromise innovation since slack and redundancy foster innovation. This could be more so in EPC projects where the contractor has to coordinate different players to deliver the end product / service to the client. Hence Keegan and Turner’s (2002) observation that while executive management can ensure channelling of resources and attention to innovation opportunities, fear of risks associated with failure may be an impediment seems applicable.

Aspects of organisational context deemed relevant for innovation within a project context are project governance (Joslin and Müller, 2015); organisational culture (Tian et al., 2018); organisational capital (Chitsazan, Bagheri and Yusefi, 2017; Prester, Podrug and Daraboš, 2016); and knowledge sharing (Al-Husseini and Elbeltagi, 2015; Yeşil and Hırlak, 2013).

### Project governance

Project governance constitutes part of organisational context that affects or influences project innovation.  A project has multiple levels of governance which include the governance of the main or parent organisation, the contractors and sub-contractors, the suppliers, and relationships among the parties. Project governance embodies the project’s value system, responsibilities, processes and policies that permits projects to accomplish the organisation’s rationale for initiating the project in the best interest of all its stakeholders both within and outside the firm (Müller, 2009). It provides the framework for project decisions (Garland, 2009) as it provides “the approaches, authorities, accountabilities and processes to define the objectives of organizations/ projects, provide the means to achieve those objectives, and control progress” (Müller et al., 2016, p.958 citing OECD, 2004). Musawir et al. (2017) found that effective project governance could be a catalyst for the project’s benefits management process through clarification of roles, responsibilities, and accountabilities.  They also found effective project governance and benefits management to positively impact project success. Given that project benefits are the ultimate deliverables of any project, and that they are in the form of value addition activities which include innovations, project governance creates a context that aids innovation within a project as it affects stakeholder engagement. As will be discussed in a subsequent section, project stakeholders have been associated with innovation within a project.

### Culture and innovation

Organisational context includes the organisation’s culture. Organisational culture has been associated with innovation as either aiding or impeding it (Tian et al., 2018). Organisational cultures that are innovation oriented (Brettel and Cleven, 2011) and those that are learning oriented (Škerlavaj et al., 2010) have been associated with positive innovation outcomes. An organisation is described as having an innovation orientation culture when it possesses a set of values, norms and artefacts that facilitate the organisation’s innovativeness (Tian et al., 2018 citing Stock et al., 2013). An organisation with a learning culture is characterised by a focus on information acquisition, interpretation, and resultant changes in behaviour and cognition and thus creating a climate that facilitates the transfer of learning and knowledge necessary for innovation. Similarly, the culture of an EPC project as relates to information sharing practices and within project learning can be expected to aid innovation.

### Organizational Capital

Organisational capital associated with innovation is largely not tangible as it is intellectual. Intellectual capital is embodied in those elements of an organisation’s capabilities, knowledge, processes, networks and strategies that enable it to create value or competitive advantage (Chitsazan, Bagheri and Yusefi, 2017 citing Hsu and Fang, 2009). It includes human, structural, internal social, and external social capital (Prester, Podrug and Daraboš, 2016).  Following a review of empirical research on intellectual capital as part of organisational capital, Inkinen (2015) concluded that it had a strong influence on organisational innovation performance.

Human capital are the competencies, capabilities and all forms of knowledge held by the employees of the organisation. It is embedded in the skills and knowledge held by the organisation’s employees. Studies have found a positive relationship between the quality of human capital and innovation while others posit that human capital is a source of knowledge and strategic renewal (Inkinen, 2015).

Social capital is based on relationships and is at times referred to as relationships-based capital. It is the total of the actual and potential resources ingrained within and accessed through a network of relationships (Nahapiet and Ghoshal, 1998). It is therefore the value of the organisation’s social relations (Reed et al., 2006). Social capital is both internal and external to the organisation. Internal social capital is in the form of non-formal relationships within the organisation. External social capital is the value of relationships with customers, suppliers, allies, local communities and any other parties outside the organisation (Inkinen, 2015 citing Wu et al., 2007; Cabrita and Bontis, 2008; F-Jardón and Martos, 2009; Hsu and Fang, 2009). Value derived from relationships can be found in both the organisation and individuals within it as indicated by Yang and Lin (2009) who associated relational capital with the value of an organisation’s internal relationships. Another relationships-based capital is customer capital which is the valuable knowledge derived from customer-supplier relationship and from the marketing channels (Jean, Kim and Sinkovics, 2012).

Social capital has been found to be a key factor in the attainment of high levels of innovativeness through generation of productive ideas and collaboration within an organisation (Inkinen, 2015).  Prester et al. (2016) found that external social capital has the highest impact on product innovation while process innovation was found to have been most affected by human capital, external social capital and structural capital and least by internal social capital. In a study focusing in the banking sector, Elsetouhi, Elbeltagi and Haddoud (2015) found that organisational capital is necessary for innovation to occur in an organisation as it creates an environment that nurtures intellectual capital derived from human capital, customer capital and social capital. In a project context, the three (human, customer and social capital) are embedded in different project stakeholders. Their shared focus on innovation within a project, it would seem, is partly dependent on organisational capital which is part of the project environment or context whether or not it facilitates the development of intellectual capital and then innovation.

Structural capital consists of knowledge assets imbedded within the company. It includes intellectual property such as trademarks, patents and copyrights, institutional memory, methodologies, administrative processes, organisational knowledge management processes, strategic direction and culture (Inkinen, 2015). Structural capital provides a supportive framework for human capital to perform (Hejazi, Ghanbari and Alipour, 2016).  In an EPC project, methodologies, administrative and management processes which are part of structural capital reside among project stakeholder groups and spreads through both formal and informal interaction.

Andersson (2007) presents innovation as involving people experiencing social processes that remodel the way they think, act and interact and in the process leading to different perspectives of looking at issues resulting in innovation. From a social capital perspective, knowledge is an organisational resource embedded in a network of social relationships (Hau et al., 2013) and in routines (Kim et al., 2012) so that as project stakeholders interact knowledge sharing occurs. This being the case, interaction among project stakeholders can lead to innovation. It can therefore be proposed that innovation within an EPC project depends on the contexts within participating project organisations in terms of state of relevant forms of organisational capital and that the more there is social interaction among project stakeholders the more there will be innovation within a project.

### Knowledge sharing

Knowledge acquisition, creation and sharing has been recognised as necessary for innovation (Al-Husseini and Elbeltagi, 2015; Yeşil and Hırlak, 2013; Kamaşak and Bulutlar, 2010; Nonaka, Von Krogh, and Voelpel, 2006). Knowledge sharing involves the mutual exchange of both tacit and explicit knowledge in order to create new knowledge (Kamaşak and Bulutlar, 2010 citing Van Den Hooff and De Ridder, 2004). Effective use of new knowledge has been associated with innovation (Kamaşak and Bulutlar, 2010 citing Dougherty et al., 2002). Kavin and Narasimhan (2018) posit that the basis of innovation is the combination of ability to leverage new knowledge from the supply-network, absorptive-capacity and investment in research and development. Whether new knowledge is exploited to produce new innovative products depends on the subsistence of innovation nurturing practices. Wang and Wang (2012) found that innovation was facilitated by sharing both tacit and explicit knowledge with the former having more influence on the quality of innovation and the latter on the speed of innovation and performance. Explicit knowledge is institutionalised knowledge that is codified in some form within the organisation (part of structural capital) while tacit knowledge exists within individuals having grown out of their experiences and is shared through interaction (part of human capital). Since tacit knowledge sharing is dependent on people willingness to share it, its transmission is affected by the state of human relations in a given situation (Wang and Wang 2012). Trusting relationships in the knowledge sharing process have been found to weaken barriers to knowledge sharing (Bakker et al. 2006). Kucharska and Kowalczyk, (2016) found trust to particularly affect the sharing of tacit knowledge in a project environment. It can therefore be expected that where there are high levels of trust among project stakeholders, there will be more knowledge sharing resulting in higher innovation performance. Since EPC projects have been noted for being both labour and knowledge intensive to an extent that management of such projects is predominantly a process of knowledge management, innovation can be expected to be derived from effective knowledge integration (Zhu et al., 2014).

## Measures of Innovation

Innovation measurement is a highly contested area with academic research so far not having been able to come up with an overall framework for measuring it and issues of how and what to measure remaining unresolved (Dziallas and Blind, 2018). This is compounded by the multiplicity of innovation types. Gault (2015; 2016) presents examples of innovation types as: making available a new product or one with significantly changed characteristics to potential users (product innovation); introducing significantly changed production or delivery processes or techniques (production or delivery innovation); introducing significant changes to workplace organisation and business practices (organisational innovation); and a significantly changed way of bringing products to market (marketing innovation). According to Janget et al. (2017) innovation can be measured through inputs, throughputs, outputs and outcomes. Inputs are what were identified in this review as enablers of innovation. The enablers of innovation that have been discussed constitute inputs of the innovation process.

### Measuring innovation through inputs

Management of innovation is an organisational problem as it calls for the coordination of different departments in a company so that successful innovation is related to how well a company selects and manages projects.  According to Mohnen and Hall (2013) innovation can be measured through its inputs so that measuring the extent of their subsistence can be indicative of whether innovation is taking place or is likely to take place. It also provides areas that can be focused on when assessing stakeholder influence on the innovation process.

Measuring innovation through inputs is based on measuring its indicators so that the indicators serve as proxy measures of innovation. Dziallas and Blind (2018) categorize product and process indicators of innovation into ex-ante and ex-post criteria and suggest that using innovation indicators is a potential solution to the problem of innovation measurement. The indicators have been classified into hard and soft with hard indicators being quantitative and soft indicators being qualitative (Dziallas and Blind, 2018). Indicators can also be classified as directly or indirectly influencing the innovation success. Examples of direct indicators include percentage of ideas that pass the viability for commercialization test (Dewangan and Godse, 2014). Examples of indirect indicators include the novelty or newness to business; the process of planning and monitoring of the innovation process and its management (Dziallas and Blind, 2018 citing Duhamel and Santi, 2012). Specific to EPC projects, absence of effective communication, slow decision making and owner-driven change orders were found to affect the performance of engineering and construction phases (Habibi, Kermanshachi and Rouhanizadeh, 2019) and by implication innovation within those phases.

Haar (2018) posits that in fact approaches to measuring innovation projects are linked to those of typical project control to an extent that some indicators may be transferable between the two. Despite this though, there still remains a need for a specific framework for single work teams (Haar, 2018) as is the case with EPC projects. Further, use of indicators as measures of innovation has been criticised for neglecting that within a company innovation is not just linked to a single project but rather to the whole company involving even those not necessary involved in the project (Fischer et al., 2015).

### Measuring innovation through throughputs and outputs

Throughputs represent the intermediate results of innovation.  They refer to the quantity and quality of innovation such as the number of innovations over a given time. Janger et al. (2016) suggest that such measures are related more to knowledge creation capability than to converting the knowledge to some economic benefit. Outputs on the other hand are the direct results of the innovation process. They include things such as introduction of a new product or service on the market in the case of product innovation and of enhancement in operating processes or procedures in the case of process innovation. In a study investigating process innovation in a manufacturing company, Scafuto et al. (2018) identified output measures of process innovation as increase in efficiency, reduction of costs, improved internal practices and deploying exploitation strategies.

### Measuring innovation through outcomes

Innovation outcomes are the results derived from the introduction of innovations. Where there is product innovation the product has to be accepted by customers while a process and organisational innovation must result in reduced or containment of costs and other inputs (Janger et al., 2017). The outcomes can be at a micro (within the organisation) and at a macro (other interested parties) level. Further the outcomes may not all necessarily be economic as they may include health and environmental issues.

According to the Oslo manual (2005) innovation outcomes are “the observed effects of innovations” (p.165). Scafuto et al. (2018) found process innovation to enable product innovation. In that context product innovation can be used as an outcome of process innovation. In an EPC project, process innovations in the engineering and procurement phases can therefore result in product innovation in the construction phase. Oslo manual (2005) recommends that outcomes be observed within three years of occurrence.

For purposes of establishing the association between stakeholders interaction and  innovation in a EPC project context, this study proposes to focus on innovation measures guided by Gault (2016) definitions of innovation types  as: making available a new product or one with significantly changed characteristics to potential users (product innovation); introducing significantly changed production or delivery processes or techniques (production or delivery innovation); introducing significant changes to workplace organisation and business practices (organisational innovation); and a significantly changed way of bringing products to market (marketing innovation). Gault’s (2016) classification of innovation measures bears resemblance to the Oslo manual measures that are classified as markets for the company’s products (marketing innovation), production and delivery (product innovation), business organisation (organisational innovation). Oslo manual includes an additional measure classified as economy, society and the environment.

Projects are meant to speed up implementation. Organisations that adopt a project approach intend to have speed to market in the projects they are implementing. Innovation therefore within such projects has to adhere to the need for speedy project implementation or for moving through the project life cycle at a speed that enables the organisation to maintain or enhance its competitiveness. Innovation speed is the time that passes between initiation of the innovation and the commercialisation of the formulated product or service (Wang and Wang, 2012) and the intention is to shorten the period since the success of new product or service is associated with speed-to-market (Carbonell and Escudero, 2010 cited in Wang and Wang, 2012). Speedy project implementation can therefore in itself be an outcome of innovation.  Wang and Wang posit that “innovation speed is a team embodied, socially complex capability” that depends on team social relations. In an EPC project environment, the team consists of multiple stakeholders. In that regard the speed of innovation within the project is a complex capability that resides within the project stakeholders.  Timely execution of a project’s phases can therefore be used as an outcome measure of innovation throughout the phases of an EPC. Timely execution outcomes include the time taken to come up with usable designs (Engineering Phase); to procure required inputs (Procurement) and to bring the intended finished product or service to market or usable condition (Construction).

## Summary

While there are several definitions of innovation, there is consensus that it results in the introduction of something new and valuable whether in terms of the product, the production process, or the way an organisation functions so that it is at product, process and organisational level (Camisón and López, 2010; Jiménez-Jiménez and Sanz-Valle, 2011). It may be transformational through introducing fundamental changes or can be incremental. It may also be restricted to within a single organisation (closed) or involve several organisations (open). The element of whether an innovation has resulted in something valuable is determined by the intended direct and indirect beneficiaries of the innovation, in a project context, the stakeholders. That being the case, stakeholder relationships would be a critical factor in the innovation process from inputs, throughputs, outputs and outcomes. A question that arises is that since stakeholders determine whether or not the “new” has created value, what role and how much influence do they have on the innovation process?  Further, given that innovation is nurtured by knowledge sharing, and that in an EPC project knowledge resides in the people involved in the project, the stakeholders, a question arises on how such knowledge influences innovation within a project. The next chapter discusses project stakeholders in each phase of the EPC project, their influence and engagement in the context of networks and how this impinges on knowledge flow and therefore on innovation.

# Project Stakeholders

## Introduction

This chapter defines project stakeholders (Section 4.2) and proceeds to discuss perspectives of stakeholder theory (Section 4.3); stakeholder analysis process (Section 4.4); and stakeholder management (Section 4.5). Stakeholder management is discussed from the perspective of interface, engagement and implications for innovation. The chapter proceeds to discuss stakeholder influence on within project innovation. It concludes by discussing methods of measuring stakeholder influence in a project and highlighting Aragonés-Beltrán, García-Melón and Montesinos-Valera (2017) model as presenting a possible avenue for measuring stakeholder influence on innovation in EPC projects.

## Project Stakeholders

Freeman et al. (2010, p.9) define a stakeholder as “those groups and individuals who can affect or be affected” by the activities of an organisation as it seeks to achieve its objectives. A stakeholder in a project context refers to a person, a group or an institution that may be affected or may affect the planned actions of the project (Bjugn and Casati, 2012 citing Jepsen and Eskerod, 2009). Such stakeholders may be both internal and external to the project initiating organisation (Bjugn and Casati, 2012). Typically, project stakeholders include Project owners; Gate Keepers; Project planners; design engineers; and Project Management Offices.  Stakeholders are identified through a systematic stakeholder analysis process. According to Bjugn and Casati (2012), while the identification process starts during project initiation phase, a detailed analysis is conducted during the planning phase. Project stakeholders play various roles throughout the project life cycle and these are better understood within the context of stakeholder theory.

## Stakeholder Theory

At the core of stakeholder theory is that a business exists to create value for all its stakeholders and not just the shareholders and succeeds when it manages to focus on mutual interests as opposed to trade-offs (Freeman et al., 2010). It analyses the relationship between the organisation and its various stakeholders. The unit of analysis therefore are the relationships between the organisation and the stakeholders and not the organisation per se (Freeman et al., 2010). According to the theory, stakeholders derive their status from their ability to affect the business and its other stakeholders.  It facilitates classification of stakeholders according to the roles they play. In that regard from the roles, the influence exerted can be determined.

Literature (Savage, Dunkin and Ford, 2004; Phillips, Berman, Elms and Johnson-Cramer, 2010; Wagner Mainardes, Alves and Raposo, 2012) highlights six main assumptions of stakeholder theory which are:

- Organisations get involved in relationships with multiple interest groups who influence the organisation or are themselves influenced by it;

- The relationships are in terms of both the processes and results for both the organisation and the stakeholders meaning that the influence can be exerted at both process and results level;

- All interests of legitimate stakeholders are of intrinsic value with none being superior to others implying that they all need to be considered;

- Managerial decision making is involved in balancing the interests;

- Methods used by stakeholders to influence decision making processes in the organisation so that they are in their favour are identified;

- The organisation must seek to understand, reconcile and balance the interests of the multiple stakeholders.

Stakeholder theory perspectives tend to be predicated on any or a combination of these assumptions.

### 4.3.1	Stakeholder theory perspectives

Donaldson and Preston (1995) identify three interlinked aspects of stakeholder theory which are descriptive, instrumental and normative. The descriptive perspective focuses on describing how businesses are run and identifying stakeholders and their interests (Sangle and Ram Babu, 2007).  They posit that a key attribute of stakeholder management is simultaneously paying attention to all stakeholders.  This view is influenced by the assumption that interests of legitimate stakeholders all have intrinsic value and deserve equal consideration. This position may be difficult to implement or operationalise in an EPC environment where the interests of the project owner take precedence.

The normative perspective of stakeholder theory focuses on identifying the stakeholders, the nature of their responsibilities, and factors that influence them. It also focuses on management’s obligations towards stakeholders and the mechanisms used to resolve disputes over clashing interests (Reed, 1999). It highlights the need for making moral decisions. The normative perspective therefore leans more towards responsible innovation (Pellé and Reber, 2015) according to which there should be interaction among innovating stakeholders and other stakeholders in assessing ethical and societal desirability of an innovation (Taebi et al. 2014).

The instrumental perspective focuses on the effects of stakeholder management on achievement of business goals. It assumes that stakeholders can affect whether or not an organisation meets its objectives (Preble, 2005). From this perspective, stakeholders need to be treated instrumentally (Preble, 2005). The interaction between management and stakeholders therefore is premised on the perceived benefits each party hopes to get from the relationship. Stakeholders are also identified for their usefulness, agency capacity and capacity to influence areas that could benefit the organisation (Bourne and Walker, 2005). It has been used to explicate the effect of stakeholder management on businesses performance related issues such as revenues, development of social capital and knowledge capturing (Hörisch et al., 2014; Mathur, Price and Austin, 2008). This perspective’s link to influencing innovation is its assumption that stakeholders can affect organisational outcomes.

Hörisch et al. (2014) extended Donaldson and Preston’s (1995) aspects to include integrative stakeholder theory that brings together the descriptive, instrumental and normative aspects. The integrative perspective sees an inextricable link among the descriptive, instrumental and normative perspectives of stakeholder theory. From this perspective Horich et al. (2014) distinguish between stakeholder management, which they describe as manipulative, and managing stakeholder relationships. Stakeholder influence on innovation, can be understood from an integrative perspective given that innovation involves and thrives on relationships. The integrative perspective therefore can be combined with Rowley’s (1997) relational network perspective. This sees stakeholder relationships as occurring within a complex network of interlinked relationships so that the behaviour of stakeholders, including their decision making, emanates from their interactions within a social structural environment (Missonier and Loufrani-Fedida, 2014, citing Rowley, 1997). From this perspective, stakeholder influence would therefore occur within the network through relationships. Studies have used the relationships-based perspective of stakeholder theory to better understand stakeholder influence. Ruggiero et al. (2014) used the theory to understand the influence of stakeholders in a community renewable energy study.  For purposes of developing a framework for understanding the interaction of stakeholders and innovation in an EPC project, the integrative and relational network perspectives of stakeholder theory is more appropriate.

## Stakeholder Analysis Process – Identification and Classification

Regardless of perspective, fundamental to stakeholder theory are two factors, classification of stakeholders and mechanisms of organisation (Wagner Mainardes, Alves and Raposo, 2012).  For Rowley (1997), among others, the fundamental issues of stakeholder theory is identifying the stakeholders and establishing the type of influence they exert on the organisation. Within a project the issue therefore is to identify the stakeholders and what influence they have on the project in terms of decisions made among which are innovation related decisions. Main stages of the stakeholder analysis process are identification and attributing values to stakeholders which also includes determining their power to influence (Bjugn and Casati, 2012).

### Identification of stakeholders

Stakeholders can be divided into two broad groups, internal and external. Internal stakeholders have been defined as those with formal connections to the project such as the owners, employees and customers while external ones are those affected by the project (Olander, 2006 citing Gibson, 2000). Carroll and Buchholtz (2006) classify stakeholders as either primary or secondary. Primary stakeholders being those directly and contractually involved in the project to an extent that its delivery depends on them. Secondary stakeholders have no formal relationship with the project owner. Rolstadås and Schiefloe (2017) add to primary and secondary stakeholders what they term tertiary stakeholders. These stakeholders are local interested parties such as non-governmental organisations. Scholes and Clutterbuck, (1998) identify stakeholders based on their power of influence, impact on the organization and affinity with the organisation’s objectives. Gürtler and Lindemann (2013) suggest that stakeholder identification includes identifying their interests, motivations and conflicts of interest.

These categorisations of stakeholders are simplistic given that projects are complex both structurally as shown by both the number and interdependence of elements and in terms of associated risks relating to both the project goals and methods. This is more so in EPC projects where complexity arises from the multiplicity of actors such as those within the client organisation that owns the project end product, the main contractor, the several sub-contractors, and other interested publics. Eyiah-Botwe, Aigbavboa and Thwala’s (2016) observation that the role of the same stakeholder in a project may change from time to time seems more consistent with the complexity of projects. In that regard classification of stakeholders can be viewed as not representing permanent labels but rather as transitionary since a stakeholder’s role in a project may change as the project progresses. That notwithstanding, at any given time in a project, stakeholder mapping clarifies relationships among stakeholders. In the context of open innovation projects, EPCs present such opportunities. Gürtler and Lindemann (2013) posit that because of resource and time constraints it is not possible to involve every stakeholder in the project and hence the need to categorise stakeholders based on their innovative capacities and influence on the project. They group stakeholders into three categories, those with high innovative capacities and high influence on the success of the project; those with high innovative capacity and low influence or low innovative capacities and high influence; and finally those low on both innovative capacities and influence. It can therefore be assumed that because stakeholders exert different levels of influence on innovation in a project, within an EPC project it is necessary to establish the influence of specific stakeholder groups.

### Stakeholder classification / mapping

Main stakeholder mapping models are Mitchell et al.’s (1997 cited in de Oliveira and Rabechini Jr, 2019) Salience model based on priority of competing claims and Olander and Landin’s, (2005) stakeholder matrix of power and interest model. According to the Salience model stakeholders can be classified according to their power to influence the organisation, the legitimacy of their relationship with the organisation, and the urgency of their demands within or from the organisation. Using it (combined with stakeholder matrix of power and interest model) Oander and Landin (2005) concluded that it is critical to evaluate the demands and interests of stakeholders during planning and implementation of a project right up to its implementation. This implies that these may change. While these frameworks simplify the classification of stakeholders, in some project contexts there is more complexity. Rowley’s (1997) framework which is based on network density and the centrality of the organisation seems more appropriate for mapping stakeholders in an EPC project environment.

Rowley (1997) explored how the structure of an organisation’s stakeholder relationships affected the way the organisation responded to the pressure exerted by stakeholders. He posits that the density of the stakeholders’ network surrounding the organisation, and the centrality of the latter’s role within the network will influence the extent to which it is influenced by, or it influences, the network as seen by its responses to stakeholder demands. Rowley (1997) further contends that when the organisation does respond, it does not respond to individual stakeholder interests but to those of the whole network. In that regard, it can be proposed that when an organisation innovates in response to stakeholder influence, it is the influence of the stakeholders as a collective that results in innovation. In such a situation, it is not sufficient to classify stakeholders based on the relationship with a single stakeholder but rather the whole pattern of relationships across multiple stakeholders, what Nohria (1992 as cited in Rowley, 1997) describes as the interaction of interactions. In the situation the organisation takes four possible behavioural stances: as commander, compromiser, subordinate or solitarian (Rowley, 1997). In an EPC project the lead contractor is the organisation that takes this role as it relates to the project owner and the other parties that are sub-contracted and other interested publics; and as it seeks to balance stakeholders’ power and influence to ensure the attainment of project objectives. It can be expected that such balancing includes decisions on innovative ideas from the various stakeholders.

### Stakeholder power and influence

There have been various streams of research on stakeholder influence such as assessing the influence (Mitchelle, et al. 1997); development of stakeholder impact analysis model (Olander and Landin, 2005); variation of stakeholder influence strategies during different stages of a project (Aaltonen and Kujala, 2010);  impact of behaviour of internal stakeholders on project success (Beringer, Jonas and Kock, 2013); stakeholder inclusiveness and expansion of the organisation’s pool of capabilities (Eskerod, Huemann and Ringhofer, 2015); measuring stakeholder influence from perspective of Project Managers using Analytical Network Process (Aragonés-Beltrán, García-Melón and Montesinos-Valera, 2017); understanding the behaviour of stakeholders from the perspective of networks the stakeholder is involved in; and stakeholder management as an instrument for directing projects to produce results that deliver value to all stakeholders (Uribe, Ortiz-Marcos and Uruburu, 2018).  Eskerod and Larsen (2018) proposed that a comprehensive understanding of stakeholders is better derived from a stakeholder analysis that is inclusive of their perceptions on the past, present and future resulting in what they term a “shadows of the context” which unifies all three.

Stakeholder influence varies during the different stages of a project in terms of which stakeholders are influential at what stage of a project as project priorities change (Olander 2006 citing Jawahar and McLaughlin 2001). Stakeholders affect (or influence) a project through resource contribution towards the project which resources include expertise. Eskerod and Larsen (2018) posit that the relationship between a project and its stakeholders must be viewed in terms of embeddedness where the two parties influence each other during the entire project duration. Developing relationships with stakeholders has been identified as an important aspect of project management as project stakeholders have been linked to project success because of, among other reasons, their contribution in terms of expertise, decision making and good ideas (Eskerod and Larsen, 2018).   Because project stakeholders can decide whether to contribute, not contribute or withdraw their contribution to the project, managing relationships in a manner that ensures their continued willingness to contribute to the project is critical as they present both a threat and an opportunity for a project (Eskerod and Larsen, 2018). One of the potential opportunities is that of harnessing the skills and competence contribution for use in decision making in order to come up with innovative ideas. That said, it would be reasonable to assume that throughout the various stages of a project, stakeholders exert specific forms of influence which could affect innovation within the project and hence the importance of stakeholder management.

## Stakeholder Management

Rajablu et al. (2015) define stakeholder management as a process within which the needs and expectations of stakeholders are identified, agreements are reached, and mechanisms are put in place to ensure that their objectives are met. To this definition Aragonés-Beltrán et al. (2017) add the development of strategies for engaging stakeholders in decisions and implementation. While acknowledging that it is a process, Bourne and Walker (2005) aver that it takes place throughout the life of the project.

Stakeholder management is predicated on stakeholder classification. It is an instrument for directing projects and managing associated risks (Uribe, Ortiz-Marcos and Uruburu, 2018; Muriana and Vizzini, 2017) which makes it an integral part of any project. It has been found to have a relationship with management decision making (Eskerod, Huemann and Ringhofer, 2015; Eskerod and Vaagaasar, 2014). Stakeholder management within a project is not static but changes over time suggesting that even innovation dynamics may change during the different stages or phases of a project (Walker, Bourne and Shelley, 2008). Further it encompasses a diversity of skills such as interpersonal, social communication and emotional intelligence skills (Azim et al., 2010) which could have implications for stakeholder influence on innovation.

Approaches to stakeholder management can be put in two categories: prescriptive and relational.  According to the prescriptive approach, the potential influence of stakeholders on a project makes it imperative that they be assessed and their interests mapped throughout the life of a project (de Oliveira and Rabechini Jr, 2019 citing Cleland, 1986; Mitchell et al., 1997; and Bourne and Walker 2005). The relational approach highlights the importance of relationships and interaction among stakeholders throughout a project’s life cycle (Mok, Shen and Yang, 2015; Bourne, 2015). The two approaches are not mutually exclusive as they can be combined to increase effectiveness with the prescriptive approach being the starting point, followed by relationships that are built on trust (de Oliveira and Rabechini Jr, 2019). The trust in relationships facilitates involvement and engagement and comes through from management of the interface with and among stakeholders.

Rogers’ (2003 cited in Hassan Al-Ali, 2017) model of stakeholders and innovation hinges on individuals sharing information with some in the network playing a more influential role than others. Rogers (2003) identifies major stakeholder roles as opinion leaders, change agents and champions. Opinion leaders play a leading role in informally influencing others. The role is therefore not necessarily formal. A change agent is usually in a formal role and influences a client to accept innovation decisions that are desired by the change agent while ignoring those not desired by the change agent. Change agents work with a change aide who informally influences a clients’ innovation-decisions. Champions advance the innovation cause ensuring the overcoming of any negative sentiments that may be invoked by an innovation (Hassan Al-Ali, 2017 citing Rogers, 2003). An understanding of the role of stakeholders in terms of being opinion leaders, change agents, champions and or their value contribution is obtained from understanding stakeholder interface management.

### Interface Management

Stakeholder interface management relates to interaction with others including aspects such as communication, coordination, information exchange, and resolving conflicts among participants (Shen et al., 2018). The complexity of EPC projects requires extensive collaboration and therefore interface management throughout the project’s life cycle. Given that interface management has been positively associated with EPCs (Shokri et al., 2015) it can be expected that stakeholder influence or contribution to innovation in a project would, to some extent, depend on the state of interface management as reflected by communication, coordination and collaboration. Shen et al. (2018) summarised formal EPC interface management procedures as involving identification of main interfaces early on in the project; documentation of interface data and information such as the nature of the interface, responsibilities of main players and any other related requirements; disseminating interface information to concerned parties; communicating to ensure that interface related assignments are executed and terminating the interface when it is agreed that it has served its purpose. In an EPC the interface has multiple players representing different organisations who also have to manage other interfaces, a situation that could add to the complexity of its management. Where interface management procedures are in place, it can be expected that there is flow of information and knowledge and that project decisions are arrived at in a manner that facilitates innovation. Linked to interface management is engagement of stakeholders as part of building trust among them.

### Stakeholder Engagement

O’Riordan and Fairbrass (2014, p.123 citing ISO, 2010) define stakeholder engagement as “activities which are undertaken to create opportunities for dialogue between an organization and one or more of its stakeholders with the aim of providing an informed basis for the organization’s decisions.” Jonas et al. (2018) define it as a psychological state that results from the experiences of a stakeholder’s experiences from interactions that occur within a particular service ecosystem. From the definitions, stakeholder engagement is presented as both dialogue enabling activities and as a state of mind. In an EPC environment, engagement would therefore refer to a psychological state resulting from interacting with, first the main contractor of a project, and with sub-contractors through activities or mechanisms put in place to facilitate the interaction. This suggests that stakeholder engagement can be measured in terms of both the activities and a stakeholder’s state of mind.

From a service ecosystem perspective all stakeholder engagement dimensions (cognitive, behavioural and emotional) are considered in the innovation processes (Jonas et al., 2016). Collaboration of stakeholders in an innovation process is viewed as increasing the complexity of an innovation process as each stakeholder seeks to represent their interests. This notwithstanding, it is necessary for innovation success as there are opportunities for exchanging of resources and self – representation (Jonas et al, 2018 citing Vargo et al., 2015). In that regard stakeholder engagement is both a psychological state of mind and also a product of environmental influence as actors influence each other as they co-create an innovation (Jonas et al, 2018 citing Chandler and Lusch, 2014). Studies have shown that shared knowledge derived from engagement with both internal and external stakeholders, when properly managed by the firm, contributes towards its sustainable innovation orientation (Vargo, Wieland and Akaka, 2015; Ayuso et al. 2011).

Jonas et al. (2018) found that stakeholder engagement is influenced by individual and organisational factors such as shared or common experiences, being acquainted, self-representation, shared or common goals, trust, resource dependency, position in the hierarchy, institutional arrangements, and local closeness.

Generally, an organisation implements innovations through projects that involve engaging multiple stakeholders both within and outside. According to Jonas et al. (2018) engagement of a stakeholder does not remain the same throughout a project but varies over time. This echoes Wagner Mainardes, Alves and Raposo (2012) who found that relevance, mutual influence and participation are important explanatory factors of the relationship between an organisation and its stakeholders. This suggests that similarly, stakeholder holder involvement and therefore influence on a project would also fluctuate in line with their level of engagement as determined by relevance issues.

## Stakeholder Influence on Project Innovation

Collins dictionary defines influence as “the power to make other people agree with your opinions or do what you want.” Godenhjelm and Johanson (2018) conceptualise influence in terms of means used to influence. They identified discussion groups and panels, contacts, and press articles as means of influence. This suggests that influence is achieved through interaction.

Stakeholder influence within a project has been looked at from various perspectives including organisational financial performance; decision making; indirect influence through different networks (Barnett, 2007; Spitzeck and Hansen, 2010; Rowley, 1997, all cited in Ruggiero, et al., 2014); project success or failure (Berardi, 2013); and as dynamic and therefore changing (Mitchell, Agle and Wood, 1997). Focusing on the implementation phase of a project (Ruggiero, et al., 2014) found that stakeholders can influence a project in a positive or negative way, in that regard, influence is perceived as two dimensional, negative and positive or desirable and undesirable. Further they found that in “influencing” stakeholders can play multiple roles and that influencing can take place at a macro level, intercommunity, and intracommunity levels. The different levels at which influencing occurs and the aspect of multiple roles confirms that stakeholder influence varies during different stages of a project. One would therefore expect that there may be specific forms of stakeholder influence that are found at the engineering, procurement, and construction stages of a project that impact innovation within a project. Stakeholder influence on within a project innovation can be understood from appreciating how they go about securing their interests in the project. Godenhjelm and Johanson (2018) conceptualisation of influence in terms of means used to influence therefore presents possible ways of understanding stakeholder influence on innovation in a project.

Because of the focus organisations are placing on sustainability issues which also involve adoption of new technologies, studies have looked at the impact of innovation on stakeholders (Dew and Sarasvathy, 2007) with limited studies focusing on the influence of stakeholders or their impact on innovation. In a review of stakeholder theory in project management, Uribe, Ortiz-Marcos and Uruburu (2018) did not highlight any studies that look at the influence of stakeholders on innovation which could be indicative of the dearth of studies focusing on this aspect. They however, found that there is a relationship between stakeholder theory dissemination and project management. Since innovation has been found to be implemented through projects that points to a stakeholder theory – project management – innovation link.

West and Bogers (2014) focused on how open innovation involvement of organisational external stakeholders can provide sources of innovation and how organisations can leverage this to their advantage. Open forms of innovation suggest a role for external stakeholders as they participate together with the organisation to co-create better products and services (Watson et al. 2017; Roberts and Candi, 2014). Watson et al. (2017) found that organisational structures and processes developed for managing stakeholder interactions explicate how companies engage their stakeholders for sustainability innovation. They however also highlighted the need for cultural alignment and harnessing of different stakeholder strengths while also translating learning on an individual, team and organisational level.

In EPC projects, innovative procurement increases opportunities for innovation in construction productivity because of the design and construction integration. In such projects early stakeholder engagement has been associated with reduction of rework, unwarranted costs, low productivity and disputes, and quality enhancement. (Baharuddin, Wilkinson and Costello, 2013). According to Priemus (2009), on a design and construct project the contractor has a lot of design freedom which provides opportunities for innovation at both process and product level. The tight timescales and focus on completion within such projects create innovation opportunities because of the early appointment of the management contractor which gives the client organisation room for design flexibility (Miller et al., 2009). Innovation developed in such situations has been found to be co-developed by project stakeholders such as clients, contractors, sub-contractors, suppliers, consultants, designers and clients who all play a role in the process (Ozorhon, 2012).

## Measuring Stakeholder Influence

Aragonés-Beltrán, García-Melón and Montesinos-Valera (2017) investigated the individual influence of stakeholders on a project and how to measure it from the perspective of a project manager. They concluded by proposing a four - clusters, twelve item model of measuring stakeholder influence from the perspective of a project manager. The clusters are: Knowledge; Social skills; Assets and External. Knowledge is broken down into expert knowledge; professional competence and experience. Expert knowledge refers to knowledge possessed by a specific stakeholder; professional competence refers to knowledge a stakeholder derives from their professional training; experience refers to what a stakeholder would have lived through in the past. Social skills cluster includes representativeness, affiliating with others, and manipulating others.  Representativeness is one’s ability to represent their interests within the network of stakeholders using their social competences. Affiliating with others is the ability to build relationships, or alliances within the network. Manipulation is the extent to which one is able to realise their own goals through managing other stakeholders within the network. Assets cluster includes financial security, provision of resources and finances. Financial security is the financial stability of a stakeholder. Resources refers to the ability and willingness of a stakeholder to provide resources needed in the project, and provision of financials refers willingness and ability to provide finances for the project. External incorporates dependency on external factors, public image and hierarchical position. Dependency on external factors is the extent to which a stakeholder depends on a factor or factors that lies outside the network of stakeholders. Public image is the image a stakeholder has outside the network and hierarchical position is the power possessed by a stakeholder because of their position in the hierarchy of the network. Using this model and measuring influence from the perspective of the project manager, Aragonés-Beltrán, García-Melón and Montesinos-Valera (2017) set out to establish or identify the influence of each stakeholder on a specific project and how this could be measured. They concluded that the model permits a Project Manager to conduct a quantitative analysis of the influence of specific stakeholders on a project.

Bourne and Walker (2005) use the Stakeholder Circle model (Bourne, 2005) to assess stakeholder power and influence. The model facilitates identification and visualisation of stakeholder influence. The Circle maps-out distance of stakeholders from the project entity, nature of stakeholder interests, the scale and scope of influence and the extent of impact. Although the model has successfully been used as a standardised methodology for stakeholder analysis, it does not directly address the measurement component of stakeholder influence, at least in as far as EPC projects are concerned.

Social Network Analysis has been proposed as another method of measuring stakeholder influence. It combines degree of trust and level of consensus to establish the criticality of experts (Wu and Chiclana, 2014). The method is criticised for yielding complex analysis structures (Aragonés-Beltrán et al., 2017). While still to be validated by more studies, Aragonés-Beltrán et al. (2017) seems more appropriate for measuring project stakeholder influence on innovation because of its use of multiple criteria which permits it to account for the many possible positions from which a stakeholder can exert influence.

## Summary

This chapter discussed definitions of stakeholders noting that at the core of the definitions is that of individuals affecting or being affected by organisational activities as it seeks to attain its objectives. Stakeholder theory was discussed starting from assumptions on which it is predicated to the different perspectives of the theory, specifically: descriptive, instrumental, normative, integrative and relational network. Stakeholder analysis was discussed focusing on identification and classification followed by stakeholder mapping, power and influence. The relationship between a project and its stakeholders was noted to be one of continuously influencing each other, a situation Eskerod and Larsen (2018) summarised as embeddedness.  Stakeholder management, which was acknowledged to be predicated upon stakeholder classification, was discussed from the prescriptive and the relational perspective, and also from the perspective of interface management. The latter was noted for its influence on knowledge sharing and therefore on innovation.  Stakeholder engagement was discussed as corollary to interface management. It was highlighted that organisations implement innovations through projects that depend on multiple internal and external stakeholders who need to be engaged for innovations to succeed, a position that implies stakeholder influence on innovation. Finally, the chapter discussed ways of measuring stakeholder influence in a project the primary interest being to establish if such measurement methods can be applied to understanding stakeholder interaction and innovation within EPC projects where the innovation process has been noted to involve co-creation among multiple stakeholders.

The next chapter presents the study’s theoretical framework through discussing stakeholder network analysis as a lens for understanding the interface among stakeholders.

# Theoretical Framework

## Introduction

Chapter 2 reviewed literature on characteristics of the downstream oil and gas sector and noted that the complexity and capital-intensive nature of oil and gas sector projects are usually in the form of EPC projects that are characterised by multiple actors. Knowledge sharing in this context was deemed to present opportunities for innovation. Chapter 3 reviewed literature on innovation, its types,  and its outcomes which are its noticeable effects and can be reflected in products, processes and organisational functioning (Oslo Manual, 2005; Camisón and López, 2010; Jiménez-Jiménez and Sanz-Valle, 2011). In an EPC project context, timely execution of a project’s phases was viewed as a possible outcome measure of innovation. Project stakeholder relations were noted to play a critical role in the innovation process since innovation is nurtured by knowledge sharing, which knowledge resides in the project stakeholders. Chapter 4 reviewed literature on project stakeholders and noted that through their interactions, they exert influence on the project from various perspectives (Ruggiero, et al., 2014) including co-developing innovation (Ozorhon, 2012). It was observed that some have pointed to a link among stakeholder theory, project management, and innovation (Uribe, Ortiz-Marcos and Uruburu, 2018) to an extent that an analysis of relations or links among stakeholders may provide pointers to measuring project stakeholder influence on innovation (Aragonés-Beltrán et al., 2017). This chapter presents the study’s theoretical framework. Based on Social Network Theory it discusses stakeholder network analysis as a possible way of understanding the interface among stakeholders and in turn mapping out the interaction within and between stakeholder networks and product and process innovation in a specific EPC project. The chapter reviews literature on indicators for innovation measurement and adoption focusing on Feng and Crawley’s (2008) definition of a Stakeholder Value Network. The chapter starts by introducing Social Network Theory (Section 5.2) and proceeds to discuss stakeholder networks at each of the phases of an EPC project (Section 5.3; 5.4; 5.5); the interface of EPC phases (Section 5.6); Stakeholder Value Network (Section 5.7); and Design Structure Matrix (Section 5.8).

## Social Network Theory

Social Network Theory is to the effect that individuals are embedded in a web of social relationships and interactions (Borgatti, et al., 2009; Scott, 1988).  Social network analysis is premised on that relations and the patterns they form create social life (Marin and Wellman, 2010). Project stakeholders constitute a social network and interface among project stakeholders, when viewed from this perspective, occurs within stakeholder social networks. A social network-based understanding of interface among stakeholders can be achieved through first detailing the work breakdown structure of each phase of an EPC project. This is followed by mapping out stakeholder involvement at each stage to come up with a network of relationships that can indicate information and or knowledge flow within the network. This provides pointers to the flow of innovative ideas. Within an EPC project, stakeholder networks exist at least at three levels: within each phase (Engineering, Procurement and Construction); between phases (for example Engineering and Procurement) and across all phases. In social network parlance, each stakeholder represents a node connected to other nodes by relations and the connections constitute patterns studied as components of a social network during stakeholder analysis (Marin and Wellman, 2011).

This chapter discusses stakeholder networks through analysis of the Work Breakdown Structure (WBS) at each phase and mapping out the knowledge flow which, according to Baron (2010), constitutes the Knowledge Breakdown Structure (KBS). Project Management Body of Knowledge (cited in Brotherton, Fried and Norman, 2008, p.2) defines a Work Breakdown Structure (WBS) as:

"A deliverable-oriented hierarchical decomposition of the work to be executed by the project team to accomplish the project objectives and create the required deliverables. It organizes and defines the total scope of the project. Each descending level represents an increasingly detailed definition of the project work. The WBS is decomposed into work packages.

Globerson (1994) defines it as the backbone of proper project planning, execution and controlling involving the slicing or decomposition of a large project into small segments in an organised manner. Similarly, Brotherton et al. (2008) consider it as foundational and a key input to, for example, project schedule network diagrams and project organisation. In that regard it can also be considered as a critical input into tracing the flow of knowledge and ideas through the project.

In linking the WBS and the KBS Baron (2010) is in line with Zhu et al.’s (2014) contention that an EPC project is predominantly a process of knowledge management so that levels of innovation depend on effective knowledge integration; Hau et al.’s (2013) view that from a social capital perspective, knowledge is an organisational resource embedded in a network of social relationships; and Inkinen’s (2015) suggestion that social capital is a key factor in achieving innovativeness through generation of productive ideas and collaboration within an organisation. Along the same vein Marin and Wellman (2011) posit that interaction of employees from different organisations creates a confluence of ideas, expertise, and tacit knowledge in the process combining previously disconnected ideas leading to innovation.

## Engineering WBS

Engineering phase involves translating functional requirements into detailed drawings and specifications that reflect all aspects of the project deliverables (Baron, 2010). It comes up with designs, production of lists, specifications, data sheets of required equipment and materials, and issuance of required documents for the construction site. The engineering stage involves multiple specialised areas the main being process, instrumentation and control, layout and piping, electrical, civil, equipment, and safety. Two steps involved in engineering are basic engineering and detailed engineering. Basic engineering is handled by the client organisation and its outputs are used for the call to tender for the EPC project. This is beyond the scope of this study. Detailed engineering involves the design process which, according to Parraguez, Eppinger and Maier (2016), comprises a system with interdependent domains namely process, organisation, and product domain. The process domain consists of a network of activities, the organisation domain consists of a network of people and the product domain consists of a network of components. There are interfaces within each domain and across domains. Interfaces facilitate information flow across activities in the form of networks of interactions. Management of the interfaces is critical as it has implications for improvements in the design process and therefore for innovation opportunities as some of its outcomes are documents for purchasing and building of plant equipment; production of specifications and bill of quantities; and production of detailed installation diagrams. Main disciplines and therefore stakeholders at this stage of an EPC project in the downstream oil and gas sector are summarised in Table 5.1.

Table 5.1: Main disciplines at the Engineering Stage of EPC (Baron, 2010)

| ACTIVITY | Process | Equipment | Instrumentation & Control | Piping | Electrical | Civil | Safety |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Diagrams | X |  | X |  | X |  |  |
| Geographical drawings |  |  | X | X | X | X |  |
| Architectural drawings |  |  | X |  | X |  |  |
| Calculations | X | X |  | X | X | X |  |
| Equipment specification & requisition |  | X | X | X | X |  |  |
| Site works specification |  |  | X | X | X |  |  |
| Hazard and operability | X |  | X |  |  |  | X |

Engineering is the first and most critical part of an EPC project and has far reaching implications for the other phases (Yi, Lee and Ahn, 2019). Engineering interfaces with the project client through receiving functional requirements, client specifications and design codes and submitting documentation to client and receiving comments and obtaining approvals. It interfaces with vendors through receiving their documents and providing comments on the same. Interface with procurement is through documents for procurement in the form of for example, bill of quantities and specifications of quality. The interface with construction is through providing construction drawings and specifications.

Managing information quality and flow at the interface is, according to Baron (2010, critical at the engineering phase of an EPC. Information needing to be interfaced through exchanges includes project owner (client’s) technical requirements; design criteria, data on the site, information from the various engineering disciplines - one discipline serving as input for another, procurement and various equipment vendors and suppliers, construction contractors and other third parties. The exchanges are multi-directional and constitute a network of both formal and informal relationships. At a formal level information is collected and distributed through formal, controlled documents that are listed on a register (Baron, 2010). It includes information that serves as input to the design and is contained in the Design Basis document and can only be altered through a formal Query from the client. Where there is to be a deviation from contractual requirements such are captured through a Deviation Request that has to be formally approved by the Client. Interface agreements are used to capture any technical information discussed and or agreed with third parties.

Parraguez, Eppinger and Maier (2015) developed a modelling method integrating the network of people and the network of activities in a project and used network metrics for centrality and clustering to demonstrate a method for analyzing information flows between activities in complex engineering design projects. They illustrated how the network of information flows in a large-scale engineering project evolves over time. Given that information flow has been associated with the innovation (ideation, spread and adoption), understanding information flows within stages of a project can assist in studying innovation within an EPC project. Parraguez et al. (2015, p.4) define information flow as “the combination of information exchanges over a period of time and involves a sequence of information exchanges about usually interdependent design activities.” To that end the design of complex products and systems is considered a social process of transforming information. This implies that notwithstanding the formal processes of information flow, there is a parallel social process. Information flow defined Engineering design activities have been found to be connected by their information dependencies together with administrative controls.

## Procurement WBS

Micheli and Cagno (2016) found links between procurement and project deviations which made them conclude that procurement has the greatest impact on an EPC project because of the importance of procuring quality products and ensuring timeous availability. Mapping out procurement components facilitates identification of procurement related risks within the procurement or supply chain structure. This enables project team members to take necessary remedies to reduce risk exposure (Cagliano, De Marco, Grimaldi and Rafele, 2012). The remedies could include introduction of new procurement methods or enhancing existing ones. Main components of the procurement WBS are, having received specifications and quantities from engineering, development of bidders’ lists; generation of purchase order pro-forma; issuance of contracts pro-forma; transportation and logistics; warehousing; and release to construction. Throughout the process there is interface and knowledge flows among those directly involved in the procurement processes creating a knowledge network. There are also risks relating to both the quality and timely delivery of procured items. It is in that regard that Cagliano et al. (2012) propose use of a Risk Breakdown Structure and Risk Breakdown Matrix, within the procurement WBS to increase awareness of supply chain risks. They posit that this enhances awareness of risks. Awareness of risks would lead to adopting innovative approaches to minimise the possible negative impact on the project since the construction phase of an EPC project depends on materials from the procurement phase.

## Construction WBS

Construction uses materials supplied by Procurement, guided by drawings provided by Engineering. Main activities in the construction WBS follow the sequence: general construction plan, site layout plan, temporary facilities; geotechnical investigation, mass earth-works, structural concrete, structural steel, mechanical and electrical equipment, piping, raceway; instrumentation and controls, system turn-over, start-up commissioning, performance run, and lastly turn-over to end-user (Fox, n.d.). Throughout the process, as per Baron (2010) there are knowledge packets as information flows within construction phase and across with the other phases.

## Interface of EPC Phases

WBS indicate engineering phase as the focal point in an EPC project in as far as in the information sharing process it interfaces directly with the other two phases: with Procurement in terms of providing the specifications and quantities of materials and with Construction in terms of providing construction drawings and specifications, and with the client organisation in terms of receiving specifications, submitting documents and obtaining approvals. This is illustrated in Figure 5.1. Where the interface occurs, there is information sharing through formal mechanisms and knowledge sharing through less formal mechanisms. These inter-functional interactions whether coordinated or not result in the formation of or constitute a network of stakeholders where there is a patterned flow of information.

Figure 5.1: EPC information flow Knowledge Breakdown Structure (Baron 2010, p.11)

It is apparent that within an EPC project while each phase has its own WBS within which are information flows, outputs of one phase serve as inputs of the next resulting in a wide range of complex knowledge and intellectual creativity activities that constitute a project knowledge network (PKN) and all the knowledge of a project resides within the network (Zhu, Sun, Xu and Haider, 2014). The smallest structural unit of the PKN is the knowledge package which carries both explicit (tangible and codified) and implicit (professional skills, experience, insights, intuition etc) knowledge accumulated over time (Zhu et al.  2014). Where explicit knowledge is transmitted through formal channels such as documentation, implicit knowledge resides in and is transmitted through individuals or groups, its integration at the business, and therefore project level, can be realized through stakeholder knowledge network. Zhu et al.  (2014) posit that “communication and application of implicit knowledge … is the process of knowledge sharing and innovation” (p.709). To that end, stakeholder knowledge networks enable the development of an organisational (or within project) knowledge system that is supported by implicit knowledge from both within and outside the project that is beneficial to the EPC project.  The distribution of knowledge within a stakeholder knowledge network determines the levels of knowledge sharing, application and innovation. Zhu et al.  (2014) suggest that correlation among stakeholder knowledge network nodes indicates the implicit knowledge communication path in the EPC project as it breaks the functional boundaries among and between the stakeholders and in that way enabling formal and informal knowledge transfer and facilitating innovation as illustrated in Figure 5.2.

Figure 5.2: The correspondence between Project Knowledge Network and Stakeholder Network (Zhu, Sun, Xu and Haider, 2014)

In an EPC project, knowledge networks cut across the three phases of Engineering, Procurement and Construction and are also within each phase’s life cycle as illustrated in Figure 5.3. The strength of the links or relationship depend on participant involvement in the phase and part of the project life cycle. I, II and III indicate period involvement of stakeholders in specific stages of a project life cycle (Zhu et al.  2014). Within an EPC project this can be viewed as occurring at least two levels: at the EPC project phase level – E, P, or C and within each of the phases since within each phase there is a life cycle. This is illustrated in Figure 5.3 which is an adaptation of Zhu et al.  2014 evolution of cycle of stakeholder knowledge network.

Figure 5.3: Evolution cycle of within phases Stakeholder Knowledge Network

Source: Own construction adapted from Zhu, Sun, Xu and Haider, 2014

In Figure 5.3 above, Engineering, Procurement and Construction refers to the periodic network of stakeholders during each of the three phases of the EPC project. Under each phase, I, II and III refer to the periodic involvement of stakeholders within the project life cycle of a phase. In both diagrams solid lines represent strong links that are likely to occur among stakeholders in the same phase or same field of specialisation or where the nature of work demands stronger links as is the case between engineering and construction. Broken lines represent weak links. Zhu et al.  (2014) opine that within various stages of an EPC there is knowledge input and output which are part of the knowledge management processes and that the ultimate output of knowledge forms knowledge innovation. They propose that innovation in an EPC project is nurtured by a knowledge integration model that is based on a Knowledge Breakdown structure (KBS) that mirrors the project’s WBS. The KBS integrates the EPC project knowledge network on the one hand and on the other the knowledge network based on the stakeholders resulting in the spiral evolution of knowledge integration in the EPC project. This then nurtures innovation since the stakeholders within the stages of a project (who constitute the network), carry, share and apply the knowledge. The network then becomes the platform for innovation as demonstrated in Figure 5.4.

Figure 5.4: Innovation model based on KBS based on WBS of EPC project and resultant spiral evolution of knowledge integration (Zhu, Sun, Xu and Haider, 2014)

## Stakeholder Value Network

Feng (2013 cited in Hein et al., 2017, p. 4) defines a stakeholder value network as:

“A multi-relational network consisting of a focal organization, the focal organization’s stakeholders, and the tangible and intangible value exchanges between the focal organization and its stakeholders, as well as between the stakeholders themselves.”

In the case of an EPC project, the focal organisation would be the main contractor representing the interests of the project owner. Within the network, stakeholders include actors in the three phases of the project and are represented by nodes. Social and economic exchanges between stakeholders are represented by value flows that are indicated by directed edges (Hein et al., 2017).  Marin and Wellman (2011) posit that the edges may also be undirected implying a flow that goes in either direction.  The flows can be described in terms of density as strong or weak; may involve multiple nodes, and may have some nodes acting like bridges; and may have a dominating central node (centrality) (Marin and Wellman, 2011 citing Freeman, 1979). Hein et al. (2017) determined the relative power of stakeholders by calculating the weighted occurrence of stakeholders in all value loops. In the case of innovation within and between the WBSs of the phases of an EPC project, tacit knowledge, as reflected in the knowledge breakdown structures, can be viewed as the relevant value flowing through the stakeholder network. Weightings of the value of the knowledge flows to innovation, and therefore their influence, can be determined through their contribution to stakeholder objectives and needs within and between WBSs of the EPC project.  Contribution can be inferred from mapping relationships.

## Design Structure Matrix

In complex engineering projects with multiple stakeholders, as is the case in EPC projects, a design structure matrix (DSM) is used to map relationships among elements of a system (Xiao and Chen, 2010) through offering network modelling tools that capture system elements and their interactions. It is compact, visual and intuitive offering analytical capacity and flexibility. Yassine (2004) posits that it differs from traditional project-management tools due to its focus on information flows rather than workflows. This aspect, according to Epping (2001) makes it suitable for depicting innovation processes especially relating to product innovation as it allows for complex learning that depends on the existence of feedback loops.

The process of developing a DSM involves:

- Identifying the information needs of the tasks as reflected in the WBS.

- Listing the tasks in the order in which they are performed.

- Arranging the tasks horizontally and vertically in the order in which they are performed.

- For each row corresponding to a task, identifying and marking off information inputs required to complete the task.

- For each column looking down identifying and marking off all information outputs to be provided to other tasks.

Figure 5.5: Developing a DSM

Source: Derived from Epping, 2001

The success of the method depends on the extent to which the collected dependence relationships are accurate and on the decomposition of the system (Yasine, 2004). In an EPC project it is the phases of the project being decomposed into meaningful systems and subsystems captured in the WBSs and the KBS which also reflects the actors or stakeholders within the structures. Appropriate decomposition is achieved through studying the project documentation such as design manuals and project schedules and through conducting structured expert interviews (Yasine, 2004).

DSM has been found relevant in understanding stakeholder relationships (Feng et al., 2010) and therefore within an EPC, appropriate for tracing influence on both process and product innovation. It has, for example, been used in construction projects (Pektaş and Pultar, 2006) and engineering design (Browning, 2016).

DSM model is appropriate for mapping the flow of innovation related value within an EPC project given that innovation is information and or knowledge driven.  In the current study, the elements in the rows and columns would be the various stakeholders (being the repositories of knowledge and information) in each part of the WBS. Using the example derived from Figure 5.5 within an EPC project, Figure 5.6 illustrates a possible DSM for a component of an EPC project. It illustrates that tasks A to J in Figure 5.5 could be stakeholders expressed as SH1 to SH10. SH1 (Task A in Figure 5.6) may be the main stakeholder, the lead EPC contractor who needs information from the project owner to get the EPC project going but does not need similar information from all the other stakeholders. SH1 being the lead EPC contractor would provide information to SH2, SH3, SH4, SH9 and SH10 who may be other stakeholders within various parts of the WBS for the phases Engineering, Procurement and Construction. Stakeholders within each of the phases would also have providers of information and while also providing information.

Figure 5.6: Stakeholders DSM

## Summary

This chapter discussed stakeholder analysis within the context of social network theory given that project stakeholders constitute a social network.  Stakeholder networks were discussed through analysing the WBS at each phase of an EPC project and mapping out the flow of knowledge and information as proxies of possible levels of product and process innovation within an EPC project. Engineering’s involvement in translating functional requirements into detailed drawings and specifications that reflect all aspects of the project deliverables was noted to make it the most critical part of an EPC interfacing directly with both Procurement and Construction. Given the general complexity of relationships within EPC projects, a DSM, itself based on mapping relationships and therefore grounded in Social Network theory, is relevant in enhancing understanding project stakeholder relationships, knowledge flows, and tracing process and product innovation. The next Chapter discusses the study’s methodology and presents a more detailed explanation of the study’s use of Social Network Analysis as a framework for mapping the flow of innovation related value within Project Alpha EPC.

# Methodology

## Introduction

This chapter discusses the study’s methodology used to assess the interaction of project stakeholders and process and product innovations in Downstream EPC projects. The chapter has the following sections: research philosophy paradigms (Section 6.2); research design (Section 6.3); data collection methods (Section 6.4); data analysis (Section 6.5); summary of the data collection and analysis procedure (Section 6.6); and concludes by discussing the study’s handling of ethics issues (6.7).

## Research Philosophy Paradigms

Corbin and Strauss (2008) describe methodology as a way of thinking about and studying social phenomenon. Bryman (1984) describes it as an epistemological position and a justification for using a particular method over others. Methods are the techniques and procedures used to gather and analyse data (Corbin and Strauss, 2008). Various terms are used to describe research approaches and strategies.  Saunders et al. (2012) definitions and description of the different research terms were adopted for anchoring the discussion on the methodology and methods used in the current study. Saunders et al. (2012) conceptualise research methodology and methods in the form of an onion with the outer parts representing a researcher’s philosophy which guides their methodological choices which in turn determine the strategies they employ, and the techniques and procedures used to collect the data. This is summarised in Figure 6.1.

Figure 6.1: Conceptualisation of research. Saunders et al. (2012)

Research philosophy or paradigm represents a researcher’s system of assumptions and beliefs on knowledge development and therefore on how data on a phenomenon must be collected, analysed, and utilised (Creswell and Plano-Clark, 2011; Saunders, et al., 2012). Guba and Lincoln (1985) posit that paradigm issues are so important that no researcher should proceed without being clear about the research philosophy informing and guiding their approach. Understanding research philosophy issues helps to clarify research designs, help the researcher pick a suitable design as it highlights the limitations of a design and enables the researcher to develop novel designs that are outside their past experiences or to adapt existing ones (Easterby-Smith et al., 2012). A researcher’s preferred paradigm is guided by the ontological question, the epistemological question, and the methodological question (Guba, 1990).

    - Ontological question

The ontological question concerns one’s beliefs on the form or nature of reality (Saunders, et al., 2012; Denzin and Lincoln, 2000). Two main ontological positions are objectivism and subjectivism. Objectivism believes that there is a true social reality which is both external to and independent of the researcher (Gallagher, 2008) and that all reality has properties and consist of entities that have relations binding them at any particular point in time (Lakoff, 1987). Subjectivism perceives social reality as constructed by those engaged in it through social interaction to derive meaning through the process. The truth of such reality is found through a rigorous interpretation process (Salvador, 2016).

### 6.2.2 Epistemological Question

Epistemology is about how the truth is known and clarifies the relationship between the researcher and the phenomenon being studied. Common epistemological positions are positivism and interpretivism. Positivism is associated with objectivism and based on the assumption that human behaviour is governed by laws and that there are objective facts that can be measured or observed in a quest for objective knowledge (Silverman, 2010). Interpretivism is associated with subjectivism and is based on viewing reality as socially constructed through the understandings and meanings developed experientially and socially (Johnson, 2006).  Positivism is underpinned by a quantitative approach and interpretivism a qualitative approach to data gathering and analysis.

### 6.2.3 Methodological Question

The methodological question addresses how the researcher can go about knowing that which they want to know. The research methodology for data collection could either be qualitative, quantitative or a mixture of the two. Quantitative methodology involves the mathematical representation of an observed and measured data that can be used to explain a phenomenon (Creswell, 2014). It is used for testing theory through the analysis relationships among variable (Creswell, 2014). Data is generally collected through surveys and experiments are the commonly used methods of collecting data for quantitative studies. Quantitative studies can be classified as descriptive, developmental, correlational, ex post facto, experimental or quasi-experimental (Bernard, 2013).  Qualitative method studies things in their natural setting, attempting to interpret phenomena in terms of the meanings people attach to them (Denkin and Lincoln, 1994). The goal of qualitative research is to understand a particular situation or phenomenon from the perspective of those involved in it (Leedy and Ormrod, 2005).

Quantitative and Qualitative methods are mixed when using both methods is likely to provide a better understanding of a phenomenon than when using a single method (Cameron and Molina-Azorin 2011). Johnson and Onwuegbuzie (2004) posit that use of multiple methods leads to superior research findings than when using one method. Similarly, Jogulu and Pansiri (2011) opine that when vigorously combined, multiple methods lend a better understanding of complex social phenomenon.

### 6.2.4 Methodological Choice

Given this study’s intended use of social network analysis as a framework for uncovering the complexity of interaction between project stakeholders and process and product innovation outcomes in downstream EPC oil and gas projects, it draws from both the qualitative and the quantitative methods and in that regard falls within a mixed methods design. Creswell (2014) defines mixed methods as involving the collection and or analysis of qualitative and quantitative data in a single study with the data being collected concurrently or sequentially and the data being integrated at some stage(s) in the process of the study. Opting for mixed methods is consistent with observations made elsewhere that trying to position network research within either the qualitative or the quantitative paradigm is problematic based on how the two paradigms are classified in literature. According to Hollstein (2014) social network analysis is neither quantitative nor qualitative but is structural. In that regard in the context of network analysis what is referred to as quantitative data is data describing relations, interactions, and structures of networks in formal terms using numbers. Qualitative network data refers to when aspects of networks are described in text form, for example where an actor explains the nature of their relations with other network members. Mixed methods have been used successfully in a related study on social networks and innovation (Kolleck, 2013). Edwards (2010) notes that because social networks are a mixture of both structure and process, mixing qualitative and quantitative methods in network analysis can enables researcher to explore a network’s structure from both an ‘outsider’s’ view and its content and processes from an insider’s view.

## Research Design – Social Network Analysis

The study will be in the form of a social network analysis-based case study of an EPC project implemented by a major Oil and Gas Company in UAE. Case study involves focusing on a single case’s particularity and complexity to understand its activity within specific circumstances (Stake 1995). The unit of analysis in a case study is a single organisation (Yin, 2003). Case study is usually criticised for its inability to render generalizable findings. In this instance the researcher’s interest is not so much to generalise the findings beyond the population under study, but rather to reach a conclusion on the case being investigated that is based on rigorous interrogation of relevant data. The use of Case study research has been accepted as a valid form of inquiry when exploring complex issues where human behaviour social interactions are at the centre of the investigation (Harrison et al. 2017) as is the situation in the case of complex stakeholder relations within an EPC project.

According to Marin and Wellman (2009) Social network analysis is not a theory, neither is it a methodology, but is a research paradigm. It is based on the premise that social life is a product of relations and the patterns they form.  However, elsewhere Social Network Analysis is presented or considered as a methodology (Chaudhary and Radhakrishna, 2018) or as an approach or a set of methodologies (De Brún and McAuliffe, 2018). In this study social network analysis is used as a method or strategy for understanding product and process innovation implemented in Oil and Gas EPC projects in the context of stakeholders’ interactions.

Davies (2009) defines a social network as actors that are connected by some relationship. Butts (2008) posits that a social network consists of a set of ‘entities’ that are distinct, are uniquely identifiable and their number is known and therefore fixed. The entities have or are linked through relationships designated as lines, paths or ties which may show the direction of information flow (Woodland, Barry and Roohr, 2014). Entities are also referred to as nodes or vertices (Woodland, Barry and Roohr, 2014). The network entities or nodes are classified based on the structure of the network as: stars being those with the highest number of connections, appearing in the centre of the network; nodes that connect nodes that are otherwise unconnected are labelled bridges  functioning as information channels; bottlenecks serve the same purpose as bridges but also decide on what information flows and where it flows to; and nodes with few or no ties are labelled an isolate (Woodland, Barry and Roohr, 2014).

Social network analysis refers to methods used to measure, represent and analyse the structure of the social relationships. It takes two main forms: whole network analysis and egocentric analysis. The former aims at understanding the relationships among all network actors and is used when all the actors are known. The latter is used in situations where the intention is to identify a single actor’s complete network or where a complete network’s boundaries or membership is not known.

Main areas of inquiry in social network analysis include the flow of exchange of resources, ideas, information, influence and innovation diffusion (Edwards, 2010). According to Digital Promise (n.d.) the first step in Social Network Analysis is establishing the network’s basis. This involves classifying the network as either a bounded network where the number of network members is known, or an unbounded network where the membership is not set. In this study the network is bounded as network participants are known. The second step is to define and refine the research questions. The third step is determining the kind of network connection data to be collected. This study collects network data on relations among stakeholders and activities as seen through the direction and frequency of interaction. The fourth step is selecting data collection tools with the common methods being dependency matrix. Step five is the selection of the method of data collection which relates to sampling method used to select the participants the common ones being full network method and snowball method. This study uses full network method as it deals with a bounded network. The sixth step is that of mapping the network and visually analysing the data using appropriate software. This study uses Gephi, an open source and free software widely used for visualisation and exploration of relationships (gephi.org).

Social Network Analysis was chosen as an appropriate data collection and analysis method for this study because of its capacity to facilitate the visualisation and understanding of the various relationships (both formal and informal) that are relevant for innovation in the EPC project. It involves studying the structure of interaction relationships among members of a network which include innovation diffusion (Edwards, 2010). Social Network Analysis therefore lends itself to facilitating understanding of linkages between the flow of innovative ideas through interactions within a network. Other studies have successfully used Social Network Analysis to understand aspects related to innovation. Cross, Parker and Borgatti (2002) used it to understand knowledge creation and transfer. For Cross, Parker, Prusak and Borgatti (2001) it provided “an X-ray” of what happens in informal networks as they sought to understand relational qualities that promote knowledge sharing. Breznik (2016) used it to identify innovation clusters. Social Network Analysis’ focus on relationships among entities makes it appropriate for understanding complex stakeholder relationships found in EPC projects.

Social Network Analysis as a research methodology has been successfully used in innovation related studies in various contexts. Van Der Valk and Gijsbers (2010) identified networks of collaboration; communication networks; and networks of technology as innovation related themes that could benefit from use of social network analysis in mapping relationships among actors. Kolleck (2013) used social network analysis approach combined with qualitative data in studying innovation in the education sector. Cammarano et al.  (2017). used the approach to investigate the impact of network strategies on innovation strategies in the bio-pharmaceutical sector while Yokura, Matsubara and Sternberg (2013) employed it in studying research and development networks and regional innovation within joint research projects in Japan. Hermans et al. (2017) used social network analysis as a framework for investigating opportunities and constraints for innovation scaling in the agricultural research sector. More recently, Lombardi et al. (2020) investigated the impact of social innovation on marginalised rural communities from a social network analysis approach while Gebhardt, Riel, and Maes (2020) used the same to study the evolving social context of innovation projects. Given this study’s focus on innovation in a project environment, social network analysis is appropriate for understanding stakeholder interactions and innovation diffusion within the project.

## Data Collection Methods

Consistent with Hanneman and Riddle’s (2005) observation that social network analysis rarely use sampling but rather conduct a census of the population, this study’s participants are all the identified stakeholders and activities of Project Alpha. The project was a Greenfield EPC project whose aim was to ensure a continuous supply of gas to main Abu Dhabi industries and to the Northern Emirates. The project presented an ideal cite given that it represents an important element for achieving  UAE 2030 Smart Growth Strategy by maximizing the value from hydrocarbon resources, and strengthens the UAE’s gas and energy infrastructure by allowing uninterrupted gas supply to Abu Dhabi and the Northern Emirates. Having been completed in a record time of 16 months, it was assumed that it would have presented a number of innovation opportunities.

The data collection process was in three stages: stakeholders related data; activities related data; and innovation outcome related data. The study population were the 182 group of stakeholders and 3231 activities identified using the Activity Distribution Matrix (ADM) as explained in the next sections.

### Data Collection Stage 1 – Identification of Stakeholder networks

Project stakeholders’ data were collected using the Activity Distribution Matrix (ADM), a formal document that is derived from the project planning package and issued at the start of the project to identify all project activities and stakeholders associated with these activities.  The ADM was used to generate a Dependency Matrix illustrating relationships among the stakeholders. The ADM identified each stakeholder and the nature of their role which were coded as Responsible or Review (R), Accountable or Approval (A), Consulted or Comment (C) and Informed or Information (I). The stakeholders were identified based on the project’s actual data. In that regard a list of project stakeholders was drawn from the Engineering, Procurement and Construction phases. The output of this stage was a listing of 182 project stakeholders spread across the EPC project. Within each phase stakeholders were grouped by Activity. This grouping enabled the researcher to identify formal stakeholder involvement both within each phase and across the phases.

The ADM is appropriate for identifying stakeholders at each phase of the EPC for several reasons.  The ADM captures the formal role or input of a stakeholder in an activity. According to Eyiah-Botwe, Aigbavboa and Thwala (2016), a stakeholder’s role may change during different phases of a project so that their classification does not represent a permanent label. In that regard, the ADM provides a stakeholder’s role on an activity-by-activity basis and therefore reflects the most accurate position. Rowley (1977) also justifies the appropriateness of ADM for identifying stakeholders through the view that stakeholder influence on innovation is a collective effort resulting from the ‘interaction of interactions.’ The ADM is a vivid and formal presentation of such interactions.

      - Engineering stakeholders

Table 6.1 presents an extract from the Engineering ADM. A detailed listing of Engineering stakeholders and their roles is presented in Appendix A.

Table 6.1: Extract from Engineering ADM

      - Procurement stakeholders

Table 6.2 is an extract from the Procurement ADM. Appendix B presents a complete listing of the Procurement phase stakeholders.

Table 6.2: Extract from Procurement phase ADM

      - Construction stakeholders

An extract from the Construction phase ADM is presented in Table 6.3. The complete list of the phase’s stakeholders is presented in Appendix C.

Table 6.3: Extract from Construction phase ADM

### Data Collection Stage 2 - Identification of Activities relationships

The second stage of data collection involved collecting data related to project activities and their relationship with each other. The project WBS and planning schedule were used to identify project activities during Engineering, Procurement and Construction phases. 3231 activities distributed as follows: 1607 in Engineering, 875 in Procurement and 749 in Construction phase were identified. The relationship between activities were identified using the successor relationship between activities. Accordingly, an Activity Matrix was generated. A small portion of the matrix is illustrated in Table 6.4.

Table 6.4: Activities relationships matrix

Based on the relationships in table 6.4, a dependency matrix of the Activities was generated. This is exemplified in Table 6.5.

Table 6.5: Activities Dependency Matrix

|  | G1000 | G1010 | G1020 | G1025 | G1030 | G1050 |
| --- | --- | --- | --- | --- | --- | --- |
| G1000 |  |  |  |  |  |  |
| G1010 | X |  |  |  |  |  |
| G1020 |  |  |  |  |  |  |
| G1025 |  |  |  |  |  |  |
| G1030 |  |  | X |  |  |  |
| G1050 |  | X |  |  |  |  |

As illustrated in Table 6.5, a relation is identified between G1000 and G1010, G1010 and G1050, and between G1020 and G1030. The relationships between each pair of activities is classified as dependent.  For example, the relation between G1010 and G1000 is such that G1010 is sequential to G1000. The relationship is illustrated in Figure 6.2.

Figure 6.2: Sequential relationship

### Data Collection Stage 3 - Identification of Innovation Outcomes

The study’s dependent variable is innovation within the project. Consistent with diffusion of innovation theory (Rogers, 1983 cited in Woodland, Barry and Roohr, 2014) it is expected that the strength and attributes of the social network within the EPC are indicative of the occurrence or otherwise of innovation within the various activities of the project.

Given this study’s focus on product and process type innovation within EPC projects, in its consideration of innovation measures it adopts the OECD Oslo manual’s (OECD, p.9) definition of process innovation as: “the implementation/adoption of new or significantly improved production or delivery methods. It may involve changes in equipment, human resources, working methods or a combination of these.” And that of product innovation as: “the implementation/ commercialisation of a product with improved performance characteristics such as to deliver objectively new or improved services to the consumer.” To measure process and product innovation the study is guided by Un and Asakawa’s (2015) highlighted differences between product and process as illustrated in Table 6.6 as these have implications for applicable measures.

Table 6.6: Difference between product and process innovation (Asakawa, 2015)

| Dimensions of Analysis | Process Innovation | Product Innovation |
| --- | --- | --- |
| Objectives of the innovation | Efficiency | Novelty |
| Value of innovation | Internal | External |
| Degree of novelty valued | Incremental | Radical |
| Codifiability of knowledge | Unclear, obscure, tacit, lower | Clear, concrete, explicit, higher |
| Location of knowledge or substitutability | Organizational, interdependent | Technological, independent |

Process innovation measures that have been highlighted in literature include: reduction or containment of costs and other inputs (Janger et al., 2017); innovation speed (Wang and Wang 2012);  amount of time taken to develop the next generation of a product (Ivanova and Avasilcăi, 2014);  innovative activities (Therrien and Mohnen, 2003); the difference between plans and implementation (Kim, 2014); and satisfying customer needs through adding new functions (Duhamel and Santi, 2012; Dewangan and Godse, 2014). Product innovation measures include: visibility of advantages of an innovative product to a customer; ease of use or access of a product’s functionality; quantity of new product ideas; future usability of products; performance of the new product after launch (Dziallas and Blind, 2018 citing Cooper, 1999; Astebro and Michaela, 2005; Cooper and Kleinschmidt, 1993; Astebro and Michaela, 2005); successful commercialization of innovations in terms of high sales rates (Astebro and Michaela, 2005).

From literature it is apparent that there are no agreed innovation measures. In the current study process innovation will be measured based on the OECD Oslo manual’s (OECD, p.9) definition of process and product innovation.  Data on the EPC project’s process innovation will be obtained through soliciting participant opinions on changes in equipment, human resources, working methods or a combination of these that could have resulted in cost savings; faster implementation compared to similar other projects they have participated in and or compared to set targets; and beneficial changes to processes. Rammer (2016) posits that it is possible to employ quantitative output measures of product innovation across different sectors noting that it has been widely used and even found superior to simple binary measures that do not link product innovation to economic results (citing European Innovation Scoreboard, European Commission 2016;  Klingebiel and Rammer 2014).

Data on product innovation was obtained through analysing stakeholder involvement in activities.  Stakeholders are assumed to influence activities that influence innovation so that the relationship between stakeholders and innovation is through stakeholders’ performance of some project activities.

Literature indicates that the engineering phase of an EPC project has the highest influence as it involves identification of client needs and coming up with designs to address the expected deliverables while reducing the need for rework at later stages, especially at construction stage. Rework leads to escalating costs and has been attributed to coordination problems among the design teams at engineering stage (Chandrusha and Basha, 2017; Kamalirad et al. 2017; Safapour and Kermanshachi). Wilson and Odesola (2017) found omissions and errors in design documents, poor communication among project team members, design changes, none verification of the site by team members and absence of as-built documentation to have been leading causes of design related rework in oil and gas projects. Innovation in the engineering phase of a project can therefore be measured through outcomes of reduced rework, reduced costs and time realised at the construction phase emanating from use of updated design methods. For example, experiencing a lot of rework would imply more time and costs being used, a situation which, according to Wilson and Odesola (2017) would be indicative of poor interaction, and therefore inadequate information or knowledge sharing in the project engineering phase.

At product level, innovation at the Engineering phase can be measured through outcomes in the impact of the final product on public health and safety and quality of the product. According to the Oslo Manual (2018), improving public health and safety, and improving the quality of goods and services are among outcome measures of innovation.

In the procurement phase innovation can be measured based on the outcomes of the collaboration between equipment suppliers and the user organisation. Studies have noted that development and installation of new equipment in production plants is associated with collaboration between the organisation putting up the production plant and its suppliers (Sjödin and Eriksson, 2010).  This is confirmed by Sjödin (2011) who highlights the essentiality of collaboration in the transfer of equipment specific knowledge between the supplier organisation and the receiving organisation engaged in production or construction work as the installed equipment may need continuous fine tuning. Basu (2017) highlights that another critical element of procurement that contributes to project success is cost effective and correct delivery of project inputs. Along the same vein, Laradi (2017) identifies procurement aspects as presenting risks to project success.  Micheli and Cagno (2016) posit that procurement within an EPC project has the biggest impact since purchasing may account for as much as 80% of the project’s total value with as much as 45% being critical supplies. The need to achieve cost effectiveness, punctuality, right quantities and quality provide possible areas of innovation measurement as outcomes in those areas impinge project success. Stressing the importance of on time inputs delivery, Wolf (2010, p15) notes that “To the workers, rework and waiting for materials translates into incompetent project management.” Process innovation outcome measures that will be derived from procurement phase relate to outcomes of on time delivery and cost-effective sourcing methods.

In construction phase the end result of innovation is observed in outputs such as projects that meet or exceed cost, quality, schedule and safety goals (Gambatese and Hallowell, 2011). Xue et al. (2014) identify outcomes of construction innovation as also including corporate performance, quality improvement, client satisfaction, improved corporate image, shortened project duration, environmental performance and enhancement of quality of life.

Although it may be possible to measure innovation at the different phases of an EPC, because the effect of some innovation cuts across the phases, this study measures innovation from process and product perspective without making any distinction based on EPC phase. Table 6.7 summarises the innovation measures used in the study and literature supporting the applicability of the measures.

Table 6.7: Innovation measures used in the study

| Type of Innovation | Innovation Outcome Measures | Supporting Literature |
| --- | --- | --- |
| Process |  | Wolf, 2010; Wilson and Odesola , 2017; Wang and Wang, 2012 |
|  | Creative design resulted in reduced implementation time; |  |
|  | Creative ideas used to improve procurement activities | Basu, 2017; Micheli and Cagno, 2016 |
|  | Creative design and installation ideas resulted in reduced operational cost | Wilson and Odesola, 2017 |
| Product | Creative design resulted in reduced production cost; | Janger et al., 2017; Chandrusha and Basha, 2017; Kamalirad et al. 2017; Micheli and Cagno, 2016 |
|  | Creative design and installation and procurement resulted in improved public health and safety associated with the product | Oslo Manual, 2018; Xue et al., 2014 |
|  | Improved quality of materials and equipment that resulted in achieving or exceeding industrial standards. | Gambatese and Hallowell, 2011; Xue et al. 2014 |

Data on product innovation was obtained through asking participants to identify activities that resulted in innovation outcomes and to insert their input in the Dependency Matrix as illustrated in Table 6.8. The feedback received was verified with the project deliverables as depicted in project documents to ensure consistency and accuracy. Further, verification enabled the researcher to identify informal stakeholder influence on both activities and innovation. For example, a stakeholder could be found to have identified themselves as having been involved in an activity yet the official documents would not have captured their involvement. The final data were populated in a Dependency Matrix as illustrated in Table 6.9. The dependency matrix was circulated to stakeholders for them to confirm completeness of the captured activities. Where necessary, the dependency matrix was adjusted and a final version was issued.

Table 6.8: Observed innovation by activity

|  | Innovation 1 | Innovation 2 | Innovation 3 | Innovation 4 | Innovation 5 | Innovation 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Activity Code |  |  |  |  |  |  |
| Activity Code |  |  |  |  |  |  |
| Activity Code |  |  |  |  |  |  |
| Activity Code |  |  |  |  |  |  |
| Activity Code |  |  |  |  |  |  |

Table 6.9: Stakeholder influence on innovation data captured in DSM

|  | Stakeholder 1 | Stakeholder 2 | Activity 1 | Activity 2 | Innovation 1 | Innovation 2 |
| --- | --- | --- | --- | --- | --- | --- |
| Stakeholder1 |  |  |  |  |  |  |
| Stakeholder2 |  |  |  |  |  |  |
| Activity1 |  |  |  |  |  |  |
| Activity2 | X |  |  |  |  |  |
| Innovation1 |  |  |  | X |  |  |
| Innovation2 |  |  |  |  |  |  |

The example captured in Table 6.9 illustrates that Stakeholder1 impacted Activity2 which impacted Innovation1. The relationship is as illustrated in Figure 6.3.

Stakeholder1

Activity2

Innovation 1

Figure 6.3: Stakeholder influence on innovation

### Data collection Stage 4 – Quantitative survey

In order to validate the occurrence of innovation in the EPC project through triangulating the results obtained from earlier stages of data collection, a questionnaire survey was administered on a selected group of stakeholders representing each phase of the project. The questionnaire had six questions asking respondents to rate stakeholders’ contribution towards reducing the project duration; improving the procurement activities; reducing the project (unit) operational cost; reducing production (manufacturing and execution) cost; meeting health and safety requirements; and achieving the industry standards. Using triangulation through use of multiple methods of data collection to validate study results is consistent with studies that have suggested that such an approach provides corroboration evidence and thus enhances confidence in research results (Turner and Turner, 2009).

The questionnaire survey (Appendix D) was e-mailed to 300 professional project members who are working in EPC projects in the oil and gas sector in UAE. Selection was based on simple random sampling where all members had equal chance of being selected. The sample size was guided by the need to have at least 50 valid responses in line with Delice’s (2010) view that in a quantitative study a sample size of between 30 and 500 is sufficient. Responses were received from 60 participants representing a 20% response rate. This was considered adequate for purposes of triangulating the study’s findings.

## Data Analysis

Analysis of the data was conducted in three stages: visually mapping out the network using social network analysis tools; measuring and modelling of network structural properties to facilitate understanding of the intensity of interaction among stakeholders and within activities; analysis of stakeholder involvement in activities linked to innovation; and quantitative analysis of data from the quantitative survey.

    - Visually mapping stakeholder networks and activities

Four sets of networks were mapped out: sets for each of the phases of the EPC project, and a set for the whole EPC project. These are explained in detail in the respective chapters (Chapters 7, 8, 9 and 10).  The major output of this stage of analysis were the networks of stakeholder relations and of activities linkages which were used as indicative of information flow and knowledge sharing within the networks. Given the association of knowledge or information sharing and innovation (Wang and Wang, 2012), analyses of the relationships and linkages were used to trace influence on innovation.

### 6.5.2 Social Network Analysis Measures

Measuring and modelling of network structural properties facilitates understanding of intensity of interaction between individuals or entities in the network and clarifying those acting as bridges, bottlenecks, isolates and stars. Similarly, in a knowledge network it illustrates and quantifies knowledge flow. Given that innovation has been said to be a result of knowledge sharing, in a network measuring and modelling the structural properties of knowledge sharing nodes can help explicate levels of influence on innovation within a given network. According to Rogers’ (1962 cited in Woodland, Barry and Roohr, 2014) diffusion of innovation theory, the spread of innovation among actors is aided or impeded by social relationships within the network. Relevant network structure elements are: density which refers to the number of lines in a network, degree which is the number of connections for a specific node; looseness centrality referring to the total distance of a node from all other nodes; and betweenness centrality referring to the frequency with which a node needs a specific node to reach another node (Woodland, Barry and Roohr, 2014).

The network of each phase of the EPC project was mapped to reflect the activities and the information sharing, both formal and informal among involved stakeholders. Network characteristics were measured to establish density of stakeholder relationships and centrality.

#### Network Density

Network density refers to the number of connecting lines in a network. It is derived from dividing the number of actual connections between nodes by the network’s potential number of interactions. When a network’s density approximates 1 it is indicative of strong connections among all the stakeholders of an EPC project. Such a situation would suggest high levels of interaction and therefore of information and knowledge sharing creating favourable conditions for innovation. When the density is close to 0 this suggests weak connections, low levels of interaction, information and knowledge sharing resulting in low levels or absence of innovation. Network density is an appropriate measure in this study as it can provide pointers on the speed of information diffusion in the network. Given that EPC projects, like any other project, operate within specific time constraints, the density of a network can aid or hinder innovation. It can be expected that when the network density is nearer 1, innovation may be more likely as the process of adopting and implementing new ideas would be more likely to occur within the confines of the project timeframes.

The density of a network may give us insights into such phenomena as the speed at which information diffuses among the nodes, and the extent to which actors have high levels of social capital and/or social constraint.

#### Centrality measures

Centrality measures were used to establish the stakeholders (represented by nodes) who are most critical for spreading knowledge in the network during the engineering, procurement and construction phases of the project. Centrality measures used are local or degree centrality, and global (closeness) centrality and betweenness centrality.

Local or degree centrality: Local or degree centrality counts each node’s number of links and identifies stakeholders that can establish links with the rest of the network quickly. Because it does not consider the rest of the network, its importance depends on the size of the network. In the case of stakeholders, degree centrality examines the number of links to a stakeholder (in-degree) and from a stakeholder (out-degree). The measure allocates a node an importance score based on the number of links it holds. It helps identify stakeholders who are more connected, or popular and therefore likely to have most project information and are best positioned to pass it on to most other stakeholders. In the context of an EPC project, each of the phases may have a stakeholder in such a position and in that way aiding within phase and across the project innovation.

Betweenness centrality:  Betweenness centrality measures the degree to which a node occupies a strategic position in a network as seen from the frequency with which a stakeholder lies on the shortest path connecting all other stakeholders in the network and therefore serving as a bridge.  This metric is valuable, as it helps identify a stakeholder that influences the flow of information and knowledge around the network and therefore who is likely to be influential in spreading both throughout the network. Quantifying the betweenness of stakeholders will assist in identifying those stakeholders more likely to have higher influence on innovation both within the individual EPC phases and across.

Closeness centrality: Closeness centrality scores nodes based on the extent of their closeness to the rest of the nodes in the network. It assists in finding stakeholders who are in the best position to influence the whole network that is individuals in all phases of the EPC most quickly. Such a stakeholder would facilitate the spread of new ideas and in that way having high influence on innovation throughout the network.

Results of the stakeholders’ network analysis were presented in the form of network maps and relevant network metrics for each phase of the EPC project and also for all the phases combined.

Network centrality measures used in the study are summarised in Table 6.10.

Table 6.10: Network centrality measures applicable to the study (Cheliotis, 2010)

| Centrality Measure | How it will be used |
| --- | --- |
| Degree | The number of other stakeholders a specific stakeholder can reach directly |
| Betweenness | The likeliness of a stakeholder being the one linking two other stakeholders |
| Closeness | The speed with which a stakeholder can reach all other stakeholders |

### 6.5.3 Social Network and innovation diffusion

The next phase of data analysis involved data relating to innovation as observed or experienced during the phases of the EPC project. Social networks are widely recognised as instruments of innovation diffusion and to that extent they can aid tacit knowledge transmission and interchange both of which foster innovation (Kolleck, 2013). The state of stakeholder network relationships as depicted through the density and centrality measures were used as the independent variables of the study.

Social network data is analysed using a number of software applications that have been developed for that purpose. The software falls into two categories: that which facilitates visualisation of networks such as NetDraw, NetMiner and Pajek, and that which focuses on production of text reports such as UCINET, Agna and MultiNet (Pan, 2007). Commonly used software designed mainly for studying the whole network include: Pajek, UCINet, MultiNet, Siena, P*/ERGM, R from R Development Core Team, and Node XL (Pan, 2007). For egocentric network data commonly, used software includes:  SAS, SPSS or Stata (Müller et al., 1999), and UCINet (Wellman, 2009). The current study uses Gephi, which is a visualisation and text-oriented software. It is an open source software for exploring and manipulating network data (Bastian, Sebastien and Mathieu, 2009).

Data on innovation was therefore analysed using Gephi software to simulate the network. It was expected that a relationship would be found between stakeholder perceptions of having observed or experienced innovation outcomes and the pattern of relationships of the stakeholder network. Qualitative analysis in the form of discussions was used to juxtapose innovation perceptions results with those from the stakeholder network analysis.

6.5.4	Quantitative analysis

Findings from network analysis were combined and used to generate questions for the quantitative survey (Section 6.4.4).  In Appendix D, charts were constructed to demonstrate the ranking of perceptions on individual stakeholders’ contribution towards each product and process innovation outcomes and the finding are discussed in Chapter 10.

## Summary Data Collection and Analysis Procedure

Given the research’s aim of using Social Network Analysis to come up with a framework for analysing the complex interaction among project stakeholders, and the product and process innovation in an EPC project in the UAE’s downstream oil and gas sector the study’s adopted framework included steps that ensured that the research questions were addressed, and the study objectives were met. Specifically, the framework facilitated identifying, from archival data, the most influential stakeholders, and stakeholder activities on process and product innovation during each phase of an EPC project, the most influential interactions, and capturing the perceptions of stakeholder contributions from a large number of participants. Use of Gephi enabled the generation of network maps whose visual effects facilitated mapping

out of stakeholder interactions and activities, which in turn facilitated development of an appropriate questionnaire for collecting quantitative data. The framework was effective in so far as it enabled the researcher to address the study’s research questions and objectives systematically and comprehensively. The framework that guided data collection and analysis is illustrated in Figure 6.4.

Figure 6.4: Research methodology flow diagram

## Ethical Issues

The need to be conscious to ethical issues that may arise in a study has been emphasized in literature (Creswell 2014 citing Berg, 2001; Hesse-Biber and Leavy, 2011). Ethical issues that may arise – personal privacy given that while aware of the official links in the project the study is going beyond these to also seek out social links facilitating the transmission of tacit knowledge. This may invade the privacy of some stakeholders who may not wat to be necessarily known that they have links that go beyond the official reporting systems. In that regard once stakeholders have been identified, they will be allocated codes that reflect their phases of the EPC projects, for example: Eng1, Cons1, Pro1. On the network nodes stakeholders will therefore be identified using their codes. Maintenance of privacy of people’s interactions will ensure protection of participants and engender trust between the researcher and the participants.

Table 6.11 illustrates this study’s intended actions of addressing ethical issues at the various stages of the inquiry process.

Table 6.11: Addressing ethical issues

| Stage of Inquiry | Likely ethical issues | How they will be addressed |
| --- | --- | --- |
| Step 0: Inception stage prior to commencing the study | Conflict of interest and bias Permission to access the Project site and participants | Choosing a research site (Project) where the researcher has no vested interests Formally request access to the EPC project sites and abide by the conditions given Seeking university review board (IRB) approval of the study proposal |
| Step 1: Documentary / archival research - Project objectives and expected deliverables | Confidentiality of project objectives and strategies related to them | Signing of a non-disclosure agreement by the researcher |
| Step 2: Identification of stakeholders through analysis of project WBS - Official list of project stakeholders | Need not to apportion expressed opinions to specific people | Use of stakeholder codes |
| Step 3: Surveying the stakeholders in each EPC phase network to identify the relationships and knowledge flows - (Matrix of Stakeholders and knowledge flow | Information on unofficial personal or social relationships among stakeholder | Inform participants of objectives of the study Get participants to sign informed consent forms Inform participants of their right to opt out of the study whenever they wish Matrix of stakeholders to be based on allocated codes |
| Step 4: Visually mapping out the network - 4 Maps of stakeholder networks | Information on unofficial personal or social relationships among stakeholder | Network map of stakeholders will be based on allocated codes |
| Step 5: Quantitative survey of specific stakeholders on process and product innovation | Need for confidentially to be able to freely express individual assessment of innovation | Use of stakeholder codes |
| Step 6: Quantitative and qualitative analysis of data | Need for the analysis results to preserve participant anonymity | Use of stakeholder codes to maintain anonymity Report all perspectives including contrary findings |

## Summary

This chapter presented the study’s preferred methodology and methods. Following a discussion of positivism and interpretivism research paradigms, the study’s intention to use social network analysis as a framework for uncovering the interaction of project stakeholders and process and product innovation,  and Hollstein (2014)’s assertion that social network analysis is neither quantitative (positivist) nor qualitative (interpretivist), the researcher decided to adopt a mixed methods design for the study. Given that EPC projects tend to differ from site to site, the researcher adopted a case study design to ensure that detailed data is collected on a single project to facilitate tracing stakeholders’ interaction and product and process innovation. The study’s choice of Social Network Analysis as a method or strategy for tracing stakeholder relations and their strength in order to use them to infer the movement of tacit knowledge among stakeholders was discussed and illustrated.  Measures to be used in analysing relations among stakeholders within the whole EPC project and within its sub-phases were presented. Further the measures that will be used to determine the occurrence of process and product innovation were also discussed and it was noted that the measures are in fact proxies as they are more of innovation indicators. The multiple data collection steps to be followed throughout the phases of the study were discussed and illustrated together with the analysis tools to be employed. The chapter concluded by presenting the study’s approaches to addressing ethics issues given that the study will be focused on relationships among project stakeholders. The next chapter presents the study’s findings.

# Results - Engineering

## Introduction

This chapter discusses the results of the analysis of the social network built with the data collected on the EPC project for the Engineering Phase. The analysis is focused on centrality metrics, namely, degree centrality, closeness centrality and betweenness centrality. The scope of the analysis starts with an overview of the Engineering Phase social network and then moves to details of Innovation Outcome nodes’ Ego Networks, grouped into Process Innovation and Product Innovation. These Ego Networks have a depth of two, meaning that they are composed by the Innovation Outcome node itself, its neighbours, and its neighbours’ neighbours. For each Ego Network, centrality metrics are computed with the help of Gephi software in order to find Stakeholders and Activities that have an influencing role in the corresponding Innovation Outcome.

## Engineering Phase Overview

Focusing on the first of the three phases of the EPC project, Figure 7.1 presents the social network composed by the nodes and relationships of the Engineering Phase. The image was produced with the Gephi software, using the Force Atlas layout algorithm with a repulsion strength of 300, among other visualization parameters.

Figure 7.1: Engineering Phase Social Network

Figure 7.1 shows that there are nodes which present a central position in the network, while other nodes are very peripheral. This will be further assessed, since it will allow the study of their importance in the network. The EPC Project graph is directed, meaning that there is a direction associated with a relationship between nodes. This directionality is due to the nature of the problem itself and that can be summarized in the following example: Stakeholder 1 influences Activity A to achieve Innovation Outcome IV. In this context, an Innovation Outcome is the result of an activity which is a result of either other activities’ or stakeholders’ influence. Due to the magnitude of the graph in Figure 7.1, which presents a remarkably high number of nodes and links, it is difficult to further conclude from visual observation. Figure 7.2 presents a detailed version of the social network in Figure 7.1 which illustrates that there are three different node type depicted by their colour: nodes referring to an Activity are coloured in Green, nodes referring to a Stakeholder are coloured in Blue and nodes referring to an Innovation Outcome are coloured in Red. Figure 7.2 also presents the node labels, which facilitate uniquely identification.

Figure 7.2: Detail of Engineering Phase Social Network

Figure 7.2 shows that some Stakeholders appear to possess a substantial power on the network, since they are connected to many activities and innovation outcomes. This will be the focus of study in the following subsections.

Table 7.1 presents a summary of the Engineering Phase social network’s main general characteristics.

Table 7.1: General Characteristics of the Engineering Phase Social Network

| Characteristic | Value |
| --- | --- |
| Total of Nodes | 1684 |
| Total of Edges | 15335 |

Focusing on the types of nodes that exist in the social network under analysis, Figure 7.3 presents a pie chart with their distribution.

Figure 7.3: Distribution of Node Types in the Engineering Phase Social Network

The vast majority of the Engineering Phase social network is composed of activities, which represent 95,5% of the total number of nodes. The second largest group is the Stakeholder nodes’ group, which represent 4,1% of the whole network, and the smallest group belongs to the Innovation Outcome nodes, which represent just 0,4% of the total number of nodes. In summary, there are 1608 Activity nodes, 69 Stakeholder nodes and 7 Innovation Outcomes.

### Engineering Phase Social Network Metrics

In the previous section, general metrics of the social network were presented to get a glimpse of the graphical overview. Here, the focus is on specific metrics related to Social Network Analysis, such as the network diameter, the graph density, the average path length, the average clustering coefficient, and the average degree. The network diameter is the greatest distance between any pair of nodes in the graph. This distance is the shortest path between the node pairs. The network diameter is therefore the maximum of all the shortest paths between any pair of nodes present in the network. The graph density measures the fraction of all the connections that may exist in a network with a certain number of nodes and those that in fact exist. The graph density therefore measures how complete the network is, knowing that a complete graph which has all the possible edges between all of its nodes has a density of 1. The average path length is the average of the length of all paths in the network. The average clustering coefficient is the average of a measure that quantifies the density of the subgraph that includes the neighbours of a specific node. The average clustering coefficient therefore indicates the average of the degree to which network nodes tend to aggregate in clusters established among nodes which share a high density of ties. The average degree is the average of the degrees of all the nodes in the network and offers an overview of the connectivity between the nodes of the network. Table 7.2 presents the metrics for the Engineering Phase Social Network.

Table 7.2: Social Network Metrics of the Engineering Phase Social Network

| Social Network Metrics | Value |
| --- | --- |
| Network Diameter | 28 |
| Graph Density | 0,005 |
| Average Path Length | 5,33 |
| Average Clustering Coefficient | 0,095 |
| Average Degree | 9,106 |

Table 7.2 shows that the network diameter for this network is 28. That means that one of all the possible node pairs has a shortest path that passes through 28 nodes. This implies that there is a set of activities/processes, stakeholders and possible innovation outcomes that are composed by 28 “steps”. This number is in accordance with the magnitude of this EPC project.

Table 7.2 also shows that the graph density is relatively small, presenting a value of 0,005, which is considerably smaller than the value for a complete graph. This means that of all possible connections that may exist in this network, only a small fraction of them are in fact present. This shows that not all entities involved in the EPC Project are interconnected.

In terms of the average path length, the value 5,33 indicates that there are, on average, 5,33 nodes along the shortest paths for all pairs of nodes in this network. The fact that this number is relatively small points to the possibility that this network is an easily negotiable network. This does not mean, however, that there are no nodes which are remotely connected as is the case with the peripheral ones illustrated in Figure 7.1 analysis.

Table 7.2 indicates that the average clustering coefficient is 0,095 which is relatively small, meaning that it is not easy to find well defined clusters in this network. This can be explained by the interconnectivity between activity categories and the fact that stakeholders could have impact on quite different activities. Lastly, the average degree of the network is 9,106 meaning that on average, a node of this network is connected to 9,106 nodes. This metric does not distinguish between in-degree and out-degree. The next subsection will further focus on this Engineering Phase graph’s degree distribution.

### Degree Centrality

The degree of a node is the number of relationships it has with other nodes. In the case of directed graphs (like the one studied here), it is possible to further detail the study of this metric: a node can have a connection starting at it and ending in its neighbour node (Out-degree) or vice-versa (In-degree). Table 7.3 presents the meaning of Degree Centrality, according to each type of node in the EPC Project.

Table 7.3: Degree Centrality Interpretation

| Type of Node | Degree Centrality Interpretation |
| --- | --- |
| Activity Nodes | The degree centrality of an Activity node represents the number of nodes that are connected to it. This number indicates the connectivity of the Activity in the network. As the number of degree centrality increases it indicates that the node can be considered a Hub in the network and thus present an ability to easily receive or send information to a significant number of nodes. |
| Stakeholder Nodes | The degree centrality of a Stakeholder node represents the number of nodes that are connected to it. This number indicates the connectivity of the Stakeholder in the network. As the number of degree centrality increases it indicates that the node can be considered a Hub in the network and thus present an ability to easily receive or send information to a significant number of nodes. |
| Innovation Outcome Nodes | The degree centrality of an Innovation Outcome node represents the number of nodes that are connected to it. This number indicates the connectivity of the Innovation Outcome in the network. As the number of degree centrality increases it indicates that the node can be considered a Hub in the network and thus present an ability to easily receive or send information to a significant number of nodes. |

Figure 7.4 presents the results of the analysis of the Degree, In-Degree and Out-Degree Distribution for the Engineering Phase social network.

a)

b)

c)

Figure 7.4: Degree a), In-Degree b) and Out-Degree c) Centrality in the Engineering Phase Social Network

Figures 7.4 (a), (b) and (c) show that the distribution of the Degree, In-degree and Out-degree values of this network is skewed to the right, meaning that the mean is higher than the mode. Most of the nodes have a low degree value, while there are some nodes which have an exceedingly high degree centrality. This means that most of the nodes of this EPC Project Network have low connectivity and may present some difficulty to access information from other nodes. The existence of outliers (nodes which have a degree centrality that is much higher than the mean) means that the visualisation in Figure 7.4 (a) and 7.4 (b) is difficult. This problem is solved in Figure 7.5 (a), where the nodes with a Degree and Out-Degree Centrality higher than 100 are removed from the plot.

a)

b)

Figure 7.5: Degree a) and Out-Degree b) Centrality in the Engineering Phase Social Network for nodes with less than 100 value

Figure 7.5 shows that the majority of the nodes of the Engineering Phase network has 25 or less connections for both Degree (a) and Out-Degree Centrality (b). Further, few nodes have more than 25 connections, which means that those nodes play a connector role in the network as they are entities that are related to many other entities. Although high Degree Centrality does not necessarily mean high influence or power in the network, it certainly means that the node is very well connected and so it has access to a lot of other nodes.

To facilitate detailed analysis based on different node types, the plots on Figure 7.6 present the results for Degree, In-Degree and Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

b)

a)

c)

I

a)

b)

II

b)

a)))

III

Figure 7.6: Degree Centrality (III) in the Engineering Phase according to node type

Figure 7.6 shows that all distributions are skewed to the right, regardless of the node types and centrality metric. Figure 7.6 II do not present Stakeholder nodes because these nodes do not receive connections from other nodes. This can be explained by that in an EPC project it is expected that activities tend to connect with activities that will happen before and after themselves and that these are numerous. Following the same line of thought, Figure 7.6 III presents only the results for Activity and Stakeholder nodes. This happens because Innovation Outcome nodes do not present any outgoing connection. This is because innovation outcomes are real outcomes, meaning that they are the end-use of several processes in an EPC project.

Focusing on Figure 7.6 I, it is observed that Activities tend to have a considerably lower degree centrality than Stakeholders. This can be explained by that in an EPC project it is expected that activities tend to connect with activities that will happen before and after themselves and that these are numerous. On the other hand, it is also expected that a Stakeholder in the EPC project presents a lot of connections with other nodes, being their activities or innovation outcomes. Also, innovation outcomes originate from several activities and from several stakeholders, so it is likely for them to have a somewhat high degree centrality.

Observing Figure 7.6 II, it is can be note that while Activity nodes follow the same right-skewed distribution that was presented in the Degree Centrality analysis (Figure 7.6 I), Innovation Outcome nodes only differ in terms of In-Degree. In fact, each of the innovation outcome nodes have a unique In-Degree, when in comparison to the same type of nodes.

Focusing on Figure 7.6 III, while Activity nodes present few outgoing connections (most of the nodes have few or no outgoing links at all), Stakeholder Nodes are responsible for having most outcome connections in the network. This is because of their functions as coordinators and influencers of activities and innovation outcomes. In fact, in an EPC Project, a Stakeholder interacts with many Activities and Innovation Outcomes on an outgoing direction, meaning that he/she is the one making decisions and taking actions that influence those nodes. Table 7.4 summarizes the values presented in Figure 7.6 across the different node types and Centrality metrics analysed.

Table 7.4: Degree Centrality relevant values of the Engineering Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Centrality Metric | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| DEGREE | Maximum | 1474 | 285 | 54 | 1474 |
|  | Mean | ~18 | ~11 | ~23 | ~190 |
|  | Mode | 9 | 9 | 9 | 2 |
|  | Minimum | 1 | 1 | 4 | 1 |
| IN-DEGREE | Maximum | 54 | 46 | 54 | 0 |
|  | Mean | ~9 | ~10 | ~23 | 0 |
|  | Mode | 8 | 8 | 9 | 0 |
|  | Minimum | 0 | 0 | 4 | 0 |
| OUT-DEGREE | Maximum | 1474 | 285 | 0 | 1474 |
|  | Mean | ~9 | ~1 | 0 | ~190 |
|  | Mode | 1 | 1 | 0 | 2 |
|  | Minimum | 0 | 0 | 0 | 1 |

Gephi software allows the presentation of the Engineering Phase social network affected by the Degree Centrality metrics calculated above. Figure 7.7 shows these results for Degree, In-Degree and Out-Degree: bigger nodes indicate a higher centrality result.

b)

a)

c)

Figure 7.7: Degree a), In-Degree b) and Out-Degree Centrality c) in the Engineering Phase Social Network

Figure 7.7 (a) shows that nodes representing Stakeholders (blue colour) tend to have higher degree centrality. This is consistent with what was observed before. Figure 7.7 (b) highlights nodes with a high in-degree in larger sizes. Following the colour code created before, it is possible to note that with this distribution, activity and innovation outcome nodes gain relevance in the network.  In Figure 7.7 (c), the visualisation of the Engineering Phase social network was affected by the Out-Degree Centrality: larger nodes indicate a higher Out-Degree Centrality. Following the colour code created before, it is apparent that with this centrality metric, Stakeholder nodes gain relevance in the network. Despite this, there are also some Activity nodes that have achieved some relevance with this metric.

To summarize the conclusions related to the analysis of the Engineering Phase social network, Figure 7.8 presents the Degree, In-Degree and Out-Degree metrics in the same plot.

Figure 7.8: Engineering Phase Social Network summary of Degree Centrality values

Figure 7.8 shows that Stakeholder nodes have only outgoing connections and that they are responsible for the higher values of Degree Centrality, which indicates they possess access to a lot of nodes belonging to activities and innovation outcomes. Also, it is possible to conclude that most activities have incoming connections but present an exceptionally low number of outgoing connections. Most of the Activity nodes are then receptors. Regarding Innovation Outcome nodes, they present only incoming connections, which is aligned to their role in this EPC project. Table 7.5 shows the 10 nodes with higher Degree, In-Degree and Out-Degree centrality in the Engineering Phase.

Table 7.5: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Engineering Phase Social Network

| Centrality Metric | Node Description | Type |
| --- | --- | --- |
| Degree | Engineering Manager | Stakeholder |
|  | Project Manager | Stakeholder |
|  | QA/QC Manager | Stakeholder |
|  | Cost Control Manager/Procurement Engineer | Stakeholder |
|  | Sr. Process Engineer | Stakeholder |
|  | Pipeline Representative | Stakeholder |
|  | Senior Engineer, Piping | Stakeholder |
|  | Sr. Electrical Engineer | Stakeholder |
|  | Sr. Engineer I&C | Stakeholder |
|  | Senior Engineer, Static Equipment | Stakeholder |
| In-Degree | Achieved Industrial Standards | Innovation Outcome |
|  | IPF (SIL Review) | Activity |
|  | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in Philosophy (Successor for Piping Tie-in Schedule & etc.) | Activity |
|  | Issue as IFC | Activity |
|  | Reduced Operational Cost | Innovation Outcome |
|  | Issue as IFC | Activity |
|  | Receive COMPANY Comments / Approval | Activity |
|  | Receive COMPANY Comments / Approval | Activity |
|  | Receive Company Approval | Activity |
|  | 60% Model Review | Activity |
| Out-Degree | Engineering Manager | Stakeholder |
|  | Project Manager | Stakeholder |
|  | QA/QC Manager | Stakeholder |
|  | Cost Control Manager/Procurement Engineer | Stakeholder |
|  | Sr. Process Engineer | Stakeholder |
|  | Pipeline Representative | Stakeholder |
|  | Senior Engineer, Piping | Stakeholder |
|  | Sr. Electrical Engineer | Stakeholder |
|  | Sr. Engineer I&C | Stakeholder |
|  | Senior engineer, Static Equipment | Stakeholder |

Table 7.6 shows the 10 nodes with lower Degree, In-Degree and Out-Degree centrality in the Engineering Phase.

Table 7.6: Ten Nodes with Lower Degree, In-Degree and Out-Degree Centrality in the Engineering Phase Social Network

| Centrality Metric | Node Description | Type |
| --- | --- | --- |
| Degree | Issue Final MTO and MRs for Piping and E&I bulk materials for all facilities. | Activity |
|  | Civil Drawing | Activity |
|  | Foundation and Civil Drawing | Activity |
|  | Civil Drawing | Activity |
|  | Senior Engineer (Operations Readiness) | Stakeholder |
|  | Sr. Engineer, HSE | Stakeholder |
|  | Issue IFC Drawings for E&I and HVAC Systems for Substation & Control Building | Activity |
|  | Issue IFC Drawings / Isometrics for all Under Ground and Above Ground Piping works (90%) required for Train-1 / 2 / 3 | Activity |
|  | Issue all IFC Electrical & Instrument Cable Schedules, Cable Layouts and Equipment Layouts complete for all Facilities. | Activity |
|  | Issue Functional Design Specifications (FDS) duly approved by COMPANY for ICS System | Activity |
| In-Degree | Civil Drawing | Activity |
|  | Foundation and Civil Drawing | Activity |
|  | Civil Drawing | Activity |
|  | Senior Project Manager/Project Manager | Activity |
|  | Sr. Project Engineer | Stakeholder |
|  | Interface Co-ordinator | Stakeholder |
|  | Sr. Planning Engineer | Stakeholder |
|  | Sr. Construction Engineer | Stakeholder |
|  | Team Leader/Engineering Manager | Stakeholder |
|  | Project Co-ordinator | Stakeholder |
| Out-Degree | Geo data and final Reports | Activity |
|  | Reduced project implementation time | Innovation Outcome |
|  | Meets Health and Safety Requirements | Innovation Outcome |
|  | Reduced Operational Cost | Innovation Outcome |
|  | Achieved Industrial Standards | Innovation Outcome |
|  | E&I Cable Tray Drawings | Activity |
|  | Receive COMPANY Comments / Approval | Activity |
|  | Structural Drawings | Activity |
|  | Issue as IFC | Activity |
|  | Issue as IFC | Activity |

### Betweenness Centrality

Betweenness Centrality is the number of shortest paths between each node pair a node is on. This metric represents the degree to which a node stands between each other. A high value of Betweenness indicates a powerful and influential position in a social network because more information passes through it. Betweenness Centrality is an important metric in graph analysis, since it allows to identification of, depending on the problem at hand, who can mediate a conflict, who can share knowledge and information and who can influence a network. In the context of this study, a high betweenness of a node means that it has a high direct influence on the nodes that are connected to it. For instance, if a node has high betweenness and has a lot of incoming connections, it means that node aggregates information from many other nodes and might be able to pass it to its outgoing connections. That node could play a “bridge spanning” role in the network.

An hypothetical example for this case study is the case of an activity with high betweenness that aggregates a lot of information from other activities and stakeholders and that has an outgoing connection to an innovation outcome: this activity would have a very high influence on that innovation outcome, since the amount of information coming from many other sources passing through it is high. In the specific case of the EPC Project being studied, Table 7.7 presents the meaning of Betweenness Centrality, according to each type of node.

Table 7.7: Betweenness Centrality Interpretation

| Type of Node | Betweenness Centrality Interpretation |
| --- | --- |
| Activity Nodes | The betweenness centrality of an Activity node indicates the importance and influence of the component in terms of connecting the components in the network. A high betweenness centrality means that a node can make bridges in the network, putting it in a position of having a lot of information passing through it. For an Activity node, a high betweenness centrality means that it can concentrate information from other Activities and inputs from Stakeholders, treat that information in its task and pass the result onto other Activity or Innovation Outcome nodes. |
| Stakeholder Nodes | The betweenness centrality of a Stakeholder node indicates the importance of the component in terms of connecting the components in the network. A high betweenness centrality means that a node can make bridges in the network, connecting nodes belonging to different parts of the graph. For a Stakeholder node, a high betweenness centrality means that it can influence Activities and Innovation Outcome nodes. |
| Innovation Outcome Nodes | The betweenness centrality of an Innovation Outcome node indicates the importance of the component in terms of connecting the components in the network. A high betweenness centrality means that a node can make bridges in the network, connecting nodes belonging to different parts of the graph. For an Innovation Outcome node, a high betweenness centrality means that it can concentrate information from Activities and inputs from Stakeholders to bridge that information into Innovation |

Figure 7.9 shows the results of the Betweenness Centrality distribution for the Engineering Phase social network.

Figure 7.9: Betweenness Centrality in the Engineering Phase Social Network

Figure 7.9 shows that the distribution is skewed to the right, which means that the mode of the Betweenness Centrality is lower than the mean. It also means that most of the nodes have a low level of betweenness centrality, while a few of them present a high value. This indicates that a small number of nodes of this network might have a high influence in the graph.

To produce a detailed visual analysis, the plot in Figure 7.10 presents the Betweenness Centrality distribution for values smaller than 500.

Figure 7.10: Betweenness Centrality in the Engineering Phase Social Network for nodes with less than 500 value

Figure 7.10 illustrates that the mode of this distribution is 0 and that the majority of nodes present a Betweenness Centrality lower than 100.

Proceeding from the previous subsection, the Betweenness Centrality was analysed categorised by node types: Activity nodes, Innovation Outcome nodes and Stakeholder nodes. Figure 7.11 shows the results of this analysis.

c)

b)

a)

Figure 7.11: Betweenness Centrality in the Engineering Phase according to node type

Figure 7.11 shows that both Innovation Outcome nodes and Stakeholder nodes have a zero Betweenness centrality, which means that the most influential nodes on the Engineering Phase social network are the activity nodes. In fact, Activity nodes’ distribution is like the general Betweenness Centrality distribution presented in Figure 7.9. This conclusion seems counter-intuitive as it might have been expected that Stakeholder nodes would have high Betweenness and influence in the network. One explanation maybe that Stakeholders’ influence can be very localised and so does not have a broader impact on the whole social network. Besides, in an EPC project, it is plausible that a Stakeholder happens to be someone who oversees a group of activities which are interrelated. For instance, it is improbable that a Senior Civil and Structural Engineer (responsible for overseeing Civil and Structural Engineering Activities) has a connection to an Electric Vendor of Switchgears (who acts in Electrical activities). In this example, the existence of a connection between these Stakeholder nodes could bring their Betweenness Centrality to a high value since they would be able to create a bridge between their own sets of activities and so become very influential in the network. Table 7.8 presents relevant values of this distribution.

Table 7.8: Betweenness Centrality relevant values of the Engineering Phase Social Network according to node types

| Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- |
| Maximum | 5198 | 5198 | 0 | 0 |
| Mean | ~163 | ~163 | 0 | 0 |
| Mode | 0 | 0 | 0 | 0 |
| Minimum | 0 | 0 | 0 | 0 |

As illustrated in Table 7.8, only Activity nodes present Betweenness centrality values different from zero. This means that these nodes can pass information from groups of nodes that have loose connection between them.

Following the same procedure as before, a visualisation of the Engineering Phase social network affected by the Betweenness Centrality was performed using Gephi software. Figure 7.12 shows these results: larger nodes indicate a higher Betweenness Centrality.

Figure 7.12: Engineering Phase Social Network affected by Betweenness Centrality

Figure 7.12 highlights nodes with high Betweenness in larger sizes. Using the colour code created earlier, it is possible to note that with this distribution, Activity nodes gain relevance in the network. This happens because some activities can act as boundary spanners, creating bridges between activities and stakeholders which have a loose relationship between them. Table 7.9 shows the 10 nodes with higher Betweenness Centrality in the Engineering Phase for the Activity nodes since the other types of nodes have a zero betweenness value. To allow a more precise identification of the nodes, the WBS name and the project activity description were added.

Table 7.9: Ten Nodes with Higher Betweenness Centrality in the Engineering Phase Social Network

| Betweenness Centrality |  |  |  |
| --- | --- | --- | --- |
| Node | Type | WBS Task Name | Project Activity Description |
| A30180 | Activity | Compressor Area | Piling Drawings |
| A30340 | Activity | Utility Area | Piling Drawings |
| A30670 | Activity | Tank Area | Piling Drawings |
| A17170 | Activity | Overall Plot Plans/Area Plot Plans | Issue as IFC |
| A11060 | Activity | P&ID - Sales Gas Compressor | Issue as IFC |
| A17160 | Activity | Overall Plot Plans/Area Plot Plans | Receive Company Approval |
| A30450 | Activity | Control Room | Piling Drawings |
| A30560 | Activity | Custody Area | Piling Drawings |
| A19070 | Activity | Piping General Arrangement Drawings extracted from 3-D Model | Prepare & Issue for COMPANY Review (ICR) |
| A12920 | Activity | Process Calculations Report | Issue as IFC |

Table 7.9 facilitates understanding of the meaning of Betweenness Centrality in an EPC Project. The nodes with higher betweenness seem to be associated with activities that are transversal to several WBS tasks, making an effective bridge between those tasks. For instance, the activity “Piling Drawings” involves several WBS tasks whose only relationship maybe through this activity.

### Closeness Centrality

Closeness Centrality is the inverse of the mean shortest path between a node and all other nodes in the network that are reachable from it. This metric reflects the ability of a node to access information through the network and communicating quickly (because they are close). It also indicates how close a node is from every other node in the network. Nodes with high closeness centrality have a central position in the network since they are close to other nodes.

Table 7.10: Closeness Centrality Interpretation

| Type of Node | Closeness Centrality Interpretation |
| --- | --- |
| Activity Nodes | The closeness centrality of an Activity node indicates the importance of the component in terms of having a central position in the network. A high closeness centrality means that a node is very central and is practically close to every other node. For an Activity node, a high closeness centrality means that it possesses a direct connection to many Activities, Stakeholders, and Innovation Outcomes. |
| Stakeholder Nodes | The closeness centrality of a Stakeholder node indicates the importance of the component in terms of having a central position in the network. A high closeness centrality means that a node is very central and is practically close to every other node. For a Stakeholder node, a high closeness centrality means that it possesses a direct connection to many Activities, Stakeholders, and Innovation Outcomes. |
| Innovation Outcome Nodes | The closeness centrality of an Innovation Outcome node indicates the importance of the component in terms of having a central position in the network. A high closeness centrality means that a node is very central and is practically close to every other node. For an Innovation Outcome node, a high closeness centrality means that it possesses a direct connection to many Activities, Stakeholders, and Innovation Outcomes. Particularly, this would mean that it could be easy for Activities and Stakeholders to reach this Innovation Outcome node and therefore induce innovation. |

Figure 7.13 shows the results of the Closeness Centrality distribution for the Engineering Phase social network.

Figure 7.13: Closeness Centrality in the Engineering Phase Social Network

As illustrated, most of the nodes have a low closeness, meaning that they are not central to the network, while a few of them tend to have a high closeness value. The analysis of Closeness Centrality was performed according to the types of nodes. Figure 7.14 presents the results of this analysis.

b)

c)

a)

Figure 7.14: Closeness Centrality in the Engineering Phase according to node type

Figure 7.14 shows that Innovation Outcome nodes are generally distant from every other node in the network since their closeness is zero. If Innovation Outcomes are not close to an EPC Project activities and stakeholders, it means that innovation might not be a priority. Table 7.11 summarises the relevant values presented across the different node types.

Table 7.11: Closeness Centrality relevant values of the Engineering Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- |
| Maximum | 1 | 1 | 0 | 0,93 |
| Mean | ~0,31 | 0,31 | 0 | 0,36 |
| Mode | 0,25 | 0,5 | 0 | 0,20 |
| Minimum | 0 | 0 | 0 | 0,15 |

Table 7.11 shows what was previously noted for the Innovation Outcome nodes. It also shows that the Closeness values for Activity nodes and for Stakeholder nodes are somehow similar.

Following the same procedure as before, a visualisation of the Engineering Phase social network was performed using Gephi software. Figure 7.15 shows these results: larger nodes indicate a higher Closeness Centrality.

Figure 7.15: Engineering Phase Social Network affected by Closeness Centrality

Figure 7.15 highlights nodes with a high closeness in larger numbers. Following the colour code created earlier, it is noted that with this distribution, activity and stakeholder nodes gain relevance in the network. This happens because activities are close to each other in terms of a WBS logic and they are also close to stakeholders. Table 7.12 shows the 10 nodes with higher Closeness Centrality in the Engineering Phase. To allow a more precise identification to the nodes, the WBS name and the project activity description were added.

Table 7.12: Ten Nodes with Higher Closeness Centrality in the Engineering Phase Social Network

| Closeness Centrality |  |  |  |
| --- | --- | --- | --- |
| Node | Type | WBS Task Name | Project Activity Description |
| G1020 | Activity | - | Site Survey |
| A30980 | Activity | Substation area | E&I Support Drawings |
| A30320 | Activity | Compressor Area | E&I Support Drawings |
| A.10 | Activity | - | Issue Functional Design Specifications (FDS) duly approved by COMPANY for ICS System (Includes DCS, ESD, F&G, MMS and An |
| A.11 | Activity | - | Finalize and issue IFC all instrumentation loop diagrams |
| A4350 | Activity | Architectural Raised Floor Layout Details and Schedule for Control Room Building | Receive Company Approval |
| A13780 | Activity | Doors | Issue as IFC |
| A4700 | Activity | New Gas Compressor Station Storm water drainage - layout | Receive Company Approval |
| A4770 | Activity | New Gas Compressor Station Storm water drainage - Details | Receive Company Approval |
| A4840 | Activity | New Gas Compressor Station AOC water drainage - layout | Receive Company Approval |

Table 7.12 presents a list of nodes which have high closeness and so play a central role in the network. Looking at the nodes’ descriptions, it is observed that they belong to activities which are related to beginning or ending tasks. This means that these activities seem to be the ones at the beginning of the project (“Site survey”) and the last ones of some WBS tasks. It is therefore expected that these nodes have a high closeness, since they must be close to all the other nodes that represents sets of activities related to the task they belong to.

### Comparison of Centrality Metrics

The previous subsections focused on individual analysis of each of the social network centrality measures: Degree Centrality, Betweenness Centrality and Closeness Centrality. These analyses were performed for the whole Engineering Phase social network. Figure 7.16 shows an ensemble of these measures.

Figure 7.16: Engineering Phase Social Network summary of Centrality metrics

Observing Figure 7.16, it is apparent that Closeness Centrality tends to present higher values. Further, most of the nodes have a low degree centrality. Focusing on the outliers present in Figure 7.16, it is observed that there are some nodes that happen to have high values closeness and degree centralities but have low betweenness. Most of these nodes belong to the Activity type of nodes.

## Study of Process Innovation Outcomes

The focus of this work is based on Innovation associated with this EPC project. It is therefore important to use Social Network Analysis to help categorize and characterize the Innovation Outcome nodes. To do so, the ego network tool will be used. An Ego Network consists of a focal node (which is called the “ego”) and all the nodes that have some relationship to it. This relationship can be direct, meaning that the nodes are adjacent, or it can be derived in second levels.

The use of this technique will allow the modelling and study of the influence that activities and/or stakeholders have in each of the three Innovation Outcomes related to Process Innovation.

### Process Innovation Outcomes’ Ego Networks.

There are three Innovation Outcomes related to Process Innovation in this Engineering Phase’s EPC project. Table 7.13 presents these Innovation Outcomes considered in this study, along with their description and identifications, and the characteristics of their Ego Networks.

Table 7.13: Process Innovation Outcomes’ Information

| Innovation Outcome | Label | Description | Total of Nodes | Total of Edges |
| --- | --- | --- | --- | --- |
| 3501 | B | Reduced Project Implementation Time | 115 | 722 |
| 3506 | G | Improved Procurement Activities | 30 | 108 |
| 3508 | I | Reduced Operational Cost | 147 | 1253 |

According to the information on Table 7.13, it is possible to see that Innovation Outcome “Reduced Operational Cost” presents a bigger Ego Network than those of Innovation Outcome “Reduced Project Implementation Time” and “Improved Procurement Activities”. To further assess the characteristics of these Ego Networks, the plot in Figure 7.17 presents their distribution according to node types.

Figure 7.17: Distribution of Node Types for Process Innovation Outcomes’ Ego Networks

Figure 7.18 presents the Process Innovation Outcomes’ Ego Networks, created with Gephi software. The Fruchterman Reingold layout algorithm was used to improve visualisation.

b)

a)

c)

Figure 7.18: Ego Networks of Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

### Degree Centrality

Following the procedure performed for the Engineering Phase Overview, Figure 7.19 presents the results for the Degree, In-Degree and Out-Degree Centrality analysis of the Process Innovation Ego Networks.

c)

b)

a)

I

c)

b)

a)

II

b)

c)

a)

III

Figure 7.19: Degree (I), In-Degree (II) and Out-Degree Centrality (III) of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figure 7.19 shows that for all the three Innovation Outcomes analysed in this section, the distributions are all right skewed. This is the case for Degree, In-Degree and Out-Degree Centrality, which means that most of the nodes of these Ego Networks present few connections (whether incoming or outgoing). In fact, this is according to the EPC Project Network in which only a few Activities, Innovation Outcomes and/or Stakeholders present a high number of connections. These outliers can be team leaders, project managers, planning activities, financial and project management related tasks, which are entities that traditionally need information or exercise coordination over a high number of other entities and/or activities. Figures 7.19 I (b), 7.19 II (b) and 7.19 III (b) present a relatively low value of degree centrality metrics which could be explained by that Innovation Outcome “Improved Procurement Activities” has a low number of nodes and is a small Ego Network. This can be explained focusing on the description of the Innovation Outcome: Improved Procurement Activities. In fact, this innovation is targeted since its scope is within Procurement, which is also a major phase of this EPC Project. It is not part of the Engineering Phase.

Figures 7.19 I (c), 7.19 II (c) and 7.19 III (c) present some heavy outliers on the degree centrality metric which means Innovation Outcome “Reduced Operational Cost” has a few nodes that present a significant amount of links to other nodes. These outliers may prove to be nodes with high influence on the Ego Network.  Further, Figures 7.19 II and 7.19 III show that the Out-Degree outliers present in the three Innovation Outcomes have a higher centrality metric than the In-Degree ones, which means the nodes with more outgoing connections have more links than the nodes with incoming connections.

Detailed analysis according to the different node types (Activities, Innovation Outcomes and Stakeholders) produced results for Degree Centrality illustrated on Figure 7.20.

c)

b)

a)

b)

c)

a)

I

II

c)

a)

b)

III

Figure 7.20: Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 7.20 I shows that the maximum value of Degree Centrality for Activity nodes is higher than 40, while for Stakeholder it is even higher. Meanwhile, most Innovation Outcome nodes present a low value of Degree Centrality. Figure 7.20 II shows that the maximum value of Degree Centrality for Stakeholder nodes is 12, while for Activity it is slightly higher. Meanwhile, most Innovation Outcome nodes present a low value of Degree Centrality. Figure 7.20 III shows that the maximum value of Degree Centrality for Stakeholder nodes is close to 125, while for Activity around 30 and for Innovation Outcome nodes is close to 40. Further, Figure 7.20 shows that it is difficult to find homogeneity in the comparison of the results of each Innovation Outcome, but there is a little similarity between the results in Figure 7.20 I and Figure 7.20 II. This can be explained by that Innovation Outcomes “Reduced Project Implementation Time” and “Reduced Operational Cost” are both related to efficiency increase (time and cost) in processes and, despite their Ego Networks’ differences in size, they present some acquaintance.

Table 7.14 summarizes the values presented in Figure 7.20 across the different node types.

Table 7.14: Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 50 | 44 | 14 | 54 |
|  | Mean | ~13 | ~15 | ~8 | ~11 |
|  | Mode | 3 | 3 | 4 | 3 |
|  | Minimum | 1 | 1 | 4 | 1 |
| Improved Procurement Activities | Maximum | 17 | 17 | 4 | 12 |
|  | Mean | ~7 | ~10 | ~3 | ~7 |
|  | Mode | 8 | 11 | 2 | 8 |
|  | Minimum | 2 | 3 | 2 | 2 |
| Reduced Operational Cost | Maximum | 121 | 33 | 39 | 121 |
|  | Mean | ~17 | ~12 | ~20 | ~53 |
|  | Mode | 15 | 15 | 6 | 31 |
|  | Minimum | 2 | 2 | 2 | 19 |

Figure 7.21 was built to present the impact of Degree Centrality in the studied social ego networks: larger nodes indicate a higher Degree Centrality.

b)

a)

c)

Figure 7.21: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” a), “Improved Procurement Activities” b) and “Reduced Operational Cost” c)

Figure 7.21 shows the conclusions drawn before, that some Stakeholder and Activity nodes tend to have high Degree Centrality, while Innovation Outcome nodes tend to present lower values than the other. Figure 7.22 is similar to Figure 7.20, but it shows the results for In-Degree Centrality according to the node types.

b)

c)

a)

c)

b)

a)

I

II

b)

c)

a)

III

Figure 7.22: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 7.22 shows that, across all the Innovation Outcomes analysed, every Stakeholder node presented an In-Degree of zero. This means that there are no Stakeholder nodes with incoming links. This can be explained looking at the nature of the Stakeholder itself: a Stakeholder of an EPC Project is a person who interacts with one or more activities and one or more innovation outcomes during his job. For instance, a Project Manager is a Stakeholder who can interact (and this interaction can be a supervision) with many activities and or innovation outcomes. Nonetheless, activities and or innovation outcomes cannot interact with Stakeholders and that is the reason why they do not possess incoming connections. Therefore, it is possible to conclude that, given the fact that Figure 7.20 showed that there are many Stakeholder nodes with a Degree value different from zero, these types of nodes present only outgoing connections in the Engineering Phase.

Table 7.15 summarizes the values presented in Figure 7.22 across the different node types.

Table 7.15: In-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 42 | 42 | 14 | 0 |
|  | Mean | ~6 | ~12 | ~8 | 0 |
|  | Mode | 0 | 2 | 4 | 0 |
|  | Minimum | 0 | 0 | 4 | 0 |
| Improved Procurement Activities | Maximum | 13 | 13 | 4 | 0 |
|  | Mean | ~4 | ~9 | ~3 | 0 |
|  | Mode | 0 | 10 | 2 | 0 |
|  | Minimum | 0 | 2 | 2 | 0 |
| Reduced Operational Cost | Maximum | 39 | 14 | 39 | 0 |
|  | Mean | ~9 | ~10 | ~20 | 0 |
|  | Mode | 0 | 9 | 6 | 0 |
|  | Minimum | 0 | 0 | 2 | 0 |

Figure 7.23 was built to present the impact of In-Degree Centrality in the studied social ego networks: larger nodes indicate a higher In-Degree Centrality.

a)

b)

c)

Figure 7.23: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figure 7.24 is like Figure 7.20 and Figure 7.22, but it shows the results for Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

I

c)

b)

a)

II

c)

b)

a)

III

Figure 7.24: Out-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 7.24 shows that, across all the Innovation Outcomes analysed, every Innovation Outcome node presented an Out-Degree of zero. This means that there are no Innovation Outcome nodes with outgoing links. This can be explained looking at the nature of the Innovation Outcome itself: they are real outcomes, meaning that they are the end-use of several processes in an EPC project. This way, as was observed in Figure 7.22, it is plausible that this type of node possesses no outgoing connections and one or more incoming links. Besides, Figure 7.24 also shows that Stakeholder nodes are responsible for the maximum values of Out-Degree and that Activity nodes tend to present low levels of Out-Degree Centrality. Table 7.16 summarizes the values presented in Figure 7.24 across the different node types.

Table 7.16: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 54 | 13 | 0 | 54 |
|  | Mean | ~6 | ~3 | 0 | ~11 |
|  | Mode | 0 | 1 | 0 | 3 |
|  | Minimum | 0 | 0 | 0 | 1 |
| Improved Procurement Activities | Maximum | 12 | 5 | 0 | 12 |
|  | Mean | ~4 | ~2 | 0 | ~7 |
|  | Mode | 0 | 0 | 0 | 8 |
|  | Minimum | 0 | 0 | 0 | 2 |
| Reduced Operational Cost | Maximum | 121 | 33 | 0 | 121 |
|  | Mean | ~9 | ~3 | 0 | ~53 |
|  | Mode | 0 | 1 | 0 | 31 |
|  | Minimum | 0 | 0 | 0 | 19 |

Figure 7.25 was built to present the impact of Out-Degree Centrality in the studied social ego networks: larger nodes indicate a higher Out-Degree Centrality.

b)

a)

c)

Figure 7.25: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

To summarize the conclusions related to the analysis of the Process Innovation Outcomes, Figure 7.26 presents the Degree, In-Degree and Out-Degree metrics in the same plots.

b)

a)

b)

c)

Figure 7.26: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c))

Figure 7.26 shows that Stakeholder nodes have only outgoing connections and that they are responsible for the higher values of Degree Centrality, which indicates that they possess access to a lot of nodes belonging to activities and innovation outcomes. It is also possible to conclude that there are some Activity nodes with high values of In-Degree and a significant value of Out-Degree Centrality. This happens across all the Innovation Outcomes.

Focusing on the results for Activity nodes, it is possible to conclude that they tend to present higher In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (Figure 7.26 a), while for Innovation Outcome “Improved Procurement Activities” (Figure 7.26 b), Activity nodes present a mix of high In- and Out- Degree values. This means that the Innovation Outcome described by “Improved Procurement Activities” tends to present activities with a high number of connections, both in and out of their nodes. This can be explained by these activities being related to procurement, which is categorized for a lot of in and out relationships between different tasks and Stakeholders on an EPC Project. On the other hand, Innovation Outcome “Reduced Operational Costs” Ego Network (Figure 7.26 c)) presents Activity nodes with low In-Degree Centrality value.

Table 7.17 shows the five nodes with higher Degree, In-Degree and Out-Degree centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”).

Table 7.17: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Networks

|  | Centrality Metric | Node Description | Type |
| --- | --- | --- | --- |
| Reduced Project Implementation Time | Degree | QA/QC Manager | Stakeholder |
|  |  | Sr. Process Engineer | Stakeholder |
|  |  | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in Philosophy (Successor for Piping Tie-in Schedule & etc.) | Activity |
|  |  | IPF (SIL Review) | Activity |
|  |  | Reduced deliverable review cycle (From 10 to 3 days) | Activity |
|  | In-Degree | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in Philosophy (Successor for Piping Tie-in Schedule & etc.) | Activity |
|  |  | IPF (SIL Review) | Activity |
|  |  | 60% Model Review | Activity |
|  |  | 90% Model Review | Activity |
|  |  | Reduced deliverable review cycle (From 10 to 3 days) | Activity |
|  | Out-Degree | QA/QC Manager | Stakeholder |
|  |  | Sr. Process Engineer | Stakeholder |
|  |  | Senior Engineer, Piping | Stakeholder |
|  |  | Sr. Engineer I&C | Stakeholder |
|  |  | Senior Engineer, Rotating Equipment | Stakeholder |
| Improved Procurement Activities | Degree | Issue as IFC | Activity |
|  |  | Issue as IFC | Activity |
|  |  | Issue as IFC | Activity |
|  |  | QA/QC Manager | Stakeholder |
|  |  | Receive Company Approval | Activity |
|  | In-Degree | Issue as IFC | Activity |
|  |  | Issue as IFC | Activity |
|  |  | Issue as IFC | Activity |
|  |  | Prepare & Issue for COMPANY Review (ICR) Mechanical Design Basis TBE for Mechanical equipment & packages Addendum to DGS etc. | Activity |
|  |  | Issue as IFC | Activity |
|  | Out-Degree | QA/QC Manager | Stakeholder |
|  |  | Sr. Electrical Engineer | Stakeholder |
|  |  | Project Manager | Stakeholder |
|  |  | Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | QA/QC Manager | Stakeholder |
| Reduced Operational Cost | Degree | QA/QC Manager | Stakeholder |
|  |  | Sr. Process Engineer | Stakeholder |
|  |  | Senior Engineer, Piping | Stakeholder |
|  |  | Senior Engineer, Static Equipment | Stakeholder |
|  |  | Sr. Engineer I&C | Stakeholder |
|  | In-Degree | Reduced operational cost | Innovation Outcome |
|  |  | Reduced Production Cost | Innovation Outcome |
|  |  | Issue as IFC 1) Process flow diagram 2) Utility flow diagram 3) Block flow diagram 4) Process design basis & process description 5) All other P&IDs 6) Line list (predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in | Activity |
|  |  | Issue as IFC | Activity |
|  |  | Achieved industrial standards | Innovation Outcome |
|  | Out-Degree | QA/QC Manager | Stakeholder |
|  |  | Sr. Process Engineer | Stakeholder |
|  |  | Senior Engineer, Piping | Stakeholder |
|  |  | Senior Engineer, Static Equipment | Stakeholder |
|  |  | QA/QC Manager | Stakeholder |

### Betweenness Centrality

Following the procedure of the previous sections, Figure 7.27 presents the results for the Betweenness Centrality analysis of the Process Innovation Ego Networks.

c)

a)

b)

Figure 7.27: Betweenness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figure 7.27 shows that the Betweenness Centrality distribution is skewed to the right for all Process Innovation Outcomes, which means that the mode of the Betweenness Centrality is lower than the mean. It also means that most of the nodes have a low level of betweenness centrality, while a few of them present a high value. This indicates that a small number of nodes of this network might have a high influence in it. Particularly, these nodes might be able to make bridges in the social network and make information flow through the graph. In an EPC Project, this role is particularly important, especially when it comes to Innovation, because before innovating it is crucial to have access to a lot of information from different sources in order to correctly tackle the problem.

Focusing on Figure 7.27 (b), it is possible to notice that most of the nodes present a zero Betweenness value, which indicates that only a small fraction of nodes might have a high influence in the graph. This can be explained by that Innovation Outcome “Improved Procurement Activities” Ego Network is relatively small, meaning that the existence of bridges is difficult, since the nodes are too close to each other. In terms of the EPC Project, this means that for innovating Improved Procurement Activities there might not be need to search for information from different Activities and/or Stakeholders since Procurement is a highly specific activity.

From Figure 7.27 (a) and 7.27 (c), it is apparent that most of the nodes have a zero betweenness and this can be due to a certain homogeneity among the nodes present in the Innovation Ego Networks. This means that, as the Ego Networks are built around the Innovation Outcome in analysis, their scope is focused making it difficult for most of the nodes to make bridges. In that regard, few can present significant values. A detailed analysis for Betweenness Centrality according to the different node types is presented in Figure 7.28.

a)

b)

c)

I

a)

b)

c)

II

b)

c)

a)

III

Figure 7.28: Betweenness Centrality for “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 7.28 shows that, independently of the Innovation Outcome studied, Innovation Outcome nodes and Stakeholder nodes present zero betweenness centrality, which means that the most influencing nodes on this Ego Network are the Activity nodes. This comes in line with what was noted and explained in previous sections, namely in section 7.2.3.

Table 7.18 summarizes the values presented in Figure 7.28 across the different node types.

Table 7.18: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | ~364 | ~364 | 0 | 0 |
|  | Mean | ~15 | ~29 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Improved Procurement Activities | Maximum | ~39 | ~39 | 0 | 0 |
|  | Mean | ~3 | ~7 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Reduced Operational Cost | Maximum | ~7 | ~77 | 0 | 0 |
|  | Mean | ~7 | ~8 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 7.29 was built to present the impact of Betweenness Centrality in the studied social ego networks: larger nodes indicate a higher Betweenness Centrality.

b)

a)

c)

Figure 7.29: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Following the colour code created earlier, it is possible to note that with this distribution, activity nodes gain relevance in the network. This happens because some activities can act as boundary spanners, creating bridges between activities and stakeholders which have a loose relationship between them.

Table 7.19 shows the five nodes with higher Betweenness centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”). To allow a more precise identification to the nodes, the WBS name and the project activity description were added to the table.

Table 7.19: Five Nodes with Higher Betweenness Centrality for each Process Innovation Outcome

| Betweenness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Project Implementation Time | PM0005b | Activity | Document Review Management | Reduced deliverable review cycle (From 10 to 3 days) |
|  | PM0006b | Activity | Document Review Management | Across the table approval for critical documents |
|  | A11060 | Activity | P&ID - Sales Gas Compressor | Issue as IFC |
|  | A12360 | Activity | P&ID - Flare Package | Issue as IFC |
|  | A11730 | Activity | P&ID - Nitrogen Generation Package | Issue as IFC |
| Improved Procurement Activities | A16610 | Activity | Instrument air package Data Sheets (air dry compressor) | Issue as IFC |
|  | A14720 | Activity | Specification for Pressure Vessels | Issue as IFC |
|  | A23820 | Activity | Electrical Load List | Issue as IFC |
|  | A16600 | Activity | Instrument air package Data Sheets (air dry compressor) | Receive Company Approval |
|  | A22490 | Activity | Overall Electrical Equipment Layout - Plan & Section | Issue as IFC |
| Reduced Operational Cost | A11060 | Activity | P&ID - Sales Gas Compressor | Issue as IFC |
|  | A19410 | Activity | Pipeline Design Basis | Issue as IFC |
|  | A14930 | Activity | Mechanical Design Basis -Static Equipment | Issue as IFC |
|  | A11730 | Activity | P&ID - Nitrogen Generation Package | Issue as IFC |
|  | A14920 | Activity | Mechanical Design Basis -Static Equipment | Receive Company Approval |

### Closeness Centrality

Following the procedure of the previous sections, Figure 7.30 presents the results for the Closeness Centrality analysis of the Process Innovation Ego Networks.

c)

a)

b)

Figure 7.30: Closeness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

There are a significant number of nodes with zero closeness across all the Process Innovation Outcomes, meaning that they do not have a central position in their Ego Network. It is also apparent that once those nodes are excluded, the closeness is relatively high and that some nodes seem to be close to their neighbours.  To further detail the analysis according to the different node types, the plots on Figure 7.31 present the results for Closeness Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

a)

b)

c)

I

c)

b)

a)

II

c)

b)

a)

III

Figure 7.31: Closeness Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figures 7.31 I (b), 7.31 II (b) and 7.31 III (b) show that Innovation Outcome nodes are generally distant from every other node in the network since their closeness is zero. Further, it can be observed that some Activity nodes are very peripheral in the network and that some of them tend to play a central role in it. Besides, Stakeholder nodes seem to present a high closeness centrality. This means that Stakeholder nodes can directly influence other nodes in these three Ego Networks.

Figures 7.31 I (a), 7.31 II (a) and 7.31 III (a) also show that, across all Innovation Outcomes studied, there is a high number of Activity nodes with zero closeness centrality.

Observing Figures 7.31 I (c), 7.31 II (c) and 7.31 III (c), it is possible to conclude that there are no Stakeholder nodes with zero closeness. Table 7.20 summarizes the values presented in Figure 7.31 across the different node types.

Table 7.20: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 1 | 1 | 0 | ~0,92 |
|  | Mean | ~0,51 | ~0,51 | 0 | ~0,54 |
|  | Mode | 0 | 0 | 0 | ~0,41 |
|  | Minimum | 0 | 0 | 0 | ~0,41 |
| Improved Procurement Activities | Maximum | 1 | 1 | 0 | ~0,8 |
|  | Mean | ~0,53 | ~0,53 | 0 | ~0,7 |
|  | Mode | 0 | 0 | 0 | ~0,8 |
|  | Minimum | 0 | 0 | 0 | ~0,53 |
| Reduced Operational Cost | Maximum | 1 | 1 | 0 | ~0,97 |
|  | Mean | ~0,53 | ~0,53 | 0 | ~0,77 |
|  | Mode | 0 | 0 | 0 | ~0,94 |
|  | Minimum | 0 | 0 | 0 | ~0,51 |

Figure 7.32 was built to present the impact of Closeness Centrality in the studied social ego networks: larger nodes indicate a higher Closeness Centrality.

b)

a)

c)

Figure 7.32: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Following the colour code created before and by observing the results presented in Figure 7.32 (a), 7.32 (b) and 7.32 (c), it is apparent that with this distribution, Activity and Stakeholder nodes gain relevance in the network. It is also possible to notice that generally the Closeness Centrality is high.

Table 7.21 shows the five nodes with higher Closeness centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”). To allow a more precise identification of the nodes, the WBS name and the project activity description were added.

Table 7.21: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks

| Closeness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Project Implementation Time | EP1120 | Activity |  | 90% Model Review |
|  | A29360 | Activity | Process Balance Documents | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in Philosophy ( Successor for Piping Tie-in Schedule & etc.) |
|  | SH62 | Stakeholder |  | Engineering Manager |
|  | A11060 | Activity | P&ID - Sales Gas Compressor | Issue as IFC |
|  | A11730 | Activity | P&ID - Nitrogen Generation Package | Issue as IFC |
| Improved Procurement Activities | A16610 | Activity | Instrument air package Data Sheets (air dry compressor) | Issue as IFC |
|  | A14720 | Activity | Specification for Pressure Vessels | Issue as IFC |
|  | A22490 | Activity | Overall Electrical Equipment Layout - Plan & Section | Issue as IFC |
|  | A23820 | Activity | Electrical Load List | Issue as IFC |
|  | A16610 | Activity | Instrument air package Data Sheets (air dry compressor) | Issue as IFC |
| Reduced Operational Cost | A11060 | Activity | P&ID - Sales Gas Compressor | Issue as IFC |
|  | A11730 | Activity | P&ID - Nitrogen Generation Package | Issue as IFC |
|  | A12360 | Activity | P&ID - Flare Package | Issue as IFC |
|  | A29360 | Activity | Process Balance Documents | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in Philosophy ( Successor for Piping Tie-in Schedule & etc.) |
|  | A16330 | Activity | EOT crane Data Sheets | Issue as IFC |

### Comparison of Centrality Metrics

The previous subsections focused on individual analysis of each of the social network centrality measures: Degree Centrality, Betweenness Centrality and Closeness Centrality. These analyses were performed together for the three Process Innovation Outcomes.

Figure 7.33 presents an ensemble of these measures’ results.

b)

a)

c)

Figure 7.33: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figures 7.33 (a), (b) and (c) show that across all Innovation Outcomes, there are nodes which possess zero Closeness and zero Betweenness Centrality. Apart from these, Activity and Stakeholder nodes tend to present high Closeness Centrality. Also, in this latest group, a significant number of nodes present Betweenness Centrality above zero, with some cases presenting a high value of this metric. In fact, there is an important group of outliers, all Activity nodes, which present high values of Betweenness, Closeness and Degree centrality. These can be found in the top left of the plots of Figure 7.33 (a), (b) and (c).

In terms of relevance for this study, one can note that there are some Activity nodes that have high betweenness and so could prove to be influential in the network. Also, it is possible to observe that Stakeholder nodes have access to a lot of nodes and possess some central role in the network, so they can also be considered influential.

Considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network, the most influential Stakeholder nodes of Innovation Outcome “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost” are the ones present in Table 7.22.

Table 7.22: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost” Ego Networks

| Stakeholder Nodes |  |  |  |
| --- | --- | --- | --- |
| Innovation Outcome | Node | Degree | Closeness |
| Reduced Project Implementation Time | QA/QC Manager | 54 | 0.921875 |
|  | Sr. Process Engineer | 53 | 0.907692 |
|  | Senior Engineer, Piping | 38 | 0.880000 |
|  | Sr. Engineer I&C | 32 | 0.796296 |
|  | Senior Engineer, Rotating Equipment | 30 | 0.767857 |
| Improved Procurement Activities | QA/QC Manager | 12 | 0.800000 |
|  | Sr. Electrical Engineer | 10 | 0.777778 |
|  | Project Manager | 8 | 0.750000 |
|  | Cost Control Manager/Procurement Engineer | 8 | 0.750000 |
|  | QA/QC Manager | 8 | 0.750000 |
| Reduced Operational Cost | QA/QC Manager | 121 | 0.961832 |
|  | Cost Control Manager/Procurement Engineer | 54 | 0.935484 |
|  | QA/QC Manager | 54 | 0.935484 |
|  | Sr. Process Engineer | 108 | 0.928571 |
|  | Senior Engineer, Piping | 82 | 0.927083 |

In terms Activities influence on Innovation Outcomes “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”, Table 7.23 presents those which have high Betweenness, high Closeness and high Degree.

Table 7.23: Five Activity nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost” Ego Networks

| Activity Nodes |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | WBS Name | Description | Degree | Closeness |
| Reduced Project Implementation Time | Document Review Management | Reduced deliverable review cycle (From 10 to 3 days) | 42 | 0.625000 |
|  | Document Review Management | Across the table approval for critical documents | 42 | 0.625000 |
|  | P&ID - Sales Gas Compressor | Issue as IFC | 22 | 0.909091 |
|  | P&ID - Flare Package | Issue as IFC | 20 | 0.909091 |
|  | P&ID - Nitrogen Generation Package | Issue as IFC | 20 | 0.909091 |
| Improved Procurement Activities | Instrument air package Data Sheets (air dry compressor) | Issue as IFC | 17 | 1 |
|  | Specification for Pressure Vessels | Issue as IFC | 17 | 1 |
|  | Electrical Load List | Issue as IFC | 9 | 1 |
|  | Instrument air package Data Sheets (air dry compressor) | Receive Company Approval | 11 | 0.545455 |
|  | Overall Electrical Equipment Layout - Plan & Section | Issue as IFC | 8 | 1 |
| Reduced Operational Cost | P&ID - Sales Gas Compressor | Issue as IFC | 22 | 1 |
|  | Pipeline Design Basis | Issue as IFC | 21 | 0.923077 |
|  | Mechanical Design Basis -Static Equipment | Issue as IFC | 20 | 1 |
|  | P&ID - Nitrogen Generation Package | Issue as IFC | 10 | 1 |
|  | Mechanical Design Basis -Static Equipment | Receive Company Approval | 10 | 0.521739 |

## Stude of Product Innovation Outcomes

### Product Innovation Outcomes’ Ego Networks.

There are three Innovation Outcomes related to Product Innovation in this Engineering Phase’s EPC project. Table 7.24 presents the Innovation Outcomes considered in this study along with their description and identifications and the characteristics of their Ego Networks.

Table 7.24: Product Innovation Outcomes’ Information

| Innovation Outcome | Label | Description | Total of Nodes | Total of Edges |
| --- | --- | --- | --- | --- |
| 3500 | A | Reduced Production Cost | 122 | 917 |
| 3503 | D | Meets Health and Safety Requirements | 84 | 393 |
| 3509 | I | Achieved Industrial Standards | 192 | 1636 |

According to the information on Table 7.24, Innovation Outcome “Achieved Industrial Standards” presents a bigger Ego Network than those of Innovation Outcome “Reduced Production Cost” and “Meets Health and Safety Requirements”. To further assess the characteristics of these Ego Networks, the plot in Figure 7.34 presents their distribution according to node types.

Figure 7.34: Distribution of Node Types for Product Innovation Outcomes

Figure 7.35 presents the Product Innovation Outcomes’ Ego Networks. The Fruchterman Reingold layout algorithm was used to improve visualisation.

b)

a)

c)

Figure 7.35: Ego Networks of Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

### Degree Centrality

Figure 7.36 presents the results for the Degree, In-Degree and Out-Degree Centrality analysis of the Product Innovation Ego Networks.

c)

b)

a)

I

c)

a)

b)

II

c)

a)

b)

III

Figure 7.36: Degree, In-Degree and Out-Degree Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 7.36 shows that for all the three Innovation Outcomes analysed in this section, are all right skewed, like was observed for Process Innovations. This means that most of the nodes of these Ego Networks present few connections (being them incoming or outgoing). It is observed that there are some outliers (nodes which present high values across the different centrality metrics) and that in some cases – like in Figure 7.36 III c) – these outliers are heavy. These can be team leaders, project managers, planning activities, financial and project management related tasks, which are entities that traditionally need information or exercise coordination over a high number of other entities and/or activities.

Detailed analysis based on the different node types (Activities, Innovation Outcomes and Stakeholders) produced Degree Centrality results illustrated in Figure 7.37.

c)

b)

a)

I

c)

a)

b)

II

a)

c)

b)

III

Figure 7.37: Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Figure 7.37 I shows that the maximum value of Degree Centrality for Activity nodes is 25, while for Stakeholder nodes is 100. This and the fact that the Degree Centrality distribution for Stakeholder nodes has a high average value means that Stakeholder nodes present higher connectivity in this social network. Innovation Outcome nodes present high value of Degree Centrality in general. Figure 7.37 II shows that the maximum value of Degree Centrality for Activity nodes is 50, while for Stakeholder nodes is lower. Meanwhile, most Innovation Outcome nodes present a low value of Degree Centrality.

Figure 7.37 III shows the maximum value of Degree Centrality for Stakeholder nodes is above 130, while for Activity is 50 and for Innovation Outcome nodes is above 40.

Table 7.25 summarises the values presented in Figure 7.37 across the different node types.

Table 7.25: Degree Centrality relevant values of the Product Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 101 | 25 | 33 | 101 |
|  | Mean | ~15 | ~10 | ~23 | ~43 |
|  | Mode | 13 | 13 | 29 | 53 |
|  | Minimum | 2 | 3 | 2 | 2 |
| Meets Health and Safety Requirements | Maximum | 50 | 50 | 12 | 22 |
|  | Mean | ~10 | ~17 | ~7 | ~6 |
|  | Mode | 3 | 14 | 6 | 4 |
|  | Minimum | 1 | 2 | 3 | 1 |
| Achieved Industrial Standards | Maximum | 133 | 50 | 54 | 133 |
|  | Mean | ~17 | ~13 | ~20 | ~27 |
|  | Mode | 10 | 10 | 8 | 2 |
|  | Minimum | 1 | 5 | 2 | 1 |

Figure 7.38 was built to present the impact of Degree Centrality in the studied social ego networks: larger nodes indicate a higher Degree Centrality.

b)

a)

c)

Figure 7.38: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 7.39 shows the results for In-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

a)

b)

I

c)

a)

b)

a)

c)

b)

II

III

Figure 7.39: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node types

Figures 7.39 I (c) and 7.39 II (c) show that Stakeholder nodes do not possess any incoming links, meaning that the values presented in Figure 7.37 for this type of node refers only to Out-Degree Centrality. This is in accordance with what was observed for Process Innovation Outcomes’ In-Degree Centrality. Table 7.26 summarises the values presented in Figure 7.39 across the different node types.

Table 7.26: In-Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 101 | 25 | 33 | 101 |
|  | Mean | ~15 | ~10 | ~23 | ~43 |
|  | Mode | 13 | 13 | 29 | 53 |
|  | Minimum | 2 | 3 | 2 | 2 |
| Meets Health and Safety Requirements | Maximum | 50 | 50 | 12 | 22 |
|  | Mean | ~10 | ~17 | ~7 | ~6 |
|  | Mode | 3 | 14 | 6 | 4 |
|  | Minimum | 1 | 2 | 3 | 1 |
| Achieved Industrial Standards | Maximum | 133 | 50 | 54 | 133 |
|  | Mean | ~17 | ~13 | ~20 | ~27 |
|  | Mode | 10 | 10 | 8 | 2 |
|  | Minimum | 1 | 5 | 2 | 1 |

Figure 7.40 was built to present the impact of In-Degree Centrality in the studied social ego networks: larger nodes indicate a higher In-Degree Centrality.

a)

b)

c)

Figure 7.40: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 7.41 shows the results for Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

I

c)

b)

a)

II

b)

a)

c)

III

Figure 7.41: Out-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Figure 7.41 shows that, across all the Innovation Outcomes analysed, every Innovation Outcome node presented an Out-Degree of zero. Table 7.27 summarises the values presented in Figure 7.41 across the different node types.

Table 7.27: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 101 | 25 | 33 | 0 |
|  | Mean | ~8 | ~8 | ~23 | 0 |
|  | Mode | 0 | 8 | 29 | 0 |
|  | Minimum | 0 | 2 | 2 | 0 |
| Meets Health and Safety Requirements | Maximum | 22 | 15 | 0 | 22 |
|  | Mean | ~5 | ~3 | 0 | ~4 |
|  | Mode | 4 | 4 | 0 | 4 |
|  | Minimum | 0 | 0 | 0 | 1 |
| Achieved Industrial Standards | Maximum | 133 | 33 | 0 | 133 |
|  | Mean | ~9 | ~3 | 0 | ~28 |
|  | Mode | 1 | 1 | 0 | 2 |
|  | Minimum | 0 | 0 | 0 | 1 |

Figure 7.42 was built to present the impact of Out-Degree Centrality in the studied social ego networks: larger nodes indicate a higher Out-Degree Centrality.

b)

a)

c)

Figure 7.42: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

To summarise the conclusions related to the analysis of the Process Innovation Outcomes, Figure 7.43 presents the Degree, In-Degree and Out-Degree metrics in the same plots.

a)

b)

c)

Figure 7.43: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c))

Figure 7.43 shows that Stakeholder nodes have only outgoing connections and that they are responsible for the higher values of Degree Centrality, which indicates they possess access to a lot of nodes belonging to activities and innovation outcomes. It is also possible to conclude that there are some Activity nodes with high values of In-Degree and a significant value of Out-Degree Centrality. This happens across all the Innovation Outcomes.

Focusing on the results for Activity nodes, it is possible to conclude that they tend to present a low value of In-Degree Centrality in Figure 7.43 (a) and 7.43 (c). However, Figure 7.43 (b) shows that some Activity nodes present a high value for this metric.

Innovation Outcome nodes present typically low values for all Degree Centrality metrics, although it is possible to see that Figure 7.43 (c) presents some heavy outliers with high In-Degree centrality. Table 7.28 shows the five nodes with higher Degree, In-Degree and Out-Degree centrality for the three Process Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”).

Table 7.28: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Network

|  | Centrality Metric | Node Description | Type |
| --- | --- | --- | --- |
| Reduced Production Cost | Degree | Engineering Manager | Stakeholder |
|  |  | Sr. Process Engineer | Stakeholder |
|  |  | Senior Engineer, Piping | Stakeholder |
|  |  | Project Manager | Stakeholder |
|  |  | Cost Control Manager/Procurement Engineer | Stakeholder |
|  | In-Degree | Reduced Production Cost | Innovation Outcome |
|  |  | Achieved industrial standards | Innovation Outcome |
|  |  | Reduced operational cost | Innovation Outcome |
|  |  | Issue As IFC | Activity |
|  |  | Issue as IFC | Activity |
|  | Out-Degree | Engineering Manager | Stakeholder |
|  |  | Sr. Process Engineer | Stakeholder |
|  |  | Senior Engineer, Piping | Stakeholder |
|  |  | Project Manager | Stakeholder |
|  |  | Cost Control Manager/Procurement Engineer | Stakeholder |
| Meets Health and Safety Requirements | Degree | IPF (SIL Review) | Activity |
|  |  | 60% Model Review | Activity |
|  |  | 90% Model Review | Activity |
|  |  | 30% Model Review | Activity |
|  |  | HAZOP | Activity |
|  | In-Degree | IPF (SIL Review) | Activity |
|  |  | 60% Model Review | Activity |
|  |  | 90% Model Review | Activity |
|  |  | 30% Model Review | Activity |
|  |  | HAZOP | Activity |
|  | Out-Degree | Project Manager | Stakeholder |
|  |  | Engineering Manager | Stakeholder |
|  |  | QA/QC Manager | Stakeholder |
|  |  | Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | Senior Project Manager/Project Manager | Activity |
| Achieved Industrial Standards | Degree | Engineering Manager | Stakeholder |
|  |  | Project Manager | Stakeholder |
|  |  | QA/QC Manager | Stakeholder |
|  |  | Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | Sr. Process Engineer | Stakeholder |
|  | In-Degree | Achieved industrial standards | Innovation Outcome |
|  |  | IPF (SIL Review) | Activity |
|  |  | Issue as IFC | Activity |
|  |  | 60% Model Review | Activity |
|  |  | Reduced Production Cost | Innovation Outcome |
|  | Out-Degree | Engineering Manager | Stakeholder |
|  |  | Project Manager | Stakeholder |
|  |  | QA/QC Manager | Stakeholder |
|  |  | Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | Sr. Process Engineer | Stakeholder |

### Betweenness Centrality

Figure 7.44 presents the results for the Betweenness Centrality analysis of the Product Innovation Ego Networks.

c)

b)

a)

Figure 7.44: Betweenness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 7.44 results are in line with what was previously noted for Process Innovation Outcomes: right skewed distribution, which means that most of the nodes have a low level of betweenness centrality, while a few of them present a high value. Detailed analysis of Betweenness Centrality based on the different node types (Activities, Innovation Outcomes and Stakeholders) is presented in Figure 7.44.

b)

a)

c)

I

c)

a)

b)

II

c)

a)

b)

III

Figure 7.45: Betweenness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Figure 7.45 shows that, independent of the Innovation Outcome studied, Innovation Outcome nodes and Stakeholder nodes present zero betweenness centrality, which comes in line with what was noted and explained in previous sections. Table 7.29 summarises the values presented in Figure 7.45 across the different node types.

Table 7.29: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | ~50 | ~50 | 0 | 0 |
|  | Mean | ~4 | ~4 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Meets Health and Safety Requirements | Maximum | ~194 | ~194 | 0 | 0 |
|  | Mean | ~9 | ~27 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Achieved Industrial Standards | Maximum | ~146 | ~146 | 0 | 0 |
|  | Mean | ~9 | ~12 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 7.46 was built to present the impact of Betweenness Centrality in the studied social ego networks: larger nodes indicate a higher Betweenness Centrality.

b)

a)

c)

Figure 7.46: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Following the colour code created earlier, it was observed that with this distribution, Activity nodes gain relevance in the network. This is consistent with what was observed before. Table 7.30 shows the five nodes with higher Betweenness centrality for the three Product Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”). To allow a more precise identification of the nodes, the WBS name and the project activity description was added.

Table 7.30: Five Nodes with Higher Betweenness Centrality for each Product Innovation Outcome

| Betweenness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Production Cost | A19410 | Activity | Pipeline Design Basis | Issue as IFC |
|  | A14930 | Activity | Mechanical Design Basis -Static Equipment | Issue as IFC |
|  | A12990 | Activity | Utility Design Basis and Sizing Report (*) | Issue as IFC |
|  | A12980 | Activity | Utility Design Basis and Sizing Report (*) | Receive Company Approval |
|  | ISSUE AS IFC | Activity | Specification for Pressure Vessels | Issue as IFC |
| Meets Health and Safety Requirements | EP1110 | Activity |  | IPF (SIL Review) |
|  | EP1100 | Activity |  | 60% Model Review |
|  | EP1120 | Activity |  | 90% Model Review |
|  | A.01 | Activity |  | Complete HAZOP / SIL Reviews for all facilities and submit Reports - ICR |
|  | G1050 | Activity |  | 30% Model Review |
| Achieved Industrial Standards | EP1110 | Activity |  | IPF (SIL Review) |
|  | A19410 | Activity | Pipeline Design Basis | Issue as IFC |
|  | A14930 | Activity | Mechanical Design Basis -Static Equipment | Issue as IFC |
|  | A19400 | Activity | Pipeline Design Basis | Receive Company Approval |
|  | A14920 | Activity | Mechanical Design Basis -Static Equipment | Receive Company Approval |

### Closeness Centrality

Figure 7.47 presents the results for the Closeness Centrality analysis of the Process Innovation Ego Networks.

a)

b)

c)

Figure 7.47: Closeness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Improved Procurement Activities” (b) and “Achieved Industrial Standards” (c)

Figure 7.47 shows that there is a significant number of nodes with zero closeness, meaning that they do not have a central position in this ego network. Further it is observed that when one excludes those nodes, the closeness is relatively high and that some nodes seem to be close to their neighbours. This observation applies across all the Product Innovation Outcomes analysed.

A detailed analysis based on different node types (Activities, Innovation Outcomes and Stakeholders) is illustrated on Figure 7.48.

a)

c)

b)

I

c)

b)

a)

b)

c)

II

a)

III

Figure 7.48: Closeness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Figures 7.48 I b), 7.48 II b) and 7.48 III b) show that Innovation Outcome have zero closeness centrality, like was observed for Process Innovation. It is also observed that some Activity nodes are very peripheral in the network and that some of them tend to play a central role in it as observed in Figures 7.48 I a), 7.48 II a) and 7.48 III a).

Figures 7.48 a), 7.48 b) and 7.48 c) show that Stakeholder nodes have a Closeness Centrality that is higher than zero, which means that they can reach other nodes directly in an easier way. Table 7.31 summarises the values presented in Figure 7.48 across the different node types.

Table 7.31: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 1 | 1 | 0 | ~0,96 |
|  | Mean | ~0,55 | ~0,53 | 0 | ~0,80 |
|  | Mode | 0 | 1 | 0 | ~0,93 |
|  | Minimum | 0 | 0 | 0 | ~0,51 |
| Meets Health and Safety Requirements | Maximum | 1 | 1 | 0 | ~0,85 |
|  | Mean | ~0,53 | ~0,58 | 0 | ~0,55 |
|  | Mode | ~0,55 | 1 | 0 | 0,4 |
|  | Minimum | 0 | 0 | 0 | 0,4 |
| Achieved Industrial Standards | Maximum | 1 | 1 | 0 | ~0,96 |
|  | Mean | ~0,63 | ~0,66 | 0 | ~0,64 |
|  | Mode | 0 | 1 | 0 | ~0,53 |
|  | Minimum | 0 | 0 | 0 | ~0,47 |

Figure 7.49 was built to present the impact of Closeness Centrality in the studied social ego networks: larger nodes indicate a higher Closeness Centrality.

b)

a)

c)

Figure 7.49: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Following the colour code created earlier and by observing the results presented in Figure 7.49 a), 7.49 b) and 7.49 c), it is noted that with this distribution, Activity and Stakeholder nodes gain relevance in the network. This is in consistent with what was observed for Process Innovation Outcomes on section 7.3.4.

Table 7.32 shows the five nodes with higher Closeness centrality for the three Product Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”). To allow a more precise identification to the nodes, the WBS name and the project activity description were added.

Table 7.32: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks

| Closeness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Production Cost | A11170 | Activity | Process Data Sheet for Sales Gas Compressor After Cooler (834-K-101 / 201 / 301) | Issue as IFC |
|  | A11380 | Activity | Process Simulation & Equipment Sizing Report | Issue as IFC |
|  | A12990 | Activity | Utility Design Basis and Sizing Report (*) | Issue as IFC |
|  | A16260 | Activity | EOT crane motor Data Sheets | Issue as IFC |
|  | A16330 | Activity | EOT crane Data Sheets | Issue as IFC |
| Meets Health and Safety Requirements | A.01 | Activity |  | Complete HAZOP / SIL Reviews for all facilities and submit Reports - ICR |
|  | EP1120 | Activity |  | 90% Model Review |
|  | A.02 | Activity |  | Complete HSEIA Study Report and submit |
|  | A28720 | Activity | Fire Water System - Design Basis | Issue as IFC |
|  | A28790 | Activity | Deluge System - Design Basis | Issue as IFC |
| Achieved Industrial Standards | EP1100 | Activity |  | 60% Model Review |
|  | A.01 | Activity |  | Complete HAZOP / SIL Reviews for all facilities and submit Reports - ICR |
|  | A16330 | Activity | EOT crane Data Sheets | Issue as IFC |
|  | A16610 | Activity | Instrument air package Data Sheets (air dry compressor) | Issue as IFC |
|  | A16680 | Activity | Instrument air package Data Sheets (dryer) | Issue as IFC |

### Comparison of Centrality Metrics

The previous subsections focused on individual analysis of each of the social network centrality measures: Degree Centrality, Betweenness Centrality and Closeness Centrality. These analyses were performed together for the three Process Innovation Outcomes. Figure 7.50 presents an ensemble of these measures’ results.

a)

b)

c)

Figure 7.50: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figures 7.50 (a), (b) and (c) show that across all Innovation Outcomes, there are nodes which possess zero Closeness and zero Betweenness Centrality. Apart from these, Activity and Stakeholder nodes tend to present high Closeness Centrality. Also, in this latest group, a significant number of nodes present Betweenness Centrality above zero, with some cases presenting a high value of this metric. In fact, there is an important group of outliers, all being Activity nodes, which present high values of Betweenness, Closeness and Degree centrality. These can be found in the top left of the plots of Figure 7.50 (a), (b) and (c). These results are in line with the ones observed in section 7.3.5, for Process Innovation Outcomes.

Considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network, the most influential Stakeholder nodes of Innovation Outcome namely “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards” are the ones present in Table 7.33.

Table 7.33: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards” Ego Networks

| Stakeholder Nodes |  |  |  |
| --- | --- | --- | --- |
| Innovation Outcome | Description | Degree | Closeness |
| Reduced Production Cost | Engineering Manager | 101 | 0.963303 |
|  | Sr. Process Engineer | 89 | 0.932039 |
|  | Senior Engineer, Piping | 59 | 0.927536 |
|  | Project Manager | 53 | 0.934426 |
|  | Cost Control Manager/Procurement Engineer | 53 | 0.934426 |
|  | QA/QC Manager | 53 | 0.934426 |
| Meets Health and Safety Requirements | Civil Engineer | 10 | 0.857143 |
|  | Subcontractor-F&G | 10 | 0.857143 |
|  | Project Manager | 22 | 0.783784 |
|  | Engineering Manager | 19 | 0.750000 |
|  | QA/QC Manager | 20 | 0.743590 |
| Achieved Industrial Standards | Engineering Manager | 133 | 0.952381 |
|  | Project Manager | 87 | 0.939394 |
|  | QA/QC Manager | 86 | 0.930000 |
|  | Cost Control Manager/Procurement Engineer | 83 | 0.885714 |
|  | Sr. Process Engineer | 79 | 0.882353 |

In terms of Activities influence on Innovation Outcomes “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”,

Table 7.34: High Betweenness, high Closeness and high Degree

| Activity Nodes |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | WBS Name | Description | Degree | Closeness |
| Reduced Production Cost | Pipeline Design Basis | Issue as IFC | 21 | 0.923077 |
|  | Mechanical Design Basis -Static Equipment | Issue as IFC | 20 | 1 |
|  | Utility Design Basis and Sizing Report (*) | Issue as IFC | 16 | 1 |
|  | Utility Design Basis and Sizing Report (*) | Receive Company Approval | 10 | 0.526316 |
|  | Specification for Pressure Vessels | Issue as IFC | 17 | 1 |
| Meets Health and Safety Requirements |  | IPF (SIL Review) | 50 | 0.600000 |
|  |  | 60% Model Review | 38 | 0.833333 |
|  |  | 90% Model Review | 37 | 1 |
|  |  | Complete HAZOP / SIL Reviews for all facilities and submit Reports - ICR | 12 | 1 |
|  |  | 30% Model Review | 33 | 0.666667 |
| Achieved Industrial Standards |  | IPF (SIL Review) | 50 | 0.750000 |
|  | Pipeline Design Basis | Issue as IFC | 21 | 0.923077 |
|  | Mechanical Design Basis -Static Equipment | Issue as IFC | 20 | 1.000000 |
|  | Pipeline Design Basis | Receive Company Approval | 16 | 0.500000 |
|  | Mechanical Design Basis -Static Equipment | Receive Company Approval | 14 | 0.521739 |

## Summary

In this chapter, an analysis of the social network of Activities, Stakeholders and Innovation Outcomes of the Engineering Phase of the EPC project was performed. It was observed that Activity nodes tend to present a high Betweenness Centrality and that Stakeholder nodes tend to present a high Closeness Centrality. After an initial overview of the Engineering Phase, this chapter presented the detailed analysis for the Innovation Outcomes. This analysis was divided in two: Process Innovation Outcomes and Product Innovation Outcomes. The first consists of the following EPC Project tasks: Reduced Project Implementation Time, Improved Procurement Activities and Reduced Operational Cost. The second consists of the following EPC Project tasks: Reduced Production Cost, Meets Health and Safety Requirements and Achieved Industrial Standards. It was observed that the following stakeholders present a high influence on Innovation Outcomes: Engineering Manager, Sr. Process Engineer and Project Manager.

The next chapter presents findings on the Procurement phase of the EPC project.

# Results – Procurement

## Introduction

This chapter discusses the results of the analysis of the social network built with the data collected on the EPC project for the Procurement Phase. The analysis is focused on centrality metrics, namely, Degree centrality, Closeness centrality and Betweenness centrality. The scope of the analysis starts with an overview of the Procurement Phase social network and then moves to a detailed analysis of Innovation Outcome nodes’ Ego Networks grouped into Process Innovation and Product Innovation. These Ego Networks have a depth of two, meaning that they are composed by the Innovation Outcome node itself, its neighbours and its neighbours’ neighbours. For each Ego Network, centrality metrics are computed with the help of Gephi software, in order to find Stakeholders and Activities that influence the corresponding Innovation Outcome.

## Procurement Phase Overview

Focusing on the second of the three phases of the EPC project, Figure 8.1 presents the social network composed by the nodes and relationships of the Procurement Phase. The image was produced with the Gephi software, using the Force Atlas layout algorithm with a repulsion strength of 100, among other visualisation parameters.

Figure 8.1:  Procurement Phase Social Network

Just as it was observed in Figure 8.1 in the previous chapter, Figure 8.1 shows that there are nodes which present a central position in the network, while other nodes are very peripheral. This will be further assessed since it will allow the study of their importance in the network.

As observed earlier, this network is directed, meaning that there is a direction associated with a relationship between nodes. Table 8.1 presents a summary of the Procurement Phase social network’s main general characteristics, which allows one to conclude that this phase involves less entities than the previous Engineering Phase.

Table 8.1: General Characteristics of the Procurement Phase Social Network

| Characteristic | Value |
| --- | --- |
| Total of Nodes | 1068 |
| Total of Edges | 7127 |

Focusing on the types of nodes that exist in the social network under analysis, Figure 8.2 presents a pie chart with their distribution.

Figure 8.2: Distribution of Node Types in the Procurement Phase Social Network

Most of the Procurement Phase social network is composed of activities, which represent 82% of the total number of nodes. The second largest group is the Stakeholder nodes’ group, which represent 17% of the whole network, and the smallest group belongs to the Innovation Outcome nodes, which represent 0,9% of the total number of nodes. These numbers are in line with those observed in the previous chapter, for the Engineering Phase, although it is possible to notice that the weight of the Activity nodes is slightly lower. In summary, the Procurement Phase Social Network has 876 Activity nodes, 182 Stakeholder nodes and 10 Innovation Outcomes nodes.

### Procurement Phase Social Network Metrics

Table 8.2 presents relevant metrics for the Procurement Phase Social Network. These metrics are related to Social Network analysis and are the following: network diameter, graph density, average path length, average clustering coefficient and average degree.

Table 8.2: Social Network Metrics of the Procurement Phase Social Network

| Social Network Metrics | Value |
| --- | --- |
| Network Diameter | 8 |
| Graph Density | 0,006 |
| Average Path Length | 2,301 |
| Average Clustering Coefficient | 0,097 |
| Average Degree | 6,673 |

Table 8.2 shows that the network diameter for this network is eight, which is much lower than the 28 reported in section 7.2.1. That means of all the possible node pairs, that one has the shortest path that passes through eight nodes. This metric demonstrates that this network is significantly smaller than that of the Engineering Phase. In terms of the interpretation related to the specific problem here studied, this number means that there is a set of activities/processes, stakeholders and possibly innovation outcomes that are composed of eight “steps”. This number is in accordance with the magnitude of this EPC project and specifically to its Procurement Phase, since it presents less tasks than that of Engineering.

Table 8.2 shows that the graph density is relatively small, presenting a value of 0,006, which means that of all the connections that may exist in this network a small fraction of them is present. In terms of the average path length, the value 2,301 indicates that there are, on average, a little more than two nodes along the shortest paths for all pairs of nodes in this network. Besides this, Table 8.2 indicates that the average clustering coefficient is of 0,097 which is slightly higher than that presented in section 7.2.1. However, the value is also small. Lastly, the average degree of the network is 6.673 meaning that on average, a node of this network is connected to almost seven other nodes.

### Degree Centrality

Figure 8.3 presents the results of the analysis of the Degree, In-Degree and Out-Degree Distribution for the Procurement Phase social network.

c)

b)

a)

Figure 8.3: Degree a), In-Degree b) and Out-Degree c) Centrality in the Procurement Phase Social Network

All the Degree distributions presented above in Figure 8.3 are skewed to the right, which means that most of the nodes in the Procurement Phase Social Network present low connectivity.

Due to the existence of outliers in Figure 8.3 a) and 8.3 b), the visualisation was improved with the exclusion of nodes with a Degree and Out-Degree higher than 100.

b)

a)

Figure 8.4: Degree a) and Out-Degree b) Centrality in the Procurement Phase Social Network for nodes with less than 100 value

To extract further details of the analysis according to the different node types, Figure 8.5 presents the results for Degree, In-Degree and Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

a)

b)

I

a)

b)

c)

b)

II

a)

c)

III

Figure 8.5: Degree (I), In-Degree (II) and Out-Degree Centrality (III) in the Procurement Phase Social Network according to node type

Stakeholder nodes present a zero In-Degree value, while Innovation Outcome present the same value but for Out-Degree centrality. This is in accordance with the findings of the previous chapter. Figure 8.5 I shows that Activity nodes tend to have a lower Degree Centrality than Stakeholder nodes, while Innovation Outcomes present even lower values. This is in according with the characteristics of an EPC Project, in which Stakeholders present a heavy connection to a lot of activities. Table 8.3 summarises the values presented in Figure 8.5 across the different node types and Centrality metrics analysed.

Table 8.3: Degree Centrality relevant values of the Procurement Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Centrality Metric | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| DEGREE | Maximum | 790 | 91 | 52 | 790 |
|  | Mean | ~14 | ~10 | ~9 | 33 |
|  | Mode | 8 | 8 | 0 | 0 |
|  | Minimum | 1 | 1 | 0 | 0 |
| IN-DEGREE | Maximum | 90 | 90 | 52 | 0 |
|  | Mean | ~7 | ~9 | ~8.2 | 0 |
|  | Mode | 0 | 6 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| OUT-DEGREE | Maximum | 790 | 12 | 0 | 790 |
|  | Mean | ~7 | ~2 | 0 | 33 |
|  | Mode | 1 | 1 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 8.6 shows the Procurement Phase Social Network affected Degree, In-Degree and Out-Degree: bigger nodes indicate a higher centrality result.

c)

b)

a)

Figure 8.6: Degree a), In-Degree b) and Out-Degree Centrality c) in the Procurement Phase Social Network

Figure 8.6 shows that there are some Stakeholder nodes that are of significant relevance to Degree (a) and Out-Degree (c) distributions. This is according to what was observed in the previous Figures. It can also be observed that Activity nodes and some Innovation Outcomes gain relevance in Figure 8.6 b), referring to In-Degree centrality. To summarise the conclusions related to the analysis of the Procurement Phase social network, Figure 8.7 presents the Degree, In-Degree and Out-Degree metrics in the same plot.

Figure 8.7: Procurement Phase Social Network summary of Degree Centrality values

Figure 8.7 presents what was previously observed: that most of the nodes present low degree value, which reflects on the size of the labels in the plot. Besides, there is an agglomeration of nodes in the inferior left corner, where there is low level of both in-degree and out-degree. Figure 8.7 also shows that Stakeholder nodes have an Out-Degree value which is higher than zero and do not present In-Degree values. Some of these nodes present a high value of Out-Degree. The opposite conclusion can be withdrawn for the Activity nodes.  Table 8.4 shows the 10 nodes with higher Degree, In-Degree and Out-Degree centrality in the Procurement Phase.

Table 8.4: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Procurement Phase Social Network

| Centrality Metric | Node Description | Type |
| --- | --- | --- |
| Degree | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  | SH60 – QA/QC Manager | Stakeholder |
|  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  | SH55 – Project Manager | Stakeholder |
|  | SH28 – Sr. QA/QC Engineer | Stakeholder |
|  | SH16 – Sr.QA/QC Engineer | Stakeholder |
|  | SH37 – Senior Engineer, Piping | Stakeholder |
|  | SH17 – Procurement Engineer | Stakeholder |
|  | SH18 – Sr. HSE Engineer | Stakeholder |
|  | SH7 – Project Co-ordinator | Stakeholder |
| In-Degree | A29260 – Issue PO | Activity |
|  | A29270 – Delivery on Site | Activity |
|  | A29250 – Issue PO | Activity |
|  | A29280 – Delivery on Site | Activity |
|  | J – Achieved industrial standards | Innovation Outcome |
|  | A6070 – Approved Vendor Documents | Activity |
|  | A6420 – Approved Vendor Documents | Activity |
|  | A6470 – Approved Vendor Documents | Activity |
|  | A1360 – Prepare and Issue MR | Activity |
|  | A1160 - Prepare and Issue MR | Activity |
| Out-Degree | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  | SH60 – QA/QC Manager | Stakeholder |
|  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  | SH55 – Project Manager | Stakeholder |
|  | SH28 – Sr. QA/QC Engineer | Stakeholder |
|  | SH16 – Sr.QA/QC Engineer | Stakeholder |
|  | SH37 – Senior Engineer, Piping | Stakeholder |
|  | SH17 – Procurement Engineer | Stakeholder |
|  | SH18 – Sr. HSE Engineer | Stakeholder |
|  | SH7 – Project Co-ordinator | Stakeholder |

Table 8.5 shows the 10 nodes with lower Degree, In-Degree and Out-Degree centrality in the Procurement Phase.

Table 8.5: Ten Nodes with Lower Degree, In-Degree and Out-Degree Centrality in the Procurement Phase Social Network

| Centrality Metric | Node Description | Type |
| --- | --- | --- |
| Degree | SH3 – Interface Co-ordinator | Stakeholder |
|  | SH5 – Sr. Construction Engineer | Stakeholder |
|  | SH19 – Senior Engineer (Operations Readiness) | Stakeholder |
|  | SH29 – Sr. Engineer, HSE | Stakeholder |
|  | SH30 – Cost Estimation Engineer | Stakeholder |
|  | SH49 – Pipeline Representative | Stakeholder |
|  | SH50 – Engineer, I-C | Stakeholder |
|  | SH51 – Engineer, Electrical | Stakeholder |
|  | SH52 – Pipeline Engineer | Stakeholder |
|  | SH53 – Commissioning Team Leader | Stakeholder |
| In-Degree | A2000 – Prepare and Issue MR | Activity |
|  | A5780 – Prepare and Issue MR | Activity |
|  | A5800 – Prepare and Issue MR | Activity |
|  | A5840 – Prepare and Issue MR | Activity |
|  | A5860 – Prepare and Issue MR | Activity |
|  | A5960 – Prepare and Issue MR | Activity |
|  | A5940 – Prepare and Issue MR | Activity |
|  | A5900 – Prepare and Issue MR | Activity |
|  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  | SH2 – Sr. Project Engineer | Stakeholder |
| Out-Degree | J – Achieved industrial standards | Innovation Outcome |
|  | A – Reduced Production Cost | Innovation Outcome |
|  | A29270 – Delivery on Site | Activity |
|  | B.08 – Submit G-SPIRs to company and Issue orders for the operating spares for all items after obtaining COMPANY approvals. | Activity |
|  | A5490 – Issue PO | Activity |
|  | A5510 – Issue PO | Activity |
|  | A5530 – Issue PO | Activity |
|  | A5550 – Issue PO | Activity |
|  | A5590 – Issue PO | Activity |
|  | A5570 – Issue PO | Activity |

### Betweenness Centrality

Figure 8.8 shows the results of the Betweenness Centrality distribution for the Procurement Phase social network.

Figure 8.8: Betweenness Centrality in the Procurement Phase Social Network.

Figure 8.8 shows that the distribution is skewed to the right, which means that most of the nodes have a low level of Betweenness Centrality. This indicates that a small number of nodes of this network might have a high influence in the graph.

Proceeding accordingly to the previous sections, Figure 8.9 presents the Betweenness Centrality results according to the types of nodes.

c)

b)

a)

Figure 8.9: Betweenness Centrality in the Procurement Phase Social Network according to node type

As it was noted before in section 7.2.3, both Innovation Outcome nodes and Stakeholder nodes have a zero betweenness centrality, which means that the most influential nodes on the Procurement Phase social network are the activity nodes. Table 8.6 presents relevant values of this distribution.

Table 8.6: Betweenness Centrality relevant values of the Procurement Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- |
| Maximum | 634 | 634 | 0 | 0 |
| Mean | ~22 | ~25 | 0 | 0 |
| Mode | 0 | 0 | 0 | 0 |
| Minimum | 0 | 0 | 0 | 0 |

Figure 8.10 shows the Procurement Phase Social Network affected by the Betweenness Centrality results: larger nodes indicate a higher Betweenness Centrality.

Figure 8.10: Procurement Phase Social Network affected by Betweenness Centrality

Observing Figure 8.10, it is noticed that Activity nodes gain relevance in the network. This happens because some activities can act as boundary spanners, creating bridges between activities and stakeholders which have a loose relationship between them.

Table 8.7 shows the 10 nodes with higher Betweenness Centrality in the Procurement Phase for the Activity nodes since the other types of nodes have a zero betweenness value.

Table 8.7: Ten Nodes with Higher Betweenness Centrality in the Procurement Phase Social Network

| Betweenness Centrality |  |  |  |
| --- | --- | --- | --- |
| Node | Type | WBS Task Name | Project Activity Description |
| A29280 | Activity | Miscellaneous (BM) | Delivery on Site |
| A29260 | Activity | Miscellaneous (BM) | Issue PO |
| A1880 | Activity | HIPS (High Integrity Pressure Protection System) | Prepare and Issue MR |
| A1890 | Activity | HIPS (High Integrity Pressure Protection System) | Issue PO |
| A29250 | Activity | Miscellaneous (E&P) | Issue PO |
| B.03 | Activity |  | Issue Purchase Orders for 33kV & 11kV Switchgears, HIPPS and Instrument Control Systems (ICS) Equipment (NOTE-3) |
| A6860 | Activity | 33kV GIS Switchgear | Received Vendor Documents |
| A1500 | Activity | HVAC Package | Prepare and Issue MR |
| A1340 | Activity | Discharged Cooler | Prepare and Issue MR |
| A1510 | Activity | HVAC Package | Issue PO |

Table 8.7 shows that the task “Issue PO” aggregates several WBS tasks, making an effective bridge in the Procurement Phase Social Network. Along with this task, the others presented above are all activities that exert a heavy influence in the network.

### Closeness Centrality

Figure 8.11 shows the results of the Closeness Centrality distribution for the Procurement Phase social network.

Figure 8.11: Closeness Centrality in the Procurement Phase Social Network

As before, most of the nodes have a low closeness, meaning that they are not central to the network, while a few of them tend to have a high closeness value.

The analysis of Closeness Centrality according to the types of nodes is presented in Figure 8.12.

c)

a)

b)

Figure 8.12: Closeness Centrality in the Procurement Phase Social Network according to node type

Figure 8.12 shows that Innovation Outcome nodes are generally distant from every other node in the network since they are close to zero. This means that Innovation Outcomes tend not to be central in the network, which happens because they are the outputs of the Innovation flow.

Table 8.8 summarises the relevant values presented across the different node types.

Table 8.8: Closeness Centrality relevant values of the Procurement Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- |
| Maximum | 1 | 1 | 0 | 1 |
| Mean | ~0,45 | ~0,50 | 0 | ~0,25 |
| Mode | 0 | 0,50 | 0 | 0 |
| Minimum | 0 | 0 | 0 | 0 |

Figure 8.13 presents the Procurement Phase Social Network affected by Closeness Centrality: larger nodes indicate a higher Closeness Centrality.

Figure 8.13: Procurement Phase Social Network affected by Closeness Centrality

Figure 8.13 shows that there are Activity nodes with high closeness, which happens because activities are close to each other in terms of a WBS logic and they are also close to Stakeholders. Table 8.9 shows the 10 nodes with higher Closeness Centrality in the Procurement Phase.

Table 8.9: Ten Nodes with Higher Closeness Centrality in the Procurement Phase

| Closeness Centrality |  |  |  |
| --- | --- | --- | --- |
| Node | Type | WBS Task Name | Project Activity Description |
| A29250 | Activity | Miscellaneous (E&P) | Issue PO |
| A9480 | Activity | Pipes (CS) (NPS < 10") | Ex-Work Delivery (FOB) |
| A9500 | Activity | Pipes (SS) | Ex-Work Delivery (FOB) |
| A9560 | Activity | Fittings (SS) | Ex-Work Delivery (FOB) |
| A9600 | Activity | Flange (CS) (NPS < 10") | Ex-Work Delivery (FOB) |
| A9680 | Activity | GRE Pipes & Fittings | Ex-Work Delivery (FOB) |
| A9740 | Activity | GRV pipes & fittings | Ex-Work Delivery (FOB) |
| A9760 | Activity | Ball valve (NPS > 10") | Ex-Work Delivery (FOB) |
| A9780 | Activity | Ball valve (NPS < 10") | Ex-Work Delivery (FOB) |
| A10280 | Activity | GRE Flanges | Ex-Work Delivery (FOB) |

Table 8.9 shows that the task “Ex-Work Delivery (FOB)” is close to several WBS tasks, which makes it a hub in the network in terms of access to information of the other activities.

### Comparison of Centrality Metrics

Figure 8.14 presents an ensemble of the social network metrics analysed separately before: Degree Centrality, Betweenness Centrality and Closeness Centrality.

Figure 8.14: Procurement Phase Social Network summary of Centrality metrics

Observing Figure 8.14, it is apparent that there are a significant number of nodes with zero Closeness, zero Betweenness and a low Degree value. Apart from those, the general values of Closeness Centrality are around 0,50. Figure 8.14 also shows that most of the nodes present a Betweenness Centrality of zero. These nodes tend to be Stakeholder nodes. Besides, there are some Activity nodes with a high value of Betweenness, Closeness and Degree Centrality. These nodes tend to be the most influential in the Procurement Phase of the EPC Project.

## Study of Process Innovation Outcomes

### Process Innovation Outcomes’ Ego Networks.

Table 8.10 presents the general characteristics of the Innovation Outcomes’ Ego Networks analysed in this subsection.

Table 8.10: Process Innovation Outcomes’ Information for the Procurement Phase of the EPC Project

| Innovation Outcome | Label | Description | Total of Nodes | Total of Edges |
| --- | --- | --- | --- | --- |
| 3501 | B | Reduced Project Implementation Time | 41 | 157 |
| 3506 | G | Improved Procurement Activities | 38 | 152 |
| 3508 | I | Reduced Operational Cost | 19 | 21 |

Table 8.10 shows that the Innovation Outcomes’ Ego Networks are significantly smaller in the Procurement Phase when compared to the same networks in the Engineering Phase.

The “Reduced Operational Cost”’ Ego Network is the smallest of all the three presented, followed by the “Improved Procurement Activities”’ Ego Network and by the “Reduced Project Implementation Time”, in terms of size. To further assess the characteristics of these Ego Networks, the plot in Figure 8.15 presents their distribution according to node types.

Figure 8.15: Distribution of Node Types for Process Innovation Outcomes’ Ego Networks

The plot in Figure 8.15 shows that there is a prevalence of Activity nodes in the three Ego Networks. Figure 8.16 presents the Process Innovation Outcomes’ Ego Networks created with Gephi software. The Fruchterman Reingold layout algorithm was used to improve visualisation.

a)

b)

c)

Figure 8.16: Ego Networks of Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

### Degree Centrality

Figure 8.17 presents the results for the Degree, In-Degree and Out-Degree Centrality analysis of the Process Innovation Ego Networks.

c)

b)

a)

I

c)

b)

a)

II

c)

b)

a)

III

Figure 8.17: Degree (I), In-Degree (II) and Out-Degree Centrality (III) of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figure 8.17 shows that all the Degree Centrality values, across all node types, tend to have a right skewed distribution. The exception can be seen in Figure 8.17 II b), for the In-Degree Centrality of Innovation Outcome “Improved Procurement Activities”.

This observation means most of the nodes of these Ego Networks present few connections. This implies that the nodes in these Networks are not that connected so that it can be difficult for information to flow between them. Despite the observation made, Figure 8.17 shows that there are always nodes which present high values of each of the Degree centrality metrics analysed. The results of a more detailed analysis of Degree Centrality based on different node types (Activities, Innovation Outcomes and Stakeholders) are presented in Figure 8.18.

c)

b)

a)

b)

a)

I

c)

II

c)

b)

a)

III

Figure 8.18: Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 8.18 shows that Activity and Stakeholder nodes have higher Degree Centrality values when compared to Innovation Outcome nodes. Observing Figures 8.18 I and 8.18 II it is noted that the maximum value of Degree Centrality for Stakeholder nodes is 25, while for Activity nodes it is slightly lower. This indicates that Stakeholder nodes of the first two Innovation Outcomes have higher connectivity than Activity nodes.

Figure 8.18 III shows that both Innovation Outcome and Stakeholder nodes present a low value of Degree Centrality. In that regard, Activity nodes tend to have higher connectivity in the “Reduced Operational Cost”. Table 8.11 summarises the values presented in Figure 8.19 across the different node types.

Table 8.11: Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 25 | 19 | 8 | 25 |
|  | Mean | ~8 | ~7 | ~6 | ~13 |
|  | Mode | 4 | 4 | 1 | 3 |
|  | Minimum | 1 | 1 | 1 | 3 |
| Improved Procurement Activities | Maximum | 24 | 19 | 7 | 24 |
|  | Mean | 8 | ~7 | ~7 | 13 |
|  | Mode | 4 | 4 | 7 | 3 |
|  | Minimum | 2 | 2 | 6 | 3 |
| Reduced Operational Cost | Maximum | 14 | 14 | 2 | 2 |
|  | Mean | ~3 | ~6 | ~2 | ~2 |
|  | Mode | 1 | 1 | 2 | 1 |
|  | Minimum | 1 | 1 | 1 | 1 |

Figure 8.19 was built to present the impact of Degree Centrality in the studied social ego networks: larger nodes indicate a higher Degree Centrality.

b)

a)

c)

Figure 8.19: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” a), “Improved Procurement Activities” b) and “Reduced Operational Cost” c)

The Ego Networks a) and b) present Activity and Stakeholder nodes with higher relevance, which is in accordance with the analysis presented earlier. Also, in Figure 8.19 Ego Network c), it is observed that Activity nodes present higher connectivity.

Figure 8.20 presents the results for In-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders), for each Ego Network.

c)

b)

a)

b)

I

c)

a)

c)

b)

a)

II

III

Figure 8.20: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 8.20 shows that, across all the Innovation Outcomes analysed, every Stakeholder node presented an In-Degree of zero. This means that there are no Stakeholder nodes with incoming links, which was previously observed in the Engineering Phase analysis presented in the previous chapter.

Table 8.12 summarises the values presented in Figure 8.20 across the different node types.

Table 8.12: In-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 9 | 9 | 8 | 0 |
|  | Mean | ~4 | ~5 | ~6 | 0 |
|  | Mode | 4 | 4 | 1 | 0 |
|  | Minimum | 0 | 0 | 1 | 0 |
| Improved Procurement Activities | Maximum | 9 | 9 | 7 | 0 |
|  | Mean | 4 | ~5 | ~7 | 0 |
|  | Mode | 4 | 4 | 7 | 0 |
|  | Minimum | 0 | 0 | 6 | 0 |
| Reduced Operational Cost | Maximum | 10 | 10 | 2 | 0 |
|  | Mean | ~1 | 4 | ~2 | 0 |
|  | Mode | 0 | 1 | 2 | 0 |
|  | Minimum | 0 | 1 | 1 | 0 |

Figure 8.21 was built to present the impact of In-Degree Centrality in the studied social ego networks: larger nodes indicate a higher In-Degree Centrality.

b)

a)

c)

Figure 8.21: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figure 8.22 shows the results for Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

a)

b)

c)

I

c)

a)

b)

II

c)

b)

a)

III

Figure 8.22: Out-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 8.22 shows that, across all the Innovation Outcomes analysed, every Innovation Outcome node presented an Out-Degree of zero, which is in accordance with what was previously observed. From Figure 8.22 I and 8.22 II, it is noted that the outliers of Stakeholder nodes present a higher Out-Degree than Activity nodes, which means that those Stakeholder nodes have higher connectivity. This connectivity means they have access to more nodes. In the case of Innovation Outcome “Reduced Operational Cost”, the opposite holds, with Activity outlier nodes presenting higher Out-Degree value than Stakeholder ones. Table 8.13 summarises the values presented in Figure 8.22 across the different node types.

Table 8.13: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 25 | 12 | 0 | 25 |
|  | Mean | ~4 | ~2.3 | 0 | ~13 |
|  | Mode | 0 | 0 | 0 | 3 |
|  | Minimum | 0 | 0 | 0 | 3 |
| Improved Procurement Activities | Maximum | 24 | 12 | 0 | 24 |
|  | Mean | 0 | ~3 | 0 | ~13 |
|  | Mode | 0 | 0 | 0 | 3 |
|  | Minimum | 0 | 0 | 0 | 3 |
| Reduced Operational Cost | Maximum | 4 | 4 | 0 | 2 |
|  | Mean | ~1 | ~2 | 0 | ~2 |
|  | Mode | 1 | 0 | 0 | 1 |
|  | Minimum | 0 | 0 | 0 | 1 |

Figure 8.23 was built to present the impact of Out-Degree Centrality in the studied social ego networks: larger nodes indicate a higher Out-Degree Centrality.

b)

a)

c)

Figure 8.23: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

To summarise the conclusions related to the analysis of the Process Innovation Outcomes, Figure 8.24 presents the Degree, In-Degree and Out-Degree metrics in the same plots.

b)

a)

c)

Figure 8.24: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c))

The plots in Figure 8.24 show that Innovation Outcomes only present incoming links, while Stakeholder nodes only have outgoing connections across all the studied Ego Networks. Besides, it is possible to notice that Degree Centrality is quite homogenous across all Innovation Outcomes’ results. Observing the plots, it be can noticed that there are some Stakeholder nodes that present a high value of Out-Degree and some Activity nodes are able to show high values for both In- and Out-Degree Centrality. Table 8.14 shows the five nodes with higher Degree, In-Degree and Out-Degree centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”).

Table 8.14: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Networks

|  | Centrality Metric | Node Description | Type |
| --- | --- | --- | --- |
| Reduced Project Implementation Time | Degree | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | SH17 – Procurement Engineer | Stakeholder |
|  |  | PM0005 – Weekly Procurement expediting meetings with CONTRACTOR and VENDORS | Activity |
|  |  | PM0006 – Daily Procurement Meetings with Vendors | Activity |
|  |  | PM0007 – Allocation of Expeditors at Vendor Manufacturing locations | Activity |
|  | In-Degree | C.01 – Receive Gas Compressor Packages (Tag # 834-K-101/K-201/K-301) at site | Activity |
|  |  | B – Reduced project implementation time | Innovation Outcome |
|  |  | C.02 – Receive Air Coolers, Metering Skid Package, K.O Drums and Air Compressor & Dryer Package at site | Activity |
|  |  | C.03 – Receive 33kV & 11kV Switchgears and 33kV/11kV Transformers Instrument Control System (ICS) and HIPS Equipment at site | Activity |
|  |  | G – Improved procurement activities | Innovation Outcome |
|  | Out-Degree | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | SH17 – Procurement Engineer | Stakeholder |
|  |  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  |  | PM0005 – Weekly Procurement expediting meetings with CONTRACTOR and VENDORS | Activity |
|  |  | PM0006 – Daily Procurement Meetings with Vendors | Activity |
| Improved Procurement Activities | Degree | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | SH17 – Procurement Engineer | Stakeholder |
|  |  | PM0005 – Weekly Procurement expediting meetings with CONTRACTOR and VENDORS | Activity |
|  |  | PM0006 – Daily Procurement Meetings with Vendors | Activity |
|  |  | PM0007 – Allocation of Expeditors at Vendor Manufacturing locations | Activity |
|  | In-Degree | C.01 – Receive Gas Compressor Packages (Tag # 834-K-101/K-201/K-301) at site | Activity |
|  |  | C.02 – Receive Air Coolers, Metering Skid Package, K.O Drums and Air Compressor & Dryer Package at site | Activity |
|  |  | C.03 – Receive 33kV & 11kV Switchgears and 33kV/11kV Transformers Instrument Control System (ICS) and HIPS Equipment at site | Activity |
|  |  | B – Reduced project implementation time | Innovation Outcome |
|  |  | G – Improved procurement activities | Innovation Outcome |
|  | Out-Degree | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | SH17 – Procurement Engineer | Stakeholder |
|  |  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  |  | PM0005 – Weekly Procurement expediting meetings with CONTRACTOR and VENDORS | Activity |
|  |  | PM0006 – Daily Procurement Meetings with Vendors | Activity |
| Reduced Operational Cost | Degree | A5980 – Prepare and Issue MR | Activity |
|  |  | A6020 – Prepare and Issue MR | Activity |
|  |  | J – Achieved industrial standards | Innovation Outcome |
|  |  | I – Reduced operational cost | Innovation Outcome |
|  |  | SH16 – Sr.QA/QC Engineer | Stakeholder |
|  | In-Degree | A5980 – Prepare and Issue MR | Activity |
|  |  | A6020 – Prepare and Issue MR | Activity |
|  |  | J – Achieved industrial standards | Innovation Outcome |
|  |  | I – Reduced operational cost | Innovation Outcome |
|  |  | D – Meets health and safety requirements | Innovation Outcome |
|  | Out-Degree | A5980 – Prepare and Issue MR | Activity |
|  |  | A6020 – Prepare and Issue MR | Activity |
|  |  | SH16 – Sr.QA/QC Engineer | Stakeholder |
|  |  | SH28 – Sr. QA/QC Engineer | Stakeholder |
|  |  | SH6 – Team Leader/Engineering Manager | Stakeholder |

### Betweenness Centrality

Figure 8.25 presents the results for the Betweenness Centrality analysis of the Process Innovation Ego Networks.

c)

a)

b)

Figure 8.25: Betweenness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figures 8.25 a) and 8.25 b) are similar because Ego Networks of the Innovation Outcomes “Reduced Project Implementation Time” and “Improved Procurement Activities” share many nodes. Figure 8.25 c) presents a similar distribution, but the differences here are more pronounced. All the three plots in Figure 8.25 present right skewed distributions, which means most of the nodes have a low level of Betweenness Centrality, while a few of them present a relatively high value (outliers). This comes in line with the results observed in the previous Chapter for the Engineering Phase Analysis.

Figure 8.26 presents a deeper analysis of Betweenness Centrality based on node types (Activities, Innovation Outcomes and Stakeholders).

c)

a)

b)

c)

b)

a)

I

b)

II

c)

a)

III

Figure 8.26: Betweenness Centrality for “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 8.26 presents that Betweenness Centrality for Innovation Outcome and Stakeholder nodes is always zero, across the three Ego Network studied. This was observed before for the Procurement Phase Social Network. The fact that this centrality measure is zero is because Innovation Outcome nodes do not make bridges with other nodes as a result of their being the last step to Innovation. On the other side, Stakeholder nodes are the ones which influence Activities and/or Innovation Outcomes, so they are the starting point, being unable to build bridges in the Network. Table 8.15 summarises the values presented in Figure 8.26 across the different node types.

Table 8.15: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 29 | 29 | 0 | 0 |
|  | Mean | ~4 | ~4 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Improved Procurement Activities | Maximum | 29 | 29 | 0 | 0 |
|  | Mean | ~4 | ~4 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Reduced Operational Cost | Maximum | 38 | 38 | 0 | 0 |
|  | Mean | 12 | 12 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 8.27 was built to present the impact of Betweenness Centrality in the studied social ego networks: larger nodes indicate a higher Betweenness Centrality.

a)

b)

c)

Figure 8.27: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

From Figure 8.27, it is observed that through the centrality metric, Activity nodes gain relevance in the network. This happens because some activities can act as boundary spanners, creating bridges between activities and stakeholders which have a loose relationship between them. Table 8.16 shows the five nodes with higher Betweenness centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”). To allow a more precise identification of the nodes, the WBS name and the project activity description were added to the table.

Table 8.16: Five Nodes with Higher Betweenness Centrality for each Process Innovation Outcome

| Betweenness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Project Implementation Time | PM0007 | Activity | Procurement Management | Allocation of Expeditors at Vendor Manufacturing locations |
|  | PM0005 | Activity | Procurement Management | Weekly Procurement expediting meetings with CONTRACTOR and VENDORS |
|  | PM0006 | Activity | Procurement Management | Daily Procurement Meetings with Vendors |
|  | PM0001 | Activity | Vendor Management | Factory Visit 1 (Critical Equipment-Compressor Package, Instrument Air Package, Flare Package, N2 Generator Package) |
|  | PM0002 | Activity | Vendor Management | Factory Visit 2 (33kv Gis Switchgear, ICS,HIPS, Metering Skid) |
| Improved Procurement Activities | PM0007 | Activity | Procurement Management | Allocation of Expeditors at Vendor Manufacturing locations |
|  | PM0005 | Activity | Procurement Management | Weekly Procurement expediting meetings with CONTRACTOR and VENDORS |
|  | PM0006 | Activity | Procurement Management | Daily Procurement Meetings with Vendors |
|  | PM0001 | Activity | Vendor Management | Factory Visit 1 (Critical Equipment-Compressor Package, Instrument Air Package, Flare Package, N2 Generator Package) |
|  | PM0002 | Activity | Vendor Management | Factory Visit 2 (33kv Gis Switchgear, ICS,HIPS, Metering Skid) |
| Reduced Operational Cost | A5980 | Activity | RBI Study | Prepare and Issue MR |
|  | A6020 | Activity | Corrosion and Material Assessment Study | Prepare and Issue MR |
|  | J | Innovation Outcome | Product | Achieved industrial standards |
|  | D | Innovation Outcome | Product | Meets health and safety requirements |
|  | A6030 | Activity | Corrosion and Material Assessment Study | Issue PO |

### Closeness Centrality

Following the procedure of the previous sections, Figure 8.28 presents the results for the Closeness Centrality analysis of the Process Innovation Ego Networks.

c)

b)

a)

Figure 8.28: Closeness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

As it was observed previously for the other centrality metrics analysed in this section, Innovation Outcomes “Reduced Project Implementation Time” and “Improved Procurement Activities” present similar results. Figure 8.28 a) and Figure 8.28 b) shows these results. Further, it is observed in Figure 8.28 that apart from a few nodes with zero Closeness Centrality, the values of this centrality metric tend to be relatively high, which means that the nodes of these Ego Network tend to have a central position in them.

The analysis of Closeness Centrality according to the types of nodes is presented in Figure 8.29.

c)

b)

a)

c)

b)

a)

I

c)

b)

a)

II

III

Figure 8.29: Closeness Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figures 8.29 I b), 8.29 II b) and 8.29 III b) show that Innovation Outcome nodes are generally distant from every other node in the network since their closeness is zero. It is also observed that some Activity nodes are very peripheral in the network and while others play a central role in it. Besides, Stakeholder nodes seem to present a high closeness centrality. In terms of this context, this means that Stakeholder nodes can directly influence other nodes in these three Ego Networks. Figures 8.29 I c), 8.29 II c) and 8.29 III c) show that Stakeholder nodes have Closeness Centrality higher than zero. This is in accordance with what was observed in previous sections. Table 8.17 summarises the values presented in Figure 8.29 across the different node types.

Table 8.17: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 1 | 1 | 0 | ~0.88 |
|  | Mean | ~0.44 | ~0.45 | 0 | ~0.67 |
|  | Mode | 0 | 0 | 0 | ~0.54 |
|  | Minimum | 0 | 0 | 0 | ~0.54 |
| Improved Procurement Activities | Maximum | 1 | 1 | 0 | 0.9 |
|  | Mean | ~0.44 | ~0.43 | 0 | ~0.67 |
|  | Mode | 0 | 0 | 0 | ~0.54 |
|  | Minimum | 0 | 0 | 0 | ~0.54 |
| Reduced Operational Cost | Maximum | 1 | 1 | 0 | ~0.58 |
|  | Mean | ~0.46 | ~0.5 | 0 | ~0.56 |
|  | Mode | ~0.56 | 1 | 0 | ~0.56 |
|  | Minimum | 0 | 0 | 0 | ~0.56 |

Figure 8.30 was built to present the impact of Closeness Centrality in the studied social ego networks: larger nodes indicate a higher Closeness Centrality.

c)

b)

a)

c)

Figure 8.30: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

From Figure 8.30, it is observed that following the used colour code, Activity nodes tend to gain relevance across all Ego Networks studied, which is in accordance with the analysis of this subsection. Table 8.18 shows the five nodes with higher Closeness centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”).

Table 8.18: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks

| Closeness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Project Implementation Time | B.01 | Activity |  | Issue Purchase Order for Gas Compressor Packages |
|  | B.02 | Activity |  | Issue Purchase Orders for Air Coolers, Metering Skid Package and K.O Drums |
|  | B.03 | Activity |  | Issue Purchase Orders for 33kV & 11kV Switchgears, HIPPS and Instrument Control Systems (ICS) |
|  | B.04 | Activity |  | Issue Purchase Orders for other Major Electrical Equipment and 33kV Cables |
|  | B.05 | Activity |  | Issue Purchase Order for all balance equipment (Vessels & Drums, Pumps, Overhead Cranes, Gas Filters, Scrapper Launcher/ |
| Improved Procurement Activities | A6100 | Activity | Gas Compressor Train (Compressor + Motor + VFD Transformer + VFD + MMS Panel) | Receipt at Site |
|  | A6450 | Activity | IA Compressor Package | Receipt at Site |
|  | A6900 | Activity | 33kV GIS SWITCHGEAR | Receipt at Site |
|  | A7500 | Activity | Metering skid | Receipt at Site |
|  | A7650 | Activity | HIPS (High | Receipt at Site |
| Reduced Operational Cost | A6020 | Activity | Corrosion and Material Assessment Study | Prepare and Issue MR |
|  | A5980 | Activity | RBI Study | Prepare and Issue MR |
|  | SH16 | Stakeholder |  | Sr.QA/QC Engineer |
|  | SH28 | Stakeholder |  | Sr. QA/QC Engineer |
|  | SH37 | Stakeholder |  | Senior Engineer, Piping |

### Comparison of Centrality Metrics

Figure 8.31 presents an ensemble of the social network metrics which were analysed separately earlier: Degree Centrality, Betweenness Centrality and Closeness Centrality.

b)

a)

c)

Figure 8.31: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figures 8.31 a), b) and c) show that across all Innovation Outcomes, there are nodes which possess zero Closeness and zero Betweenness Centrality. Apart from these, Activity and Stakeholder nodes tend to present high Closeness Centrality. It can also be observed that the plots in Figure 8.31 a) and 8.31 b) are very similar, which is in accordance with the observations made throughout this subsection.

In terms of relevance for this study, one can note that there are some Activity nodes that have high betweenness and so could prove to be influential in the network. Also, it is possible to observe that Stakeholder nodes have access to a lot of nodes and possess some central role in the network, so they can also be considered influential. Considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network, the most influential Stakeholder nodes of Innovation Outcome “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost” are present in Table 8.19.

Table 8.19: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost’s Ego Networks

| Stakeholder Nodes |  |  |  |
| --- | --- | --- | --- |
| Innovation Outcome | Node | Degree | Closeness |
| Reduced Project Implementation Time | SH59 – Cost Control Manager/Procurement Engineer | 25 | 0.878788 |
|  | SH17 – Procurement Engineer | 23 | 0.870968 |
|  | SH1 – Senior Project Manager/Project Manager | 17 | 0.688889 |
|  | SH55 – Project Manager | 10 | 0.589286 |
|  | SH54 – Project Director | 7 | 0.563636 |
| Improved Procurement Activities | SH59 – Cost Control Manager/Procurement Engineer | 24 | 0.900000 |
|  | SH17 – Procurement Engineer | 23 | 0.870968 |
|  | SH1 – Senior Project Manager/Project Manager | 17 | 0.688889 |
|  | SH55 – Project Manager | 9 | 0.584906 |
|  | SH54 – Project Director | 7 | 0.563636 |
| Reduced Operational Cost | SH16 – Sr.QA/QC Engineer | 2 | 0.583333 |
|  | SH28 – Sr. QA/QC Engineer | 2 | 0.583333 |
|  | SH37 – Senior Engineer, Piping | 1 | 0.571429 |
|  | SH60 – QA/QC Manager | 1 | 0.571429 |
|  | SH6 – Team Leader/Engineering Manager | 1 | 0.555556 |

In terms Activities influence on Innovation Outcomes “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”, Table 8.20 presents those which have high Betweenness, high Closeness and high Degree.

Table 8.20: Five Activity nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost’s Ego Networks

| Activity Nodes |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | WBS Name | Description | Degree | Closeness |
| Reduced Project Implementation Time | Procurement Management | Allocation of Expeditors at Vendor Manufacturing locations | 18 | 1 |
|  | Procurement Management | Weekly Procurement expediting meetings with CONTRACTOR and VENDORS | 19 | 1 |
|  | Procurement Management | Daily Procurement Meetings with Vendors | 19 | 1 |
|  | Vendor Management | Factory Visit 1 (Critical Equipment-Compressor Package, Instrument Air Package, Flare Package, N2 Generator Package) | 12 | 0.909091 |
|  | Vendor Management | Factory Visit 2 (33kv Gis Switchgear, ICS,HIPS, Metering Skid) | 11 | 1 |
| Improved Procurement Activities | Procurement Management | Allocation of Expeditors at Vendor Manufacturing locations | 18 | 1 |
|  | Procurement Management | Weekly Procurement expediting meetings with CONTRACTOR and VENDORS | 19 | 1 |
|  | Procurement Management | Daily Procurement Meetings with Vendors | 19 | 1 |
|  | Vendor Management | Factory Visit 1 (Critical Equipment-Compressor Package, Instrument Air Package, Flare Package, N2 Generator Package) | 12 | 0.909091 |
|  | Vendor Management | Factory Visit 2 (33kv Gis Switchgear, ICS,HIPS, Metering Skid) | 11 | 1 |
| Reduced Operational Cost | RBI Study | Prepare and Issue MR | 14 | 1 |
|  | Corrosion and Material Assessment Study | Prepare and Issue MR | 7 | 1 |
|  | Corrosion and Material Assessment Study | Issue PO | 1 | 0 |
|  | RBI Study | Issue PO | 1 | 0 |

## Study of Product Innovation Outcomes

### Product Innovation Outcomes’ Ego Networks.

Table 8.21 presents the general characteristics of the Innovation Outcomes’ Ego Networks.

Table 8.21: Product Innovation Outcomes’ Information

| Innovation Outcome | Label | Description | Total of Nodes | Total of Edges |
| --- | --- | --- | --- | --- |
| 3500 | A | Reduced Production Cost | 22 | 64 |
| 3503 | D | Meets Health and Safety Requirements | 26 | 35 |
| 3509 | I | Achieved Industrial Standards | 149 | 923 |

Observing Table 8.21, it is possible to note that the first two (A and D) Innovation Outcomes’ Ego Networks are slightly similar in terms of size. The second (D) presents less connectivity, despite a slightly higher number of nodes. The third Ego Network (I) is relatively big when compared to the other two and to those on Table 8.10. Results of a further assessment of the characteristics of these Ego Network based on node type are presented in Figure 8.32.

Figure 8.32: Distribution of Node Types for Product Innovation Outcomes’ Ego Networks

The plot of the Figure 8.32 shows that the distribution of node types is different from that presented in section 8.3.1 but is in line with the one presented for the same Product Innovation Outcomes on the Engineering Phase. Figure 8.33 presents the Product Innovation Outcomes’ Ego Networks, created with Gephi software. The Fruchterman Reingold layout algorithm was used to improve visualisation.

b)

a)

c)

Figure 8.33: Ego Networks of Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

### Degree Centrality

Figure 8.34 presents the results for the Degree, In-Degree and Out-Degree Centrality analysis of the Product Innovation Ego Networks.

c)

b)

a)

I

c)

a)

b)

c)

a)

b)

II

III

Figure 8.34: Degree, In-Degree and Out-Degree Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 8.34 shows that the Degree Centrality Distributions are all right skewed. An analysis of Degree Centrality according to node types is illustrated in Figure 8.35.

c)

b)

a)

c)

b)

a)

I

a)

c)

b)

II

III

Figure 8.35: Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

The plots of Figure 8.35 III present the highest values of Degree Centrality, which is because the Ego Network of the Innovation Outcome “Achieved Industrial Standards” is bigger than the other two in this study. Focusing on Figure 8.35 II, it is possible to conclude that Activity nodes’ outliers tend to have a higher Degree value than Stakeholder nodes’ outliers. The opposite happens in Figure 8.35 III. Table 8.22 summarises the values presented in Figure 8.35 across the different node types.

Table 8.22: Degree Centrality relevant values of the Product Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 11 | 11 | 4 | 11 |
|  | Mean | ~6 | ~6 | ~3 | ~8 |
|  | Mode | 4 | 4 | 4 | 10 |
|  | Minimum | 1 | 1 | 1 | 2 |
| Meets Health and Safety Requirements | Maximum | 14 | 14 | 3 | 4 |
|  | Mean | ~3 | ~6 | ~2 | ~2 |
|  | Mode | 1 | 2 | 1 | 1 |
|  | Minimum | 1 | 2 | 1 | 1 |
| Achieved Industrial Standards | Maximum | 99 | 31 | 52 | 99 |
|  | Mean | ~13 | ~10 | ~19 | ~20 |
|  | Mode | 5 | 5 | 52 | 1 |
|  | Minimum | 1 | 2 | 1 | 1 |

Figure 8.36 was built to present the impact of Degree Centrality in the studied social ego networks: larger nodes indicate a higher Degree Centrality.

a)

b)

c)

Figure 8.36: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 8.37 shows the results for In-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

a)

I

c)

b)

c)

a)

b)

II

III

Figure 8.37: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figures 8.37 I c), 8.37 II c) and 8.37 c) show that Stakeholder nodes do not possess any incoming links, which is in accordance with what was observed in the previous chapter.

Table 8.23 summarises the values presented in Figure 8.37 across the different node types.

Table 8.23: In-Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 8 | 8 | 4 | 0 |
|  | Mean | ~3 | ~4 | ~3 | 0 |
|  | Mode | 0 | 3 | 4 | 0 |
|  | Minimum | 0 | 0 | 1 | 0 |
| Meets Health and Safety Requirements | Maximum | 10 | 10 | 3 | 0 |
|  | Mean | ~1.35 | 5 | ~2 | 0 |
|  | Mode | 0 | 2 | 1 | 0 |
|  | Minimum | 0 | 2 | 1 | 0 |
| Achieved Industrial Standards | Maximum | 52 | 29 | 52 | 0 |
|  | Mean | ~6 | ~8.3 | ~19 | 0 |
|  | Mode | 0 | 5 | 52 | 0 |
|  | Minimum | 0 | 1 | 1 | 0 |

Figure 8.38 was built to present the impact of In-Degree Centrality in the studied social ego networks: larger nodes indicate a higher In-Degree Centrality.

b)

a)

c)

Figure 8.38: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

It can be observed that with this distribution, Stakeholder and Innovation Outcome nodes tend to gain relevance in the networks of Figure 8.38. Figure 8.39 shows the results for Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

b)

a)

c)

a)

I

c)

b)

II

c)

b)

a)

III

Figure 8.39: Out-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Figure 8.38 shows that, across all the Innovation Outcomes analysed, every Innovation Outcome node presented an Out-Degree of zero. This was also observed previously for Process Innovation Outcomes, in Section 8.3. Table 8.24 summarises the values presented in Figure 8.39 across the different node types.

Table 8.24: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 11 | 4 | 0 | 11 |
|  | Mean | ~3 | ~2 | 0 | ~8 |
|  | Mode | 0 | 1 | 0 | 10 |
|  | Minimum | 0 | 0 | 0 | 2 |
| Meets Health and Safety Requirements | Maximum | 4 | 4 | 0 | 4 |
|  | Mean | ~2 | ~1 | 0 | ~2 |
|  | Mode | 1 | 0 | 0 | 1 |
|  | Minimum | 0 | 0 | 0 | 1 |
| Achieved Industrial Standards | Maximum | 99 | 4 | 0 | 99 |
|  | Mean | ~6.2 | ~1 | 0 | ~20 |
|  | Mode | 0 | 0 | 0 | 1 |
|  | Minimum | 0 | 0 | 0 | 1 |

Figure 8.40 was built to present the impact of Out-Degree Centrality in the studied social ego networks: larger nodes indicate a higher Out-Degree Centrality.

c)

b)

a)

Figure 8.40: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

To summarise the conclusions related to the analysis of the Process Innovation Outcomes, Figure 8.41 presents the Degree, In-Degree and Out-Degree metrics in the same plots.

b)

a)

c)

Figure 8.41: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c))

From Figure 8.41, it is apparent that Stakeholder nodes only present Out-Degree values and that some of those nodes have a high value of this metric. On the other hand, Innovation Outcome nodes present only In-Degree values. This is in line with what was previously observed. Figure 8.41 c) shows that there is an Innovation Outcome node which has a high value of In-Degree Centrality. Figures 8.41 a) and 8.41 b) present Activity nodes with high Degree, In-Degree and Out-Degree values. Table 8.25 shows the five nodes with higher Degree, In-Degree and Out-Degree centrality for the three Process Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”).

Table 8.25: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Network

|  | Centrality Metric | Node Description | Type |
| --- | --- | --- | --- |
| Reduced Production Cost | Degree | A1350 - Issue PO | Activity |
|  |  | SH55 – Project Manager | Stakeholder |
|  |  | A1630 – Issue PO | Activity |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  | In-Degree | A29250 – Issue PO | Activity |
|  |  | A1350 – Issue PO | Activity |
|  |  | A1630 – Issue PO | Activity |
|  |  | A1650 – Issue PO | Activity |
|  |  | A6260 – Received Vendor Documents | Activity |
|  | Out-Degree | SH55 – Project Manager | Stakeholder |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  |  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | SH17 – Procurement Engineer | Stakeholder |
| Meets Health and Safety Requirements | Degree | A5980 – Prepare and Issue MR | Activity |
|  |  | A6040 – Prepare and Issue MR | Activity |
|  |  | A6000 – Prepare and Issue MR | Activity |
|  |  | SH55 – Project Manager | Stakeholder |
|  |  | D – Meets health and safety requirements | Innovation Outcome |
|  | In-Degree | A5980 – Prepare and Issue MR | Activity |
|  |  | A6040 – Prepare and Issue MR | Activity |
|  |  | A6000 – Prepare and Issue MR | Activity |
|  |  | D – Meets health and safety requirements | Innovation Outcome |
|  |  | A6010 – Issue PO | Activity |
|  | Out-Degree | A5980 – Prepare and Issue MR | Activity |
|  |  | SH55 – Project Manager | Stakeholder |
|  |  | SH18 – Sr. HSE Engineer | Stakeholder |
|  |  | SH62 – Engineering Manager | Stakeholder |
|  |  | SH77 – Sr. Engineer, HSE | Stakeholder |
| Achieved Industrial Standards | Degree | SH55 – Project Manager | Stakeholder |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  |  | J – Achieved industrial standards | Innovation Outcome |
|  |  | SH16 – Sr.QA/QC Engineer | Stakeholder |
|  | In-Degree | J – Achieved industrial standards | Innovation Outcome |
|  |  | A1360 – Prepare and Issue MR | Activity |
|  |  | A1280 – Prepare and Issue MR | Activity |
|  |  | A1300 – Prepare and Issue MR | Activity |
|  |  | A1320 – Prepare and Issue MR | Activity |
|  | Out-Degree | SH55 – Project Manager | Stakeholder |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  |  | SH16 – Sr.QA/QC Engineer | Stakeholder |
|  |  | SH15 – Sr.Piping & Pipeline Engineer | Stakeholder |

### Betweenness Centrality

Figure 8.42 presents the results for the Betweenness Centrality analysis of the Product Innovation Ego Networks.

c)

b)

a)

Figure 8.42: Betweenness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

The plots of Figure 8.42 show that the results are in line with the expected: a few nodes present a high value of Betweenness Centrality, while the rest have a zero value.

A detailed analysis of Betweenness Centrality based on the different node types produces results illustrated on Figure 8.43.

a)

c)

b)

c)

b)

a)

I

II

a)

c)

b)

III

Figure 8.43: Betweenness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Independent of the Innovation Outcome analysed, Figure 8.43 shows that Innovation Outcome and Stakeholder nodes do not have a Betweenness Centrality value different from zero, which is in line with what was observed before. Table 8.26 summarises the values presented in Figure 8.43 across the different node types.

Table 8.26: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | ~14 | ~14 | 0 | 0 |
|  | Mean | ~1.6 | ~2.6 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Meets Health and Safety Requirements | Maximum | 38 | 38 | 0 | 0 |
|  | Mean | ~2.4 | 10 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Achieved Industrial Standards | Maximum | ~35 | ~35 | 0 | 0 |
|  | Mean | ~4 | ~5 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 8.44 was built to present the impact of Betweenness Centrality in the studied social ego networks: larger nodes indicate a higher Betweenness Centrality.

a)

b)

c)

Figure 8.44: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

The images of Figure 8.44 show that Activity nodes gain relevance with this Centrality metric, as was expected. Table 8.27 shows the five nodes with higher Betweenness centrality for the three Product Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”).

Table 8.27: Five Nodes with Higher Betweenness Centrality for each Product Innovation Outcome

| Betweenness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Production Cost | A1350 | Activity | Discharged Cooler | Issue PO |
|  | A1630 | Activity | LV Switchgear | Issue PO |
|  | A1650 | Activity | Power transformer 40 MVA | Issue PO |
|  | A5850 | Activity | NDT works at Site | Issue PO |
|  | B.02 | Activity |  | Issue Purchase Orders for Air Coolers , Metering Skid Package and K.O Drums (NOTE-3) |
| Meets Health and Safety Requirements | A5980 | Activity | RBI Study | Prepare and Issue MR |
|  | A6040 | Activity | F&G Mapping Study | Prepare and Issue MR |
|  | A6000 | Activity | Noise Study | Prepare and Issue MR |
|  | J | Innovation Outcome | Product | Achieved industrial standards |
|  | A6010 | Activity | Noise Study | Issue PO |
| Achieved Industrial Standards | A5980 | Activity | RBI Study | Prepare and Issue MR |
|  | A1360 | Activity | Suction K.O. drum | Prepare and Issue MR |
|  | A1280 | Activity | Instrument Air Receiver | Prepare and Issue MR |
|  | A1300 | Activity | Nitrogen Receiver | Prepare and Issue MR |
|  | A1320 | Activity | Sales Gas Filter | Prepare and Issue MR |

### Closeness Centrality

Figure 8.45 presents the results for the Closeness Centrality analysis of the Process Innovation Ego Networks.

c)

b)

a)

Figure 8.45: Closeness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Improved Procurement Activities” (b) and “Achieved Industrial Standards” (c)

Figures 8.45 a), 8.45 b) and 8.45 c) present a similar pattern: there are significant numbers of nodes with zero Closeness and another significant number with 1. Besides, the rest of the nodes present a Closeness Centrality value higher than 0.5 and lower than 1. These results are in line with what was previously observed. Results of a detailed analysis based on node types is illustrated in Figure 8.46.

c)

b)

a)

I

c)

b)

a)

c)

b)

a)

II

III

Figure 8.46: Closeness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node types (Activity (a), Innovation Outcome (b) and Stakeholder (c))

Figures 8.46 I b), 8.46 II b) and 8.46 III b) show that Innovation Outcomes have zero closeness centrality, like was observed earlier for Process Innovation and for the Engineering Phase. It is also observed that some Activity nodes are peripheral in the network and some of them tend to play a central role. (Figure 8.46 I a; 8.46 II a) and 8.46 III a). Focusing on Figures 8.46 I a), 8.46 II a) and 8.46 III a), it is observed that the distributions follow a pattern which is similar to the outliers of the plots of Figure 8.45.

Further, Figure 8.46 I c), 8.46 II c) and 8.46 III c) show that Stakeholder nodes tend to have a Closeness Centrality measure higher than 0.5 and lower than 1. Table 8.28 summarises the values presented in Figure 8.46 across the different node types.

Table 8.28: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 1 | 1 | 0 | 0.8125 |
|  | Mean | ~0.54 | ~0.52 | 0 | ~0.74 |
|  | Mode | 0 | 1 | 0 | 0.8125 |
|  | Minimum | 0 | 0 | 0 | 0.6 |
| Meets Health and Safety Requirements | Maximum | 1 | 1 | 0 | ~0.83 |
|  | Mean | ~0.51 | 0.5 | 0 | ~0.6 |
|  | Mode | 0.6 | 1 | 0 | 0.6 |
|  | Minimum | 0 | 0 | 0 | ~0.56 |
| Achieved Industrial Standards | Maximum | 1 | 1 | 0 | ~1 |
|  | Mean | ~0.54 | ~0.50 | 0 | ~0.68 |
|  | Mode | 0 | 1 | 0 | ~0.66 |
|  | Minimum | 0 | 0 | 0 | ~0.54 |

Figure 8.47 was built to present the impact of Closeness Centrality in the studied social ego networks: larger nodes indicate a higher Closeness Centrality.

b)

a)

c)

Figure 8.47: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 8.47 shows that Activity nodes followed by Stakeholder nodes gain relevance in the Networks presented. Table 8.29 shows the five nodes with high Closeness centrality for the three Product Innovation Outcomes “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”.

Table 8.29: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks

| Closeness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Production Cost | B.02 | Activity |  | Issue Purchase Orders for Air Coolers , Metering Skid Package and K.O Drums (NOTE-3) |
|  | A1350 | Activity | Discharged Cooler | Issue PO |
|  | A1630 | Activity | LV SWITCHGEAR | Issue PO |
|  | A1650 | Activity | POWER TRANSFORMER 40 MVA | Issue PO |
|  | A5850 | Activity | NDT works at Site | Issue PO |
| Meets Health and Safety Requirements | A6000 | Activity | Noise Study | Prepare and Issue MR |
|  | A6040 | Activity | F&G Mapping Study | Prepare and Issue MR |
|  | A5980 | Activity | RBI Study | Prepare and Issue MR |
|  | SH55 | Stakeholder |  | Project Manager |
|  | SH76 | Stakeholder |  | Sr. QA/QC Engineer |
| Achieved Industrial Standards | A1280 | Activity | Instrument Air Receiver | Prepare and Issue MR |
|  | A1300 | Activity | Nitrogen Receiver | Prepare and Issue MR |
|  | A1320 | Activity | Sales Gas Filter | Prepare and Issue MR |
|  | A1340 | Activity | Discharged Cooler | Prepare and Issue MR |
|  | A1360 | Activity | Suction K.O. drum | Prepare and Issue MR |

### Comparison of Centrality Metrics

Figure 8.48 presents an ensemble of the social network metrics that were analysed separately earlier.

b)

a)

c)

Figure 8.48: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figures 8.48 a), b) and c) show that across all Innovation Outcomes, there are nodes which possess zero Closeness and zero Betweenness Centrality. Most of those nodes tend to be Innovation Outcome nodes. Apart from these, Activity and Stakeholder nodes present high Closeness Centrality as well as high Degree Centrality. There is an important group of outliers all of them being Activity nodes which present high values of Betweenness, Closeness and Degree centrality. These can be found in the top left of the plots of Figure 8.48 a), b) and c). These results are in line with the ones observed in Section 8.3.5, for Process Innovation Outcomes.

Considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network, the most influential Stakeholder nodes of Innovation Outcome “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards” are presented in Table 8.30.

Table 8.30: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standard’s Ego Networks

| Stakeholder Nodes |  |  |  |
| --- | --- | --- | --- |
| Innovation Outcome | Description | Degree | Closeness |
| Reduced Production Cost | SH60 – QA/QC Manager | 10 | 0.812500 |
|  | SH76 – Sr. QA/QC Engineer | 10 | 0.812500 |
|  | SH55 – Project Manager | 11 | 0.789474 |
|  | SH17 – Procurement Engineer | 6 | 0.714286 |
|  | SH59 – Cost Control Manager/Procurement Engineer | 7 | 0.705882 |
| Meets Health and Safety Requirements | SH55 – Project Manager | 4 | 0.833333 |
|  | SH76 – Sr. QA/QC Engineer | 2 | 0.625000 |
|  | SH18 – Sr. HSE Engineer | 3 | 0.600000 |
|  | SH62 – Engineering Manager | 3 | 0.600000 |
|  | SH77 – Sr. Engineer, HSE | 3 | 0.600000 |
| Achieved Industrial Standards | SH55 – Project Manager | 99 | 0.990099 |
|  | SH76 – Sr. QA/QC Engineer | 98 | 0.990000 |
|  | SH17 – Procurement Engineer | 49 | 0.980392 |
|  | SH60 – QA/QC Manager | 98 | 0.971154 |
|  | SH54 – Project Director | 21 | 0.956522 |

In terms Activities influence on Innovation Outcomes “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”, Table 8.31 presents those which have high Closeness and high Degree.

Table 8.31: Five Activity nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial standards’ Ego Networks

| Activity Nodes |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | WBS Name | Description | Degree | Closeness |
| Reduced Production Cost | Discharged Cooler | Issue PO | 11 | 1 |
|  | LV Switchgear | Issue PO | 10 | 1 |
|  | Power Transformer 40 MVA | Issue PO | 9 | 1 |
|  | NDT works at Site | Issue PO | 5 | 1 |
|  |  | Issue Purchase Orders for Air Coolers, Metering Skid Package and K.O Drums (NOTE-3) | 4 | 1 |
| Meets Health and Safety Requirements | RBI Study | Prepare and Issue MR | 14 | 1 |
|  | F&G Mapping Study | Prepare and Issue MR | 10 | 1 |
|  | Noise Study | Prepare and Issue MR | 8 | 1 |
|  | Noise Study | Issue PO | 2 | 0 |
|  | F&G Mapping Study | Issue PO | 2 | 0 |
| Achieved Industrial Standards | RBI Study | Prepare and Issue MR | 14 | 1 |
|  | Suction KO drum | Prepare and Issue MR | 31 | 1 |
|  | Instrument Air Receiver | Prepare and Issue MR | 29 | 1 |
|  | Nitrogen Receiver | Prepare and Issue MR | 29 | 1 |
|  | Sales Gas Filter | Prepare and Issue MR | 29 | 1 |

## Summary

In this chapter, an analysis of the social network of Activities, Stakeholders and Innovation outcomes of the Procurement Phase of the EPC project was performed. It was observed that some Activity nodes tend to present a high Betweenness Centrality and that some Stakeholder nodes tend to present a high Closeness Centrality. After an initial overview of the Procurement Phase, this chapter presented the detailed analysis for the Innovation Outcomes. This analysis was divided in two sections as it was done in the previous chapter: Process Innovation Outcomes and Product Innovation Outcomes. It was observed that some stakeholders (Project Manager, Procurement Engineer and QA/QC Manager) present a high influence on Innovation Outcomes.

The next chapter presents findings on the Construction phase of the EPC project.

# Results - Construction

## Introduction

This chapter discusses the results of the analysis of the social network built with the data collected on the EPC project for the Construction Phase. The analysis is focused on centrality metrics namely, degree centrality, closeness centrality and betweenness centrality. The scope of the analysis starts with an overview of the Construction Phase social network and then moves to a detailed analysis of Innovation Outcome nodes’ Ego Networks grouped into Process Innovation and Product Innovation. These Ego Networks have a depth of two, meaning that they are composed by the Innovation Outcome node itself, its neighbours, and its neighbours’ neighbours. For each Ego Network, centrality metrics are computed with the help of Gephi software to find Stakeholders and Activities that influence the corresponding Innovation Outcome.

## Construction Phase Overview

Focusing on the third and last phase of the EPC project, Figure 9.1 presents the social network composed by the nodes and relationships of the Construction Phase. The image was produced with the Gephi software, using the Force Atlas layout algorithm with a repulsion strength of 300, among other visualisation parameters.

Figure 9.1: Construction Phase Social Network

Figure 9.1 shows that there are nodes which occupy a central position in the network, while other nodes are very peripheral. It also shows that there is a high number of edges connecting the nodes. In other words, the density of the graph seems high. This will be further analysed in the next subsections. Table 9.1 presents a summary of the Construction Phase social network’s main general characteristics.

Table 9.1: General Characteristics of the Construction Phase Social Network.

| Characteristic | Value |
| --- | --- |
| Total of Nodes | 934 |
| Total of Edges | 19930 |

The numbers in Table 9.1 show that this is a big network involving a relevant number of nodes. When compared to the other two studied networks (Engineering and Procurement), this is the second largest in terms of number of nodes, but presents the highest number of edges. This means that the nodes of this network are very interrelated and interconnected.

Focusing on the types of nodes that exist in the social network under analysis, Figure 9.2 presents a pie chart illustrating their distribution.

Figure 9.2: Distribution of Node Types in the Construction Phase Social Network

The majority of the Construction Phase social network is composed of activities, which represent 79.4% of the total number of nodes. The second largest group is the Stakeholder nodes’ group, which represent almost 20% of the whole network, and the smallest group is the Innovation Outcome nodes, which represents 1.1% of the total number of nodes.

In summary, the Construction Phase Social Network has 742 Activity nodes, 182 Stakeholder nodes and 10 Innovation Outcomes nodes.

### 9.2.1 Construction Phase Social Network Metrics

Table 9.2 presents relevant metrics for the Procurement Phase Social Network.

Table 9.2: Social Network Metrics of the Construction Phase Social Network

| Social Network Metrics | Value |
| --- | --- |
| Network Diameter | 16 |
| Graph Density | 0.022 |
| Average Path Length | ~5 |
| Average Clustering Coefficient | 0.077 |
| Average Degree | ~21 |

Table 9.2 shows that the network diameter for this network is 16, which is lower than the 28 reported in section 7.2.1 and higher than that presented in section 8.2.1. This indicates that the network is significantly smaller than that of the Engineering Phase but bigger than that of the Procurement Phase. Table 9.2 also shows that the graph density is much higher than the previous networks studied, presenting a value of 0,022. This is in accordance with the observation made before referring to the high number of edges in the network.  The average path length value 5. Table 9.2 indicates that the average clustering coefficient is of 0.077 and that the average degree of the network, which is 21, is higher than what was observed in the other two networks.

### 9.2.2 Degree Centrality

Figure 9.3 presents the results of the analysis of the Degree, In-Degree and Out-Degree Distribution for the Construction Phase social network.

a)

b)

c)

Figure 9.3: Degree a), In-Degree b) and Out-Degree c) Centrality in the Construction Phase Social Network.

All the Degree distributions presented above in Figure 9.3 are skewed to the right, which means that most of the nodes in the Construction Phase Social Network present low connectivity. Due to the existence of heavy outliers in Figures 9.3 a) and 9.3 b), the plots of Figure 9.4 were built with without nodes with a Degree and Out-Degree higher than 100.

b)

a)

Figure 9.4: Degree a) and Out-Degree b) Centrality in the Construction Phase Social Network for nodes with less than 100 value

To extract further details of the analysis according to the different node types (Activities, Innovation Outcomes and Stakeholders), Figure 9.5 presents the results for Degree, In-Degree and Out-Degree Centrality.

c)

b)

a)

I

c)

a)

b)

II

a)

b)

c)

III

Figure 9.5: Degree (I), In-Degree (II) and Out-Degree Centrality (III) in the Construction Phase Social Network according to node type

Stakeholder nodes present a zero In-Degree value, while Innovation Outcome present the same value but for Out-Degree centrality. This is in accordance with the findings of the previous chapter. Figures 9.5 I and 9.5 III show that Activity nodes tend to have a lower Degree and Out-Degree Centrality than Stakeholder nodes, while Innovation Outcomes present even lower values. This is consistent with characteristics of an EPC Project where Stakeholders serve as a connection to many activities. Table 9.3 summarises the values presented in Figure 9.5 across the different node types and the analysed Centrality metrics.

Table 9.3: Degree Centrality relevant values of the Construction Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Centrality Metric | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| DEGREE | Maximum | 722 | 97 | 19 | 722 |
|  | Mean | ~42 | ~28 | ~7 | ~98 |
|  | Mode | 22 | 22 | 0 | 0 |
|  | Minimum | 0 | 2 | 0 | 0 |
| IN-DEGREE | Maximum | 95 | 95 | 19 | 0 |
|  | Mean | ~21 | ~26 | ~7 | 0 |
|  | Mode | 0 | 21 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| OUT-DEGREE | Maximum | 722 | 12 | 0 | 722 |
|  | Mean | ~21 | ~2.1 | 0 | ~98 |
|  | Mode | 1 | 1 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 9.6 shows the Construction Phase Social Network affected Degree, In-Degree and Out-Degree: bigger nodes indicate a higher centrality result.

b)

a)

c)

Figure 9.6: Degree a), In-Degree b) and Out-Degree Centrality c) in the Construction Phase Social Network

Figure 9.6 shows that there are some Stakeholder nodes that gain a significant relevance in Degree (a) and Out-Degree (c) distributions. This is consistent with what was observed in the previous chapters.

To summarise the conclusions related to the analysis of the Construction Phase social network, Figure 9.7 presents the Degree, In-Degree and Out-Degree metrics in the same plot.

Figure 9.7: Construction Phase Social Network summary of Degree Centrality values

Figure 9.7 shows that Stakeholder nodes have an Out-Degree value which is higher than zero and do not present In-Degree values. Some of these nodes present a high value of Out-Degree. The opposite conclusion can be drawn for the Activity nodes. Innovation Outcome nodes tend to be present in the inferior left corner, meaning they tend to have few connections and that all of them are incoming. Table 9.4 shows the 10 nodes with higher Degree, In-Degree and Out-Degree centrality in the Construction Phase.

Table 9.4: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Construction Phase Social Network

| Centrality Metric | Node Description | Type |
| --- | --- | --- |
| Degree | SH56 – Construction Manager | Stakeholder |
|  | SH5 – Sr. Construction Engineer | Stakeholder |
|  | SH29 – Sr. Engineer, HSE | Stakeholder |
|  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  | SH77 – Sr. Engineer, HSE | Stakeholder |
|  | SH78 – Safety Officer, HSE | Stakeholder |
|  | SH18 – Sr. HSE Engineer | Stakeholder |
|  | SH79 – QA/QC Inspector-Civil | Stakeholder |
|  | SH16 – Sr.QA/QC Engineer | Stakeholder |
|  | SH28 – Sr. QA/QC Engineer | Stakeholder |
| In-Degree | A31970 – As-built Documentation | Activity |
|  | CC3070 – Mechanical Completion | Activity |
|  | CC2990 – Mechanical Completion | Activity |
|  | CC3260 – Mechanical Completion | Activity |
|  | CC2080 – Mechanical Completion - Substation | Activity |
|  | CC1800 – Mechanical Completion - Control Room | Activity |
|  | CC2950 – SDV / Control Valve Testing | Activity |
|  | CC1850 – Mechanical Completion - Compressor Station Guard House | Activity |
|  | CC2270 – Commissioning - Substation | Activity |
|  | CC2550 – Mechanical Completion - Custody Transfer Area | Activity |
| Out-Degree | SH56 – Construction Manager | Stakeholder |
|  | SH5 – Sr. Construction Engineer | Stakeholder |
|  | SH29 – Sr. Engineer, HSE | Stakeholder |
|  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  | SH77 – Sr. Engineer, HSE | Stakeholder |
|  | SH78 – Safety Officer, HSE | Stakeholder |
|  | SH18 – Sr. HSE Engineer | Stakeholder |
|  | SH79 – QA/QC Inspector-Civil | Stakeholder |
|  | SH16 – Sr.QA/QC Engineer | Stakeholder |
|  | SH28 – Sr. QA/QC Engineer | Stakeholder |

Table 9.5 shows the 10 nodes with lower Degree, In-Degree and Out-Degree centrality in the Construction Phase.

Table 9.5: Ten Nodes with Lower Degree, In-Degree and Out-Degree Centrality in the Construction Phase Social Network

| Centrality Metric | Node Description | Type |
| --- | --- | --- |
| Degree | SH20 – Acting Team Leader, Reliability | Stakeholder |
|  | SH21 – Senior Engineer, Reliability | Stakeholder |
|  | SH22 – Senior Engineer, Reliability | Stakeholder |
|  | SH23 – Team Leader, Integrity | Stakeholder |
|  | SH24 – Senior Engineer, Integrity | Stakeholder |
|  | SH25 – Senior Engineer, Integrity | Stakeholder |
|  | SH26 – Acting Team Leader, Integrity | Stakeholder |
|  | SH27 – Engineer, Integrity | Stakeholder |
|  | SH32 – Senior Engineer, Procurement | Stakeholder |
|  | SH63 – Sr. Process Engineer | Stakeholder |
| In-Degree | A31311 – Approval and Obtaining the NOC from Municipality & Authorities (Coordination between Siemens & Municipality) | Activity |
|  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  | SH2 – Sr. Project Engineer | Stakeholder |
|  | SH3 – Interface Co-ordinator | Stakeholder |
|  | SH4 – Sr. Planning Engineer | Stakeholder |
|  | SH5 – Sr. Construction Engineer | Stakeholder |
|  | SH6 – Team Leader/Engineering Manager | Stakeholder |
|  | SH7 – Project Co-ordinator | Stakeholder |
|  | SH8 – Interface Co-ordinator | Stakeholder |
|  | SH9 – Sr. Instrument and Control Engineer | Stakeholder |
| Out-Degree | M1110 – Commissioning Completion all area | Activity |
|  | H – Stakeholders’ engagement | Innovation Outcome |
|  | I – Reduced operational cost | Innovation Outcome |
|  | A – Reduced Production Cost | Innovation Outcome |
|  | B – Reduced project implementation time | Innovation Outcome |
|  | A31970 – As-built Documentation | Activity |
|  | G – Improved procurement activities | Innovation Outcome |
|  | D – Meets health and safety requirements | Innovation Outcome |
|  | SH20 – Acting Team Leader, Reliability | Stakeholder |
|  | SH21 – Senior Engineer, Reliability | Stakeholder |

### 9.2.3 Betweenness Centrality

Figure 9.8 shows the results of the Betweenness Centrality distribution for the Construction Phase social network.

Figure 9.8: Betweenness Centrality in the Construction Phase Social Network

Figure 9.8 shows that the distribution is skewed to the right, which means that most of the nodes have a low level of Betweenness Centrality. This indicates that a small number of nodes of this network might have a high influence in the graph. Some of these nodes are heavy outliers, meaning that they do have a high Betweenness Centrality in the network as is indicated on the inferior right side of the plot of Figure 9.8. Proceeding along the same lines as the previous sections, Figure 9.9 presents the Betweenness Centrality results according to the types of nodes.

c)

b)

a)

Figure 9.9: Betweenness Centrality in the Procurement Phase Social Network according to node type

As was noted before, both Innovation Outcome nodes and Stakeholder nodes have a zero Betweenness Centrality, which means that the most influential nodes on the Construction Phase social network are the activity nodes. Table 9.6 presents relevant values of this distribution.

Table 9.6: Betweenness Centrality relevant values of the Construction Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- |
| Maximum | 10112 | 10112 | 0 | 0 |
| Mean | ~385 | ~485 | 0 | 0 |
| Mode | 0 | 0 | 0 | 0 |
| Minimum | 0 | 0 | 0 | 0 |

Figure 9.10 shows the Construction Phase Social Network affected by the Betweenness Centrality results: larger nodes indicate a higher Betweenness Centrality

Figure 9.10: Construction Phase Social Network affected by Betweenness Centrality

Figure 9.10 illustrates that Activity nodes gain relevance in the network, which is in line with what was analysed before.

Table 9.7 shows the 10 Activity nodes with high Betweenness Centrality in the Construction Phase.  The other types of nodes have a zero betweenness value.

Table 9.7: Ten Nodes with Higher Betweenness Centrality in the Construction Phase Social Network

| Betweenness Centrality |  |  |  |
| --- | --- | --- | --- |
| Node | Type | WBS Task Name | Project Activity Description |
| CC3070 | Activity | Mechanical Completion Train 2 | Mechanical Completion |
| D.01 | Activity |  | Complete foundation works for Compressors and Compressor Shelters for all facilities including Lube Oil Skids, etc. |
| A31310 | Activity | Temporary Facilities | Site Survey |
| CC2990 | Activity | Mechanical Completion Train 1 | Mechanical Completion |
| CC1010 | Activity | Piling | Piling Works |
| CC3150 | Activity | Compressor Train 2 | Sequence Test |
| CC3090 | Activity | Compressor Train 1 | Sequence Test |
| CC3300 | Activity | Compressor Train 3 | Sequence Test |
| CC1310H | Activity | Compressor Foundation | Compressor Foundation - Back Filling |
| CC3260 | Activity | Mechanical Completion Train 3 | Mechanical Completion |

### 9.2.4 Closeness Centrality

Figure 9.11 shows the results of the Closeness Centrality distribution for the Construction Phase social network.

Figure 9.11: Closeness Centrality in the Construction Phase Social Network

As before, most of the nodes have a low closeness, meaning that they are not central to the network, while a few of them tend to have a high closeness value. The analysis of Closeness Centrality according to types of nodes is presented in Figure 9.12.

b)

c)

a)

Figure 9.12: Closeness Centrality in the Construction Phase Social Network according to node type

Figure 9.12 shows that Innovation Outcome nodes are generally distant from every other node in the network since their closeness is zero. This means that Innovation Outcomes tend not to be central in the network because they are the outputs of the Innovation flow. Table 9.8 summarises the relevant values presented across the different node types.

Table 9.8: Closeness Centrality relevant values of the Construction Phase Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- |
| Maximum | 1 | 1 | 0 | ~0.97 |
| Mean | ~0.26 | ~0.25 | 0 | ~0.34 |
| Mode | 0 | 1 | 0 | 0 |
| Minimum | 0 | 0 | 0 | 0 |

Figure 9.13 presents the Construction Phase Social Network affected by Closeness Centrality: larger nodes indicate a higher Closeness Centrality.

Figure 9.13: Construction Phase Social Network affected by Closeness Centrality

Figure 9.13 shows that there are Activity nodes with high closeness, which is because activities are close to each other in terms of a WBS logic and they are also close to Stakeholders. Table 9.9 shows the 10 nodes with high Closeness Centrality in the Construction Phase.

Table 9.9: Ten Nodes with Higher Closeness Centrality in the Construction Phase Social Network

| Closeness Centrality |  |  |  |
| --- | --- | --- | --- |
| Node | Type | WBS Task Name | Project Activity Description |
| G1070 | Activity |  | Mechanical Completion - Substation |
| G1080 | Activity |  | Commissioning Completion -Substation |
| G1090 | Activity |  | Mechanical Completion - Compressor Train 1 |
| G1100 | Activity |  | Mechanical Completion - Compressor Train 2 |
| G1110 | Activity |  | Gas In (Compressor Train 1) |
| G1120 | Activity |  | Mechanical Completion - Compressor Train 3 |
| G1130 | Activity |  | Gas In (Compressor Train 2) |
| E.02 | Activity |  | Complete Commissioning of Tr-3 Facilities and achieve "Gas-in" to Pipeline Network to meet Consumer demand (NOTE-4) |
| D.11 | Activity |  | Achieve MECHANICAL COMPLETION (MC 1) for Train 1 & 2 (NOTE-4) |
| D.12 | Activity |  | Achieve MECHANICAL COMPLETION (MC 2) for Train 3 (NOTE-4) |

### 9.2.5 Comparison of Centrality Metrics

Figure 9.14 presents an ensemble of the Construction Phase social network metrics that were analysed separately earlier: Degree Centrality, Betweenness Centrality and Closeness Centrality.

Figure 9.14: Construction Phase Social Network summary of Centrality metrics

From Figure 9.14, it is observed that there are many nodes with a Closeness Centrality value around 0.25. Besides this, one notes that Stakeholder nodes only present a positive Closeness Centrality and that in some cases their value is close to 1. In terms of Degree value, Figure 9.14 shows that some nodes present high values (especially some Stakeholder nodes and some Activity nodes) but that most of the nodes tend to present a low value of connectivity. In terms of Betweenness Centrality, the plot of Figure 9.14 shows that only Activity nodes present values greater than zero and that in some cases, the Betweenness of those nodes is high. In that regard, as was the case in previous phases, one can conclude that Activity nodes tend to be the most influential in the Construction Phase of the EPC Project.

## Study of Process Innovation Outcomes

### 9.3.1 Process Innovation Outcomes’ Ego Networks

Table 9.10 presents the general characteristics of the Innovation Outcomes’ Ego Networks analysed in this subsection.

Table 9.10: Process Innovation Outcomes’ Information for the Construction Phase of the EPC Project

| Innovation Outcome | Label | Description | Total of Nodes | Total of Edges |
| --- | --- | --- | --- | --- |
| 3501 | B | Reduced Project Implementation Time | 121 | 1399 |
| 3506 | G | Improved Procurement Activities | 44 | 286 |
| 3508 | I | Reduced Operational Cost | 1 | 0 |

Table 9.10 shows that the Innovation Outcomes’ Ego Networks are of medium size when compared to the other networks studied for the Engineering and Procurement Phase. Further it shows that the “Reduced Operational Cost” does not present any connections to the other entities (Stakeholders and Activities) in the Construction Phase. Due to this, the next subsections will not show the results for Innovation Outcome “Reduced Operational Cost” since they will always be zero. To further assess the characteristics of these Ego Networks, the plot in Figure 9.15 presents their distribution according to node types.

Figure 9.15: Distribution of Node Types for Process Innovation Outcomes’ Ego Networks

Figure 9.16 presents the Process Innovation Outcomes’ Ego Networks, created with Gephi software. The Fruchterman Reingold layout algorithm was used to improve visualisation.

b)

a)

c)

Figure 9.16: Ego Networks of Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

### 9.3.2 Degree Centrality

Figure 9.17 presents the results for the Degree, In-Degree and Out-Degree Centrality analysis of the first two Process Innovation Ego Networks.

b)

a)

I

b)

a)

II

b)

a)

III

Figure 9.17: Degree (I), In-Degree (II) and Out-Degree Centrality (III) of Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)

Figure 9.17 shows that practically all the Degree Centrality values, across all node types, tend to have a right skewed distribution. This is in line with what was previously observed and means that most of the nodes of these Ego Networks present few connections. An analysis of Degree Centrality according to the different node types is presented in Figure 9.18.

c)

a)

b)

I

c)

b)

a)

II

Figure 9.18: Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I) and “Improved Procurement Activities” (II) according to node type

Figure 9.18 I a) shows that the Degree Centrality distribution is left skewed, which means that Activity nodes tend to have high connectivity in the “Reduced Project Implementation Time” social network. Besides this, Figure 9.18 c) presents a centred distribution, which means that most of the Stakeholder nodes have an average connectivity of 20 links. Focusing on Figure 9.18 II, it is observed that the nodes tend to present a wide range of Degree centrality, which means that in this network there are nodes with few connections, but others tend to present a high number of links. Table 9.11 summarises the values presented in Figure 9.18 across the different node types.

Table 9.11: Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 52 | 40 | 19 | 52 |
|  | Mean | ~24 | ~28 | ~11 | ~20 |
|  | Mode | 16 | 29 | 8 | 16 |
|  | Minimum | 1 | 4 | 5 | 1 |
| Improved Procurement Activities | Maximum | 29 | 29 | 7 | 24 |
|  | Mean | 13 | ~15 | ~6 | ~13 |
|  | Mode | 7 | 7 | 5 | 5 |
|  | Minimum | 4 | 7 | 5 | 5 |

Figure 9.19 presents the impact of Degree Centrality in the studied social ego networks: larger nodes indicate a higher Degree Centrality.

b)

a)

Figure 9.19: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” a) and “Improved Procurement Activities” b)

The Ego Networks a) and b) present Activity and Stakeholder nodes with higher relevance, which is in accordance with the analysis presented earlier.

Figure 9.20 presents the results for In-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders), for each Ego Network.

c)

b)

a)

c)

b)

I

a)

II

Figure 9.20: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I) and “Improved Procurement Activities” (II) according to node type

As expected, the behaviour observed in the plots of Figure 9.20 are in line with what was previously concluded, that Stakeholder nodes do not present incoming connections. The values of In-Degree Centrality for Innovation Outcome nodes are the same for their Degree Centrality (observed in Figures 9.18 I b) and 9.18 II b)) since this type of nodes do not present outgoing links. Table 9.12 summarises the values presented in Figure 9.20 across the different node types.

Table 9.12: In-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 39 | 39 | 19 | 0 |
|  | Mean | ~12 | ~26 | ~11 | 0 |
|  | Mode | 0 | 27 | 8 | 0 |
|  | Minimum | 0 | 4 | 5 | 0 |
| Improved Procurement Activities | Maximum | 21 | 21 | 7 | 0 |
|  | Mean | ~6.5 | ~12 | ~6 | 0 |
|  | Mode | 0 | 5 | 5 | 0 |
|  | Minimum | 0 | 4 | 5 | 0 |

Figure 9.21 presents the impact of In-Degree Centrality in the studied social ego networks: larger nodes indicate a higher In-Degree Centrality.

b)

a)

Figure 9.21: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)

Figure 9.22 shows the results for Out-Degree Centrality according to the node type

b)

a)

c)

c)

b)

I

a)

II

Figure 9.22: Out-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I) and “Improved Procurement Activities” (II) according to node type

Figure 9.22 shows that, across all the Innovation Outcomes analysed, every Innovation Outcome node presented an Out-Degree of zero, which is in accordance with what was previously noticed in the In-Degree analysis of this subsection. An analysis of Figure 9.22 I and 9.22 II reveals that the outliers of Stakeholder nodes present a higher Out-Degree than Activity nodes. This means those Stakeholder nodes have higher connectivity. Table 9.13 summarises the values presented in Figure 9.22 across the different node types.

Table 9.13: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 52 | 12 | 0 | 52 |
|  | Mean | ~12 | ~3 | 0 | ~20 |
|  | Mode | 2 | 2 | 0 | 16 |
|  | Minimum | 0 | 0 | 0 | 1 |
| Improved Procurement Activities | Maximum | 24 | 12 | 0 | 24 |
|  | Mean | ~6.5 | ~3 | 0 | ~13 |
|  | Mode | 0 | 0 | 0 | 5 |
|  | Minimum | 0 | 0 | 0 | 5 |

Figure 9.23 presents the impact of Out-Degree Centrality in the studied social ego networks: larger nodes indicate a higher Out-Degree Centrality.

b)

a)

Figure 9.23: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)

To summarize the conclusions related to the analysis of the Process Innovation Outcomes, Figure 9.24 presents the Degree, In-Degree and Out-Degree metrics in the same plots.

b)

a)

Figure 9.24: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b))

The plots in Figure 9.24 show that Innovation Outcomes only present incoming links, while Stakeholder nodes only have outgoing connections, across all the studied Ego Networks. The first type of nodes presents a maximum In-Degree value of around 20, while the second type presents values higher than 50 for Out-Degree centrality. Observing the plots, reveals that some Activity nodes show high values for both In- and Out-Degree Centrality and that for Figure 9.24 a), the majority of this type of nodes present values around 30 for In-Degree Centrality and around 5 for Out-Degree Centrality. This indicates that there is a high number of incoming connections on these nodes. Table 9.14 shows the five nodes with higher Degree, In-Degree and Out-Degree centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”).

Table 9.14: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Networks

|  | Centrality Metric | Node Description | Type |
| --- | --- | --- | --- |
| Reduced Project Implementation Time | Degree | SH5 – Sr. Construction Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  |  | CC3070 – Mechanical Completion | Activity |
|  |  | CC2990 – Mechanical Completion | Activity |
|  |  | SH18 – Sr. HSE Engineer | Stakeholder |
|  | In-Degree | CC2990 – Mechanical Completion | Activity |
|  |  | CC3070 – Mechanical Completion | Activity |
|  |  | CC3260 – Mechanical Completion | Activity |
|  |  | D.11 – Achieve Mechanical Completion (MC 1) for Train 1 & 2 (Note-4) | Activity |
|  |  | CC2320 – All Equipment Installation | Activity |
|  | Out-Degree | SH5 – Sr. Construction Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  |  | SH18 – Sr. HSE Engineer | Stakeholder |
|  |  | SH131 – Construction Engineer-Piping &Pipeline | Stakeholder |
|  |  | SH29 – Sr. Engineer, HSE | Stakeholder |
| Improved Procurement Activities | Degree | PM0011 – Schedule Risk Analysis Workshop 5 | Activity |
|  |  | PM0008 – Schedule Risk Analysis Workshop 2 | Activity |
|  |  | PM0009 – Schedule Risk Analysis Workshop 3 | Activity |
|  |  | PM0010 – Schedule Risk Analysis Workshop 4 | Activity |
|  |  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  | In-Degree | CC307 – Mechanical Completion | Activity |
|  |  | CC2990 – Mechanical Completion | Activity |
|  |  | CC3260 – Mechanical Completion | Activity |
|  |  | PM0011 – Schedule Risk Analysis Workshop 5 | Activity |
|  |  | CC1800 – Mechanical Completion - Control Room | Activity |
|  | Out-Degree | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  |  | SH55 – Project Manager | Stakeholder |
|  |  | SH5 – Sr. Construction Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  |  | SH128 – Construction Engineer-Mechanical | Stakeholder |

### 9.3.3 Betweenness Centrality

Figure 9.25 presents the results for the Betweenness Centrality analysis of the Process Innovation Ego Networks.

b)

a)

Figure 9.25: Betweenness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)

Figures 9.25 a) and 9.25 b) present similar distributions with mode zero, which means that most of the nodes of these Social Networks do not have any influence in them, especially the ability to build bridges between pairs of somehow distant nodes. These results are in accordance with what was previously observed in the last two chapters. Figure 9.26 presents the results of an analysis of Betweenness Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

I

c)

b)

a)

II

Figure 9.26: Betweenness Centrality for “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) according to node type

Figures 9.26 I b), 9.26 I c), 9.26 II b) and 9.26 II c) present what was previously seen in other chapters, that Innovation Outcome and Stakeholder nodes do not have the ability to build bridges in the Ego Network social networks. Given this, it is possible to conclude that the distributions presented in Figure 9.25 are almost equal to those of Figures 9.26 I a) and 9.26 II a). Table 9.15 summarises the values presented in Figure 9.26 across the different node types.

Table 9.15: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | ~130 | ~130 | 0 | 0 |
|  | Mean | ~10 | ~23 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Improved Procurement Activities | Maximum | ~131 | ~131 | 0 | 0 |
|  | Mean | ~6 | ~11 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 9.27 presents the impact of Betweenness Centrality in the studied social ego networks: larger nodes indicate a higher Betweenness Centrality.

a)

b)

Figure 9.27: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)

Observing Figure 9.27, it is possible to note that with this centrality metric Activity nodes gain relevance in the network. Table 9.16 shows the five nodes with higher Betweenness centrality for the first two Process Innovation Outcomes (“Reduced Project Implementation Time” and “Improved Procurement Activities” and “Reduced Operational Cost”).

Table 9.16: Five Nodes with Higher Betweenness Centrality for each Process Innovation Outcome

| Betweenness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Project Implementation Time | PM0011 | Activity | Schedule Risk Analysis | Schedule Risk Analysis Workshop 5 |
|  | A4180 | Activity |  | Hot Tap work (Preparation and Execution) |
|  | A4174 | Activity |  | Pipeline laying and testing - 30 " - Field Welding Testing (NDT.RE etc.) |
|  | A4173 | Activity |  | Pipeline laying and testing - 30 " - lowering, Alignment & Fit up |
|  | CC1590F | Activity | Mechanical (Equipment) | Fire water Tanks - Fit Up & alignment (Prefabricated segment) - Level 4 |
| Improved Procurement Activities | PM0011 | Activity | Schedule Risk Analysis | Schedule Risk Analysis Workshop 5 |
|  | PM0008 | Activity | Schedule Risk Analysis | Schedule Risk Analysis Workshop 2 |
|  | PM0009 | Activity | Schedule Risk Analysis | Schedule Risk Analysis Workshop 3 |
|  | PM0010 | Activity | Schedule Risk Analysis | Schedule Risk Analysis Workshop 4 |
|  | PM0007b | Activity | Schedule Risk Analysis | Schedule Risk Analysis Workshop 1 |

### 9.3.4 Closeness Centrality

Following the procedure of the previous section, Figure 9.28 presents the results for the Closeness Centrality analysis of the Process Innovation Ego Networks.

a)

b)

Figure 9.28: Closeness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)

As observed in the previous section, the results of the Closeness Centrality analysis of Ego Network “Reduced Project Implementation Time” are left skewed, which means that most nodes tend to present high values.  In fact, Figure 9.28 a) and b) illustrate that apart from some nodes presenting 0 value of this metric, the others tend to show values around 0.50 or higher. This means that in these two Social Networks, besides the nodes having more connections, they can also provide connections to nodes that belong to other clusters because the nodes are closer to each other. The analysis of Closeness Centrality according to the types of nodes is presented in Figure 9.29.

c)

b)

a)

I

c)

b)

a)

II

Figure 9.29: Closeness Centrality for Innovation Outcome “Reduced Project Implementation Time” (I) and “Improved Procurement Activities” (II) according to node type

Figures 9.29 I b) and 9.29 II b) show that Innovation Outcome nodes are generally distant from every other node in the network since their closeness is zero. It can also be observed that some Activity nodes are peripheral in the network and that some tend to play a central role in it. Besides, Stakeholder nodes seem to present a high closeness centrality. These results are in line with what was observed previously. Table 9.17 summarises the values presented in Figure 9.29 across the different node types.

Table 9.17: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 1 | 1 | 0 | ~0.93 |
|  | Mean | ~0.6 | ~0.51 | 0 | ~0.74 |
|  | Mode | 0 | 0 | 0 | ~0.74 |
|  | Minimum | 0 | 0 | 0 | ~0.42 |
| Improved Procurement Activities | Maximum | 1 | 1 | 0 | 0.9 |
|  | Mean | ~0.57 | ~0.55 | 0 | ~0.68 |
|  | Mode | 0 | 0 | 0 | ~0.55 |
|  | Minimum | 0 | 0 | 0 | ~0.55 |

Figure 9.30 presents the impact of Closeness Centrality in the studied social ego networks: larger nodes indicate a higher Closeness Centrality.

b)

a)

Figure 9.30: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b)

Table 9.18 shows the five nodes with higher Closeness centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”).

Table 9.18: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks

| Closeness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Project Implementation Time | D.03 | Activity |  | Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas |
|  | D.05 | Activity |  | Complete installation of Air Coolers, Inlet Gas Filters, Suction/Interstage K.O. Drums & Pumps along with all auxiliary fa |
|  | D.11 | Activity |  | Achieve MECHANICAL COMPLETION (MC 1) for Train 1 & 2 (NOTE-4) |
|  | E.01 | Activity |  | Complete Commissioning of Tr-1 & 2 Facilities and achieve "Gas-in" to Pipeline Network to meet Consumer demand (NOTE-4) |
|  | PM0008 | Activity | Schedule Risk Analysis | Schedule Risk Analysis Workshop 2 |
| Improved Procurement Activities | D.03 | Activity |  | Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas |
|  | D.05 | Activity |  | Complete installation of Air Coolers, Inlet Gas Filters, Suction/Interstage K.O. Drums & Pumps along with all auxiliary fa |
|  | D.11 | Activity |  | Achieve MECHANICAL COMPLETION (MC 1) for Train 1 & 2 (NOTE-4) |
|  | E.01 | Activity |  | Complete Commissioning of Tr-1 & 2 Facilities and achieve "Gas-in" to Pipeline Network to meet Consumer demand (NOTE-4) |
|  | A32110 | Activity | Precommissioning | Integrated Testing and commissioning of system |

### 9.3.5 Comparison of Centrality Metrics

Figure 9.31 presents an ensemble of the social network metrics that were analysed separately earlier: Degree Centrality, Betweenness Centrality and Closeness Centrality.

b)

a)

Figure 9.31: Ego Networks of Centrality metrics: Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b)

Figure 9.31 a) shows that Activity nodes tend to have a wide range of Betweenness, Closeness and Degree centrality. This shows that for the “Reduced Project Implementation Time” Ego Network, Activity nodes have a wide range of the centrality metrics. This shows that Activity nodes tend to have influence in the network, since some of the values in that wide range are high. The results presented in Figure 9.31 b) are similar to those presented in the same sections of previous chapters. Considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network, the most influential Stakeholder nodes of Innovation Outcome are presented in Table 9.19.

Table 9.19: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time” and “Improved Procurement Activities’ Ego Networks

| Stakeholder Nodes |  |  |  |
| --- | --- | --- | --- |
| Innovation Outcome | Node | Degree | Closeness |
| Reduced Project Implementation Time | SH171 – Foreman-Instrument | 23 | 0.925926 |
|  | SH172 – I&C Technician | 23 | 0.925926 |
|  | SH175 – Helper | 23 | 0.925926 |
|  | SH5 – Sr. Construction Engineer | 52 | 0.906250 |
|  | SH56 – Construction Manager | 51 | 0.892308 |
| Improved Procurement Activities | SH1 – Senior Project Manager/Project Manager | 24 | 0.900000 |
|  | SH55 – Project Manager | 24 | 0.900000 |
|  | SH5 – Sr. Construction Engineer | 23 | 0.870968 |
|  | SH56 – Construction Manager | 23 | 0.870968 |
|  | SH128 – Construction Engineer-Mechanical | 13 | 0.658537 |

In terms of Activities influence on Innovation Outcomes “Reduced Project Implementation Time” and “Improved Procurement Activities”, Table 9.20 presents those which have high Betweenness, high Closeness and high Degree.

Table 9.20: Five Activity nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time” and “Improved Procurement Activities’ Ego Networks

| Activity Nodes |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | WBS Name | Description | Degree | Closeness |
| Reduced Project Implementation Time | Schedule Risk Analysis | Schedule Risk Analysis Workshop 5 | 29 | 0.761905 |
|  |  | Hot Tap work (Preparation and Execution) | 35 | 0.692308 |
|  |  | Pipeline laying and testing - 30 " - Field Welding Testing (NDT.RE etc.) | 34 | 0.565217 |
|  |  | Pipeline laying and testing - 30 " - lowering, Alignment & Fit up | 31 | 0.437500 |
|  | Mechanical (Equipment) | Fire water Tanks - Fit Up & alignment (Prefabricated segment) - Level 4 | 32 | 0.473684 |
| Improved Procurement Activities | Schedule Risk Analysis | Schedule Risk Analysis Workshop 5 | 29 | 0.761905 |
|  | Schedule Risk Analysis | Schedule Risk Analysis Workshop 2 | 25 | 0.928571 |
|  | Schedule Risk Analysis | Schedule Risk Analysis Workshop 3 | 25 | 0.928571 |
|  | Schedule Risk Analysis | Schedule Risk Analysis Workshop 4 | 25 | 0.928571 |
|  | Schedule Risk Analysis | Schedule Risk Analysis Workshop 1 | 19 | 0.875000 |

## Study of Product Innovation Outcomes

### 9.4.1 Product Innovation Outcomes’ Ego Networks.

Table 9.21 presents the general characteristics of the Innovation Outcomes’ Ego Networks.

Table 9.21: Product Innovation Outcomes’ Information

| Innovation Outcome | Label | Description | Total of Nodes | Total of Edges |
| --- | --- | --- | --- | --- |
| 3500 | A | Reduced Production Cost | 76 | 710 |
| 3503 | D | Meets Health and Safety Requirements | 26 | 35 |
| 3509 | I | Achieved Industrial Standards | 136 | 1740 |

Numbers in Table 9.21, indicate that the third Ego Network is the biggest of the three presented. Also, the sizes of the Ego Networks are like those observed in previous chapters.

To further assess the characteristics of these Ego Networks, the plot in Figure 9.32 presents their distribution according to node types.

Figure 9.32: Distribution of Node Types for Product Innovation Outcomes’ Ego Networks

Figure 9.32 shows that Stakeholder nodes tend to constitute the most nodes of the Ego Networks, except for 3509 Ego Network. This means that in terms of Innovation Outcome, Stakeholders play an important role in the Construction Phase. Figure 9.33 presents the Product Innovation Outcomes’ Ego Networks, created with Gephi software. The Fruchterman Reingold layout algorithm was used to improve visualisation.

b)

a)

c)

Figure 9.33: Ego Networks of Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

### 9.4.2 Degree Centrality

Figure 9.34 presents the results for the Degree, In-Degree and Out-Degree Centrality analysis of the Product Innovation Ego Networks.

c)

b)

a)

I

a)

b)

c)

II

c)

b)

a)

III

Figure 9.34: Degree, In-Degree and Out-Degree Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 9.34 shows that most of the distributions are right skewed, meaning that most of the nodes of the Ego Networks have low connectivity. However, focusing on Figure 9.34 I c), an almost centred distribution is observed. This means a significant number of nodes of “Achieved Industrial Standards”’ Ego Network tend to have some connectivity to their peers. This is consistent with the characteristics of a Construction Phase of an EPC in modern days since it is important to meet Industrial Standards as part of quality assurance of the processes. Figure 9.35 presents the results for Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

I

b)

c)

a)

II

c)

b)

a)

III

Figure 9.35: Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

The plots of Figure 9.35 I a) and III a) show that the Activity nodes of these networks present a high connectivity, meaning that the tasks they represent tend to be very interconnected and interdependent. This means that for these Ego Networks, information moves easier among these Activities which might influence the possibility of innovating.

Figure 9.35 II shows that most nodes tend to have few connections in this Ego Network. This is consistent with the numbers presented in Table 9.21. Table 9.22 summarises the values presented in Figure 9.35 across the different node types.

Table 9.22: Degree Centrality relevant values of the Product Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 35 | 35 | 13 | 26 |
|  | Mean | ~19 | ~29 | ~9 | ~14 |
|  | Mode | 7 | 33 | 13 | 7 |
|  | Minimum | 1 | 10 | 1 | 2 |
| Meets Health and Safety Requirements | Maximum | 25 | 25 | 1 | 4 |
|  | Mean | ~3 | ~10 | 1 | ~2 |
|  | Mode | 1 | 5 | 1 | 1 |
|  | Minimum | 1 | 4 | 1 | 1 |
| Achieved Industrial Standards | Maximum | 66 | 46 | 19 | 66 |
|  | Mean | ~26 | ~28 | 10 | ~25 |
|  | Mode | 30 | 30 | 10 | 35 |
|  | Minimum | 1 | 14 | 1 | 2 |

Figure 9.36 presents the impact of Degree Centrality in the studied social ego networks: larger nodes indicate a higher Degree Centrality.

b)

a)

c)

Figure 9.36: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 9.37 shows the results for In-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

c)

b)

I

a)

II

b)

a)

c)

III

Figure 9.37: In-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Once again, Stakeholder nodes do not present any incoming connection as observed in Figures 9.37 I c), 9.37 II c) and 9.37 III c). Focusing on Figure 9.37 III a), it is observed that Activity nodes of the “Achieved Industrial Standards” Ego Network have several incoming connections that are close to 30 per node. This shows that the interconnectivity of this Ego Network is high. Table 9.23 summarises the values presented in Figure 9.37 across the different node types.

Table 9.23: In-Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 32 | 32 | 13 | 0 |
|  | Mean | ~10 | ~26 | ~9 | 0 |
|  | Mode | 0 | 30 | 13 | 0 |
|  | Minimum | 0 | 10 | 1 | 0 |
| Meets Health and Safety Requirements | Maximum | 20 | 20 | 1 | 0 |
|  | Mean | ~2 | ~9 | 1 | 0 |
|  | Mode | 0 | 5 | 1 | 0 |
|  | Minimum | 0 | 4 | 1 | 0 |
| Achieved Industrial Standards | Maximum | 42 | 42 | 19 | 0 |
|  | Mean | ~13 | ~26 | 10 | 0 |
|  | Mode | 0 | 13 | 10 | 0 |
|  | Minimum | 0 | 29 | 1 | 0 |

Figure 9.38 presents the impact of In-Degree Centrality in the studied social ego networks: larger nodes indicate a higher In-Degree Centrality.

a)

b)

c)

Figure 9.38: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

As expected, in this distribution (Figure 9.38) Stakeholder and some Innovation Outcome nodes tend to gain relevance in the networks.  Figure 9.39 shows the results for Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

c)

b)

I

a)

c)

b)

a)

II

III

Figure 9.39: Out-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Figure 9.39 shows that, across all the Innovation Outcomes analysed, every Innovation Outcome node presented an Out-Degree of zero. This is consistent with what was previously observed. Table 9.24 summarises the values presented in Figure 9.39 across the different node types.

Table 9.24: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 26 | 7 | 0 | 26 |
|  | Mean | ~10 | ~3 | 0 | ~14 |
|  | Mode | 7 | 4 | 0 | 7 |
|  | Minimum | 0 | 0 | 0 | 2 |
| Meets Health and Safety Requirements | Maximum | 5 | 5 | 0 | 4 |
|  | Mean | ~2 | 1.25 | 0 | 1.55 |
|  | Mode | 1 | 0 | 0 | 1 |
|  | Minimum | 0 | 0 | 0 | 1 |
| Achieved Industrial Standards | Maximum | 66 | 7 | 0 | 66 |
|  | Mean | ~13 | ~2 | 0 | ~25 |
|  | Mode | 0 | 1 | 0 | 35 |
|  | Minimum | 0 | 0 | 0 | 2 |

Figure 9.40 presents the impact of Out-Degree Centrality in the studied social ego networks: larger nodes indicate a higher Out-Degree Centrality.

c)

b)

a)

Figure 9.40: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

To summarise the conclusions related to the analysis of the Process Innovation Outcomes, Figure 9.41 presents the Degree, In-Degree and Out-Degree metrics in the same plots.

b)

a)

c)

Figure 9.41: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c))

Drawing from Figure 9.41 a) and c), it can be concluded that Activity nodes tend to have high In-Degree values and a significant value of Out-Degree centrality. This is in accordance with what was previously observed in this subsection. Figure 9.41 b) shows that the Ego Network studied is relatively small, but that it presents at least one Activity node with a high In-Degree, Out-Degree and Degree Centrality value. Table 9.25 shows the five nodes with higher Degree, In-Degree and Out-Degree centrality for the three Process Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”).

Table 9.25: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Network

|  | Centrality Metric | Node Description | Type |
| --- | --- | --- | --- |
| Reduced Production Cost | Degree | A4180 – Hot Tap work (Preparation and Execution) | Activity |
|  |  | CC1592 – Fire water Tank - Final Testing (NDT, RT etc.) | Activity |
|  |  | A4174 – Pipeline laying and testing - 30 " - Field Welding Testing (NDT..RE etc.) | Activity |
|  |  | CC1588A – Fire water Tanks - Welding, Testing (NDT, RT etc.) - Baseplate | Activity |
|  |  | CC1590C – Fire water Tanks - Welding, Testing (NDT, RT etc.) - Level 2 | Activity |
|  | In-Degree | CC2320 – All Equipment Installation | Activity |
|  |  | CC1592 – Fire water Tank - Final Testing (NDT, RT etc.) | Activity |
|  |  | CC1588A – Fire water Tanks - Welding, Testing (NDT, RT etc.) - Baseplate | Activity |
|  |  | CC1590A – Fire water Tanks - Welding, Testing (NDT, RT etc.) - Level 1 | Activity |
|  |  | CC1590C – Fire water Tanks - Welding, Testing (NDT, RT etc.) - Level 2 | Activity |
|  | Out-Degree | SH5 – Sr. Construction Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  |  | SH18 – Sr. HSE Engineer | Stakeholder |
|  |  | SH29 – Sr. Engineer, HSE | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
| Meets Health and Safety Requirements | Degree | PM0012 – HSE Management Walk down (Week 25-Week67) | Activity |
|  |  | D.02 – Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas | Activity |
|  |  | D.03 – Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas | Activity |
|  |  | D.01 – Complete foundation works for Compressors and Compressor Shelters for all facilities including Lube Oil Skids, etc. | Activity |
|  |  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  | In-Degree | PM0012 – HSE Management Walk down (Week 25-Week67) | Activity |
|  |  | D.02 – Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas | Activity |
|  |  | D.03 – Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas | Activity |
|  |  | D.01 – Complete foundation works for Compressors and Compressor Shelters for all facilities including Lube Oil Skids, etc. | Activity |
|  |  | H – Stakeholders’ engagement | Innovation Outcome |
|  | Out-Degree | PM0012 – HSE Management Walk down (Week 25-Week67) | Activity |
|  |  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  |  | SH55 – Project Manager | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  |  | SH5 – Sr. Construction Engineer | Stakeholder |
| Achieved Industrial Standards | Degree | SH5 – Sr. Construction Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  |  | SH18 – Sr. HSE Engineer | Stakeholder |
|  |  | SH29 – Sr. Engineer, HSE | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  | In-Degree | CC2130 – All Equipment Installation | Activity |
|  |  | CC2120 – HIPS Installation | Activity |
|  |  | CC2320 – All Equipment Installation | Activity |
|  |  | CC2990 – Mechanical Completion | Activity |
|  |  | CC1592 – Fire water Tank - Final Testing (NDT, RT etc.) | Activity |
|  | Out-Degree | SH5 – Sr. Construction Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  |  | SH18 – Sr. HSE Engineer | Stakeholder |
|  |  | SH29 – Sr. Engineer, HSE | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |

### 9.4.3 Betweenness Centrality

Figure 9.42 presents the results for the Betweenness Centrality analysis of the Product Innovation Ego Networks.

a)

b)

c)

Figure 9.42: Betweenness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

The plots of Figure 9.42 show that the results are consistent with what is expected: a few nodes present a high value of Betweenness Centrality, while most of them have a zero value.

Figure 9.43 presents the results for Betweenness Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

a)

b)

c)

I

a)

b)

c)

b)

a)

c)

II

III

Figure 9.43: Betweenness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

For all the plots of Figure 9.43, Innovation Outcome and Stakeholder nodes do not have a Betweenness Centrality value different from zero, which is consistent with what was observed before. Activity nodes tend to present low Betweenness value in general, but also show some heavy outliers, which are nodes that have high influence in the network.

Table 9.26 summarises the values presented in Figure 9.43 across the different node types.

Table 9.26: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | ~83 | ~83 | 0 | 0 |
|  | Mean | ~9 | ~26 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Meets Health and Safety Requirements | Maximum | 89 | 89 | 0 | 0 |
|  | Mean | ~4 | ~23 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Achieved Industrial Standards | Maximum | ~123 | ~123 | 0 | 0 |
|  | Mean | ~10 | ~20 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 9.44 presents the impact of Betweenness Centrality in the studied social ego networks: larger nodes indicate a higher Betweenness Centrality.

b)

a)

c)

Figure 9.44: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

The images of Figure 9.44 show that Activity nodes gain relevance with this Centrality metric, as was expected. Table 9.27 shows the five nodes with higher Betweenness centrality for the three Product Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”).

Table 9.27: Five Nodes with Higher Betweenness Centrality for each Product Innovation Outcome

| Betweenness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Production Cost | A4180 | Activity | PIPING | Hot Tap work (Preparation and Execution) |
|  | A4174 | Activity | PIPING | Pipeline laying and testing - 30 " - Field Welding Testing (NDT..RE etc.) |
|  | CC1590F | Activity | Mechanical (Equipment) | Fire water Tanks - Fit Up & alignment (Pre-Fabricated segment) - Level 4 |
|  | A4173 | Activity | PIPING | Pipeline laying and testing - 30 " - lowering, Alignment & Fit up |
|  | CC1590D | Activity | Mechanical (Equipment) | Fire water Tanks - Fit Up & alignment (Pre-Fabricated segment) - Level 3 |
| Meets Health and Safety Requirements | PM0012 | Activity | HSE Walk down | HSE Management Walk down (Week 25-Week67) |
|  | D.01 | Activity |  | Complete foundation works for Compressors and Compressor Shelters for all facilities including Lube Oil Skids, etc. |
|  | D.02 | Activity |  | Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas |
|  | D.03 | Activity |  | Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas |
|  | H | Innovation Outcome | Engagement | Stakeholders’ engagement |
| Achieved Industrial Standards | A31720 | Activity |  | Piping Pre-fabrication ( CS 20" and above) |
|  | A4169 | Activity | PIPING | Pipeline laying and testing - 36 " - lowering, Alignment & Fit up |
|  | CC2130 | Activity | Mechanical (Equipment) | All Equipment Installation |
|  | CC2120 | Activity | Mechanical (Equipment) | HIPS Installation |
|  | A4180 | Activity | PIPING | Hot Tap work (Preparation and Execution) |

### 9.4.4 Closeness Centrality

Figure 9.45 presents the results for the Closeness Centrality analysis of the Process Innovation Ego Networks.

c)

b)

a)

Figure 9.45: Closeness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Improved Procurement Activities” (b) and “Achieved Industrial Standards” (c)

Figures 9.45 a) and 9.45 c) present a similar pattern: there is a significant number of nodes with zero Closeness, but the rest of them tend to present a closeness centrality higher than 0.25. These results are consistent with what was previously observed and imply that although there are nodes which do not present a central role in the network, others may have access to a lot of different nodes. Figure 9.46 presents the results for Closeness Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

I

c)

b)

a)

c)

b)

a)

II

III

Figure 9.46: Closeness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Figures 9.46 I b), 9.46 II b) and 9.46 III b) show that Innovation Outcome have zero closeness centrality, like was observed before for the other phases of the EPC Project.

Figures 9.46 I c), 9.46 II c) and 9.46 III c) show that Stakeholders tend to play a central role in the Ego Networks here studied, which is in accordance with their role as managers and supervisors of activities. This also means that they have high visibility of what is going on the Construction Phase of the EPC Project, a situation that enables them to detect opportunities to innovate. Table 9.28 summarises the values presented in Figure 9.46 across the different node types.

Table 9.28: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 1 | 1 | 0 | ~0.88 |
|  | Mean | ~0.62 | ~0.5 | 0 | ~0.74 |
|  | Mode | ~0.67 | 1 | 0 | ~0.67 |
|  | Minimum | 0 | 0 | 0 | ~0.50 |
| Meets Health and Safety Requirements | Maximum | 1 | 1 | 0 | 0.75 |
|  | Mean | ~0.49 | 0.25 | 0 | ~0.59 |
|  | Mode | ~0.55 | 0 | 0 | ~0.54 |
|  | Minimum | 0 | 0 | 0 | ~0.54 |
| Achieved Industrial Standards | Maximum | 1 | 1 | 0 | ~0.95 |
|  | Mean | ~0.58 | ~0.52 | 0 | ~0.67 |
|  | Mode | 0 | 0 | 0 | ~0.79 |
|  | Minimum | 0 | 0 | 0 | ~0.36 |

Figure 9.47 presents the impact of Closeness Centrality in the studied social ego networks: larger nodes indicate a higher Closeness Centrality.

b)

a)

c)

Figure 9.47: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 9.47 shows that Activity nodes, followed by Stakeholder nodes, gain relevance on the presented Networks. Table 9.29 shows the five nodes with higher Closeness centrality for the three Product Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”).

Table 9.29: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks

| Closeness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Production Cost | D.10 | Activity |  | Complete Hydro testing of Pipeline including Drying & Purging between |
|  | A4175 | Activity | Piping | Cold Tie-in at (Preparation and Execution) |
|  | A4180 | Activity | Piping | Hot Tap work (Preparation and Execution) |
|  | CC2320 | Activity | Mechanical (Equipment) | All Equipment Installation |
|  | SH5 | Stakeholder |  | Sr. Construction Engineer |
| Meets Health and Safety Requirements | PM0012 | Activity | HSE Walk down | HSE Management Walk down (Week 25-Week67) |
|  | SH1 | Stakeholder |  | Senior Project Manager/Project Manager |
|  | SH55 | Stakeholder |  | Project Manager |
|  | SH56 | Stakeholder |  | Construction Manager |
|  | SH5 | Stakeholder |  | Sr. Construction Engineer |
| Achieved Industrial Standards | D.10 | Activity |  | Complete Hydro testing of Pipeline including Drying & Purging between |
|  | CC3330 | Activity | Piping | A/G Piping/UG piping (Miscellaneous) |
|  | A4175 | Activity | Piping | Cold Tie-in (Preparation and Execution) |
|  | A4180 | Activity | Piping | Hot Tap work (Preparation and Execution) |
|  | CC2320 | Activity | Mechanical (Equipment) | All Equipment Installation |

### 9.4.5 Comparison of Centrality Metrics

Figure 9.48 presents an ensemble of the social network metrics that were analysed separately earlier: Degree Centrality, Betweenness Centrality and Closeness Centrality.

a)

b)

c)

Figure 9.48: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 9.48 b) shows what was previously observed for the “Meets Health and Safety Requirements” Innovation Outcome: the Ego Network during the Construction Phase is small and apart from one or more Activity nodes, there are few influential nodes in it. On the other hand, Figure 9.48 a) and 9.48 c) present some nodes with high values across the metrics analysed, which means that the chance of existing nodes having high influence is bigger. In both case, there are many Activity nodes which present high values of Degree, Betweenness and Closeness Centrality. Considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network, the most influential Stakeholder nodes of Innovation Outcome “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards” are the ones present in Table 9.30.

Table 9.30: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards’ Ego Networks

| Stakeholder Nodes |  |  |  |
| --- | --- | --- | --- |
| Innovation Outcome | Description | Degree | Closeness |
| Reduced Production Cost | SH5 – Sr. Construction Engineer | 26 | 0.882353 |
|  | SH56 – Construction Manager | 26 | 0.882353 |
|  | SH128 – Construction Engineer-Mechanical | 16 | 0.863636 |
|  | SH133 – TPI-Mechanical | 16 | 0.863636 |
|  | SH18 – Sr. HSE Engineer | 25 | 0.857143 |
| Meets Health and Safety Requirements | SH1 – Senior Project Manager/Project Manager | 4 | 0.750000 |
|  | SH55 – Project Manager | 4 | 0.750000 |
|  | SH56 – Construction Manager | 4 | 0.750000 |
|  | SH5 – Sr. Construction Engineer | 3 | 0.666667 |
|  | SH2 – Sr. Project Engineer | 1 | 0.545455 |
| Achieved Industrial Standards | SH5 – Sr. Construction Engineer | 66 | 0.945946 |
|  | SH56 – Construction Manager | 66 | 0.945946 |
|  | SH18 – Sr. HSE Engineer | 65 | 0.933333 |
|  | SH29 – Sr. Engineer, HSE | 65 | 0.933333 |
|  | SH76 – Sr. QA/QC Engineer | 65 | 0.933333 |

In terms Activities influence on Innovation Outcomes “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”, Table 9.31 presents those which have high Betweenness, high Closeness and high Degree.

Table 9.31: Five Activity nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards’ Ego Networks

| Activity Nodes |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | WBS Name | Description | Degree | Closeness |
| Reduced Production Cost | Piping | Hot Tap work (Preparation and Execution) | 35 | 1.000000 |
|  | Piping | Pipeline laying and testing - 30 " - Field Welding Testing (NDT..RE etc.) | 34 | 0.769231 |
|  | Mechanical (Equipment) | Fire water Tanks - Fit Up & alignment (Prefabricated segment) - Level 4 | 32 | 0.473684 |
|  | Piping | Pipeline laying and testing - 30 " - lowering, Alignment & Fit up | 31 | 0.550000 |
|  | Mechanical (Equipment) | Fire water Tanks - Fit Up & alignment (Prefabricated segment) - Level 3 | 32 | 0.392857 |
| Meets Health and Safety Requirements | HSE Walk down | HSE Management Walk down (Week 25-Week67) | 25 | 1 |
|  |  | Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas | 5 | 0 |
|  |  | Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas | 5 | 0 |
|  |  | Complete foundation works for Compressors and Compressor Shelters for all facilities including Lube Oil Skids, etc. | 4 | 0 |
| Achieved Industrial Standards | Piping | Piping Pre-fabrication (CS 20" and above) | 35 | 0.428571 |
|  | Piping | Pipeline laying and testing - 36 " - lowering, Alignment & Fit up | 29 | 0.433333 |
|  | Mechanical (Equipment) | All Equipment Installation | 43 | 0.384615 |
|  | Mechanical (Equipment) | All Equipment Installation | 46 | 0.538462 |
|  | Piping | Hot Tap work (Preparation and Execution) | 35 | 1.000000 |

## Summary

This chapter performed an analysis of the social network of activities, stakeholders and innovation outcomes of the Construction Phase of the EPC project similar to what was done for the Engineering and Procurement Phases. It was observed that some Activity nodes tend to present a high Betweenness Centrality and that some Stakeholder nodes tend to present a high Closeness Centrality. After an initial overview of the Construction Phase, this chapter presented the detailed analysis for the Innovation Outcomes. This analysis was divided in two sections as it was done in the previous chapters: Process Innovation Outcomes and Product Innovation Outcomes. It was observed that Construction Manager and Sr. Construction Engineer are the stakeholders who present a high influence on Innovation Outcomes.

The next chapter presents findings on all the phases of the EPC project.

# Results - EPC

## Introduction

The previous chapters focused analysis by each of the tree phases of the EPC Project. This chapter studies the whole network, meaning that all the nodes and connections are analysed altogether. As before, the analysis is focused on centrality metrics, namely, Degree centrality, Closeness centrality and Betweenness centrality are studied. The scope of the analysis starts with an overview of the EPC social network and then moves to a detail of Innovation Outcome nodes’ Ego Networks, grouped into Process Innovation and Product Innovation. These Ego Networks have a depth of two, meaning that they are composed by the Innovation Outcome node itself, its neighbours, and its neighbours’ neighbours. For each Ego Network, centrality metrics are computed with the help of Gephi software to find Stakeholders and Activities that influence the corresponding Innovation Outcome.

## EPC Social Network Overview

Figure 10.1 presents the social network composed of the nodes and relationships of the EPC Project. The image was produced with the Gephi software, using the Force Atlas layout algorithm with a repulsion strength of 100, among other visualisation parameters.

Figure 10.1: EPC Project Social Network

Figure 10.1 shows a big Social Network, especially when compared to those studied in the three previous chapters. It is can be observed that while there are some peripheral nodes, most of them seem to be a part of clusters of nodes in the Network. This means that nodes tend to be closer to those which share some characteristics with them. Table 10.1 presents a summary of the EPC social network’s main general characteristics.

Table 10.1: General Characteristics of the EPC Social Network

| Characteristic | Value |
| --- | --- |
| Total of Nodes | 3419 |
| Total of Edges | 42423 |

Table 10.1 shows high numbers of connections between the nodes. The size of this network is in line with what an EPC Project is: an enormous set of tasks interconnected which involve a high number of stakeholders to coordinate the whole project. In this case and as the scope of this study is Innovation, some of the tasks mentioned are Innovation Outcomes. Focusing on the types of nodes that exist in the social network under analysis, Figure 10.2 presents a pie chart illustrating their distribution.

Figure 10.2: Distribution of Node Types in the EPC Social Network

Most of the EPC social network is composed of activities, which represent 94.4% of the total number of nodes. The second largest group is the Stakeholder nodes’ group, which represent almost 5.3% of the whole network, and the smallest group are the Innovation Outcome nodes which represent 0.3% of the total number of nodes. These numbers are consistent with what was mentioned earlier in this chapter that EPC Projects are a set of tasks coordinated by a few stakeholders. Innovation can be generated from all those tasks and the interaction between them, and between them and the stakeholders. However, innovation is typically grouped into major themes which is why there are only a few nodes of the Innovation Outcome type. In summary, the EPC Social Network has 3227 Activity nodes, 182 Stakeholder nodes and 10 Innovation Outcomes nodes.

### EPC Social Network Metrics

Table 10.2 presents relevant metrics for the EPC Social Network.

Table 10.2: Social Network Metrics of the EPC Social Network

| Social Network Metrics | Value |
| --- | --- |
| Network Diameter | 38 |
| Graph Density | 0.004 |
| Average Path Length | 7.817 |
| Average Clustering Coefficient | 0.1 |
| Average Degree | 12.408 |

Table 10.2 shows that the network diameter for this network is 38, which means that one of all the possible node pairs has a shortest path that passes through 38 nodes. From this metric it can be concluded that this is big network. Table 10.2 also shows that the graph density is low, presenting a value of 0.022, which means that although there is already a significant number of edges, the network is far from a complete graph. This is in accordance with the observation made before referring to the high number of edges of this network. In terms of the average path length, the value is around 8. Besides this, Table 10.2 indicates that the average clustering coefficient is of 0.1 and that the average degree of the network is high when compared to the other networks: 12.408.

Table 10.3 presents a summary of the Social Network Metrics observed here and in previous chapters, for comparison.

Table 10.3: Comparison of Social Network Metrics

| Social Network | Network Diameter | Graph Density | Average Path Length | Average Clustering Coefficient | Average Degree |
| --- | --- | --- | --- | --- | --- |
| EPC | 38 | 0.004 | ~7.82 | 0.1 | ~12.4 |
| Engineering | 28 | 0.005 | ~5.33 | 0.095 | ~9.1 |
| Procurement | 8 | 0.006 | ~2.31 | 0.097 | ~6.7 |
| Construction | 16 | 0.022 | ~5 | 0.077 | ~21 |

Table 10.3 shows that the EPC social network is the biggest of the three, which was expected. It also shows that it has the highest clustering coefficient and the highest average degree. In terms of the comparison among the three phases, the Engineering Phase is the social network with highest results across the metrics analysed. This is because the Engineering Phase is a relevant one in an EPC project. Further, it involves a many activities and stakeholders. The second ranking higher in the metrics analysed is the Construction Phase and lastly comes the Procurement phase.

### Degree Centrality

c)

b)

a)

Figure 10.3 presents the results of the analysis of the Degree, In-Degree and Out-Degree Distribution for the EPC social network.

Figure 10.3: Degree a), In-Degree b) and Out-Degree c) Centrality in the EPC Social Network

As before, the Degree, In-Degree and Out-Degree Centrality distributions are right skewed, meaning that most nodes present few links. Focusing on Figures 10.3 a) and 10.3 c), it is observed that there are some heavy outliers in these distributions. In fact, the scale on the x axis shows that there might be nodes with Degree and Out-Degree Centrality values around 1500, which means that there might be nodes connected to 1500 other nodes in the EPC Network. This is quite expected, since one can immediately think of some Stakeholder with a high rank in the EPC project like a Senior Project Manager or a similar role. Due to the existence of the heavy outliers, Figures 10.4 a) and 10.4 b), show the Degree and Out-Degree Centrality distributions excluding nodes with more than 100.

b)

a)

Figure 10.4: Degree a) and Out-Degree b) Centrality in the EPC Social Network for nodes with less than 100 value

Figure 10.4 shows that, excluding the heavy outliers, it is possible to conclude that the majority of the nodes are connected to less than 25 other nodes in the EPC Project and that, in terms of outgoing connections, the majority have 10 or less links. This is in line with what was previously mentioned. Figure 10.5 present the results for Degree, In-Degree and Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

c)

b)

I

a)

c)

b)

II

a)

III

Figure 10.5: Degree (I), In-Degree (II) and Out-Degree Centrality (III) in the EPC Social Network according to node type

Stakeholder nodes present a zero In-Degree value, while Innovation Outcome present the same value but for Out-Degree centrality. This is in accordance with the findings of the previous chapters. Further, in an EPC project Stakeholders tend to be entities which act on Activities and Innovation Outcomes, which means that it is expected for them to have outgoing links. On the other hand, Innovation Outcomes are outcomes which means that they are the goal of the Innovation Process, hence they only present incoming connections. As Activity nodes can be related to Stakeholders, Innovation Outcomes, and other Activities (sets of tasks, for instance), they are the only entities in an EPC Project which can present both outgoing and incoming connections. Table 10.4 summarises the values presented in Figure 10.5 across the different node types and Centrality metrics analysed.

Table 10.4: Degree Centrality relevant values of the EPC Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Centrality Metric | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| DEGREE | Maximum | 1619 | 99 | 125 | 1619 |
|  | Mean | ~25 | ~15 | ~31 | ~205 |
|  | Mode | 8 | 8 | 0 | 1 |
|  | Minimum | 0 | 1 | 0 | 1 |
| IN-DEGREE | Maximum | 125 | 96 | 125 | 0 |
|  | Mean | ~13 | ~13 | ~31 | 0 |
|  | Mode | 6 | 6 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| OUT-DEGREE | Maximum | 1619 | 12 | 0 | 1619 |
|  | Mean | ~13 | ~1.64 | 0 | ~205 |
|  | Mode | 1 | 1 | 0 | 1 |
|  | Minimum | 0 | 0 | 0 | 1 |

Figure 10.6 shows the EPC Social Network affected Degree, In-Degree and Out-Degree: bigger nodes indicate a higher centrality result.

a)

b)

c)

Figure 10.6: Degree a), In-Degree b) and Out-Degree Centrality c) in the EPC Social Network

Figure 10.6 shows that there are some Stakeholder nodes that gain a significant relevance in Degree (a) and Out-Degree (c) distributions. This is consistent with what was observed in the previous chapters. For the In-Degree distribution, Activity and Innovation Outcomes are the ones with bigger sizes.

To summarise the conclusions related to the analysis of the EPC Social Network, Figure 10.7 presents the Degree, In-Degree and Out-Degree metrics in the same plot.

Figure 10.7: EPC Social Network summary of Degree Centrality values

Observing Figure 10.7, it is possible to draw conclusions that were previously pointed that: Stakeholder nodes present a non-zero Out-Degree value and do not present incoming links; Innovation Outcome nodes present only incoming connections; and Activity nodes tend to have a low Out-Degree value but possess both incoming and outgoing connections. Table 10.5 shows the 10 nodes with higher Degree, In-Degree and Out-Degree centrality.

Table 10.5: Ten Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the EPC Social Network

| Centrality Metric | Node Description | Type |
| --- | --- | --- |
| Degree | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  | SH62 – Engineering Manager | Stakeholder |
|  | SH60 – QA/QC Manager | Stakeholder |
|  | SH55 – Project Manager | Stakeholder |
|  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  | SH18 – Sr. HSE Engineer | Stakeholder |
|  | SH28 – Sr. QA/QC Engineer | Stakeholder |
|  | SH56 – Construction Manager | Stakeholder |
|  | SH77 – Sr. Engineer, HSE | Stakeholder |
|  | SH16 – Sr.QA/QC Engineer | Stakeholder |
| In-Degree | J – Achieved industrial standards | Innovation Outcome |
|  | CC2990 – Mechanical Completion | Activity |
|  | CC3070 – Mechanical Completion | Activity |
|  | A31970 – As-built Documentation | Activity |
|  | A29260 – Issue PO | Activity |
|  | CC3260 – Mechanical Completion | Activity |
|  | CC2080 – Mechanical Completion - Substation | Activity |
|  | A29270 – Delivery on Site | Activity |
|  | A29250 – Issue PO | Activity |
|  | A29280 – Delivery on Site | Activity |
| Out-Degree | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  | SH62 – Engineering Manager | Stakeholder |
|  | SH60 – QA/QC Manager | Stakeholder |
|  | SH55 – Project Manager | Stakeholder |
|  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  | SH18 – Sr. HSE Engineer | Stakeholder |
|  | SH28 – Sr. QA/QC Engineer | Stakeholder |
|  | SH56 – Construction Manager | Stakeholder |
|  | SH77 – Sr. Engineer, HSE | Stakeholder |
|  | SH16 – Sr.QA/QC Engineer | Stakeholder |

Table 10.6 shows the 10 nodes with lower Degree, In-Degree and Out-Degree centrality in the EPC Social Network.

Table 10.6: Ten Nodes with Lower Degree, In-Degree and Out-Degree Centrality in the EPC Social Network

| Centrality Metric | Node Description | Type |
| --- | --- | --- |
| Degree | A31280 – Civil Drawing | Activity |
|  | A2000 – Prepare and Issue MR | Activity |
|  | A5780 – Prepare and Issue MR | Activity |
|  | A5800 – Prepare and Issue MR | Activity |
|  | A5840 – Prepare and Issue MR | Activity |
|  | A5860 – Prepare and Issue MR | Activity |
|  | A5960 – Prepare and Issue MR | Activity |
|  | A5940 – Prepare and Issue MR | Activity |
|  | A5900 – Prepare and Issue MR | Activity |
|  | A31311 – Approval and Obtaining the NOC from Municipality & Authorities (Coordination between Siemens & Municipality) | Activity |
| In-Degree | A31240 – Civil Drawing | Activity |
|  | A31260 – Foundation and Civil Drawing | Activity |
|  | A31280 – Civil Drawing | Activity |
|  | A2000 – Prepare and Issue MR | Activity |
|  | A5780 – Prepare and Issue MR | Activity |
|  | A5800 – Prepare and Issue MR | Activity |
|  | A5840 – Prepare and Issue MR | Activity |
|  | A5860 – Prepare and Issue MR | Activity |
|  | A5960 – Prepare and Issue MR | Activity |
|  | A5940 – Prepare and Issue MR | Activity |
| Out-Degree | M1110 – Commissioning Completion all area | Activity |
|  | A11120 – Receive Company Approval | Activity |
|  | A27080 – Receive COMPANY Comments / Approval | Activity |
|  | A28950 – Receive COMPANY Comments / Approval | Activity |
|  | A31970 – As-built Documentation | Activity |
|  | A – Reduced Production Cost | Innovation Outcome |
|  | B – Reduced project implementation time | Innovation Outcome |
|  | D – Meets health and safety requirements | Innovation Outcome |
|  | G – Improved procurement activities | Innovation Outcome |
|  | H – Stakeholders’ engagement | Innovation Outcome |

### Betweenness Centrality

Figure 10.8 shows the results of the Betweenness Centrality distribution for the EPC social network.

Figure 10.8: Betweenness Centrality in the EPC Social Network

The results in Figure 10.8 are consistent with what was previously observed that a small number of nodes present high Betweenness Centrality while the majority do not have the ability to act as bridges in the network.

Due to the heavy outliers in the plot of Figure 10.8, Figure 10.9 improves the visualisation.

Figure 10.9: Betweenness Centrality in the EPC Social Network for nodes with less than 100 value

Proceeding according to the previous sections, Figure 10.10 presents the Betweenness Centrality results according to the types of nodes.

a)

b)

c)

Figure 10.10: Betweenness Centrality in the EPC Social Network according to node type

As was mentioned before, Figure 10.10 shows that Innovation Outcome and Stakeholder nodes have zero Betweenness Centrality which means that the most influencing nodes in terms of bridging information on the EPC social network are the Activity nodes. Table 10.7 presents relevant values of this distribution.

Table 10.7: Betweenness Centrality relevant values of the EPC Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- |
| Maximum | ~49213 | ~49213 | 0 | 0 |
| Mean | ~876 | ~928 | 0 | 0 |
| Mode | 0 | 0 | 0 | 0 |
| Minimum | 0 | 0 | 0 | 0 |

Figure 10.11 shows the EPC Social Network affected by the Betweenness Centrality results: larger nodes indicate a higher Betweenness Centrality.

Figure 10.11: EPC Social Network affected by Betweenness Centrality

Figure 10.11 illustrates that Activity nodes gain relevance in the network, which is consistent with what was analysed before. Table 10.8 shows the 10 nodes with higher Betweenness Centrality in the EPC network for the Activity nodes since the other types of nodes have a zero betweenness value.

Table 10.8: Ten Nodes with Higher Betweenness Centrality in the EPC Social Network

| Betweenness Centrality |  |  |  |
| --- | --- | --- | --- |
| Node | Type | WBS Task Name | Project Activity Description |
| CC2990 | Activity | Mechanical Completion Train 1 | Mechanical Completion |
| A30180 | Activity | Compressor Area | Piling Drawings |
| A29890 | Activity | Instrumentation & Control Balance Documents | Issue as IFC |
| CC3090 | Activity | Compressor Train 1 | Sequence Test |
| CC1010 | Activity | Piling | Piling Works |
| CC3070 | Activity | Mechanical Completion Train 2 | Mechanical Completion |
| CC3150 | Activity | Compressor Train 2 | Sequence Test |
| A29280 | Activity | Miscellaneous (BM) | Delivery on Site |
| A29260 | Activity | Miscellaneous (BM) | Issue PO |
| CC1070 | Activity | Piling | Piling Works |

### Closeness Centrality

Figure 10.12 shows the results of the Closeness Centrality distribution for the EPC social network.

Figure 10.12: Closeness Centrality in the EPC Social Network

As before, most of the nodes have a low closeness, meaning that they are not central to the network, while a few of them tend to have a high closeness value.

a)

c)

b)

The analysis of Closeness Centrality according to the types of nodes is presented in Figure 10.13.

Figure 10.13: Closeness Centrality in the EPC Social Network according to node types

Figure 10.13 shows that Innovation Outcome nodes are generally distant from every other node in the network since their closeness is zero. It also shows that Stakeholder nodes tend to have a higher Closeness Centrality than Activity nodes.

Table 10.9 summarises the relevant values presented across the different node types.

Table 10.9: Closeness Centrality relevant values of the EPC Social Network according to node types (Activity, Innovation Outcome and Stakeholder)

| Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- |
| Maximum | 1 | 1 | 0 | ~0.93 |
| Mean | ~0.17 | ~0.17 | 0 | ~0.31 |
| Mode | 0.5 | 0.5 | 0 | ~0.12 |
| Minimum | 0 | 0 | 0 | ~0.11 |

Figure 10.14 presents the EPC Social Network affected by Closeness Centrality: larger nodes indicate a higher Closeness Centrality.

Figure 10.14: EPC Social Network affected by Closeness Centrality

Figure 10.14 shows that there are Activity nodes with high closeness, which happens because activities are close to each other in terms of a WBS logic and they are also close to Stakeholders. Table 10.10 shows the 10 nodes with higher Closeness Centrality in the EPC network.

Table 10.10: Ten Nodes with Higher Closeness Centrality in the EPC Social Network

| Closeness Centrality |  |  |  |
| --- | --- | --- | --- |
| Node | Type | WBS Task Name | Project Activity Description |
| G1070 | Activity |  | Mechanical Completion - Substation |
| G1080 | Activity |  | Commissioning Completion -Substation |
| G1090 | Activity |  | Mechanical Completion - Compressor Train 1 |
| G1100 | Activity |  | Mechanical Completion - Compressor Train 2 |
| G1110 | Activity |  | Gas In (Compressor Train 1) |
| G1120 | Activity |  | Mechanical Completion - Compressor Train 3 |
| G1130 | Activity |  | Gas In (Compressor Train 2) |
| C.04 | Activity |  | Receive Other Major Electrical Equipment and 33kV cable at site |
| D.11 | Activity |  | Achieve MECHANICAL COMPLETION (MC 1) for Train 1 & 2 (NOTE-4) |
| D.12 | Activity |  | Achieve MECHANICAL COMPLETION (MC 2) for Train 3 (NOTE-4) |

### Comparison of Centrality Metrics

Figure 10.15 presents an ensemble of the EPC social network metrics analysed separately before: Degree Centrality, Betweenness Centrality and Closeness Centrality.

Figure 10.15: EPC Social Network summary of Centrality metrics

Figure 10.15 illustrates that there are many nodes with a Closeness Centrality value around 0.25. Besides this, one notes that Stakeholder nodes only present a positive Closeness Centrality and that in some cases their value is close to 1. In terms of Betweenness Centrality, the plot of Figure 10.15 shows that only Activity nodes present values greater than zero and that in some cases, the Betweenness of those nodes is high. One can therefore conclude that Activity nodes tend to be the most influential in the EPC Project.

## Study of Process Innovation Outcomes

### Process Innovation Outcomes’ Ego Networks

Table 10.11 presents the general characteristics of the Innovation Outcomes’ Ego Networks analysed in this subsection.

Table 10.11: Process Innovation Outcomes’ Information for EPC Project

| Innovation Outcome | Label | Description | Total of Nodes | Total of Edges |
| --- | --- | --- | --- | --- |
| 3501 | B | Reduced Project Implementation Time | 259 | 2661 |
| 3506 | G | Improved Procurement Activities | 108 | 641 |
| 3508 | I | Reduced Operational Cost | 191 | 1607 |

Table 10.11 shows that the Innovation Outcomes’ Ego Networks are relatively balanced in terms of number of nodes, although the 3501 and 3508 Ego Networks present a high number of edges, when compared to the 3606 one.

To further assess the characteristics of these Ego Networks, the plot in Figure 10.16 presents their distribution according to node types.

Figure 10.16: Distribution of Node Types for Process Innovation Outcomes’ Ego Networks

The plot in Figure 10.16 shows that most of the types of nodes are Activity nodes, followed by Stakeholder and lastly Innovation Outcome nodes. The plot also shows that the share of Activity nodes in the “Reduced Operational Cost”’ Ego Network is high and is the biggest of all three. Figure 10.17 presents the Process Innovation Outcomes’ Ego Networks, created with Gephi software. The Fruchterman Reingold layout algorithm was used to improve visualisation.

b)

a)

c)

Figure 10.17: Ego Networks of Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

### Degree Centrality

Figure 10.18 presents the results for the Degree, In-Degree and Out-Degree Centrality analysis of the Process Innovation Ego Networks.

a)

c)

b)

c)

b)

I

a)

b)

a)

II

c)

III

Figure 10.18: Degree (I), In-Degree (II) and Out-Degree Centrality (III) of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figure 10.18 shows, as expected, right skewed distributions, which mean that most of the nodes across all the three Ego Networks present low connectivity (both incoming and outgoing links). Further, Figure 10.18 shows that the Degree, In-Degree and Out-Degree Centrality values are similar across the three Ego Networks, which means that the Ego Networks are comparable in terms of the connectivity of their nodes. Figure 10.19 presents the results for Degree Centrality according to the node type.

b)

c)

a)

c)

b)

a)

I

c)

a)

b)

II

III

Figure 10.19: Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 10.19 shows that typically, Stakeholder nodes have a higher number of links than the number of connections that Activity nodes have. Further, Innovation Outcome nodes tend to have an evenly distributed number of connections, with the third Ego Network presenting nodes of this type with higher connectivity than those of the others.

Table 10.12 summarises the values presented in Figure 10.19 across the different node types.

Table 10.12: Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 61 | 52 | 36 | 61 |
|  | Mean | ~21 | ~20 | ~16 | ~22 |
|  | Mode | 19 | 4 | 36 | 19 |
|  | Minimum | 1 | 1 | 4 | 2 |
| Improved Procurement Activities | Maximum | 46 | 29 | 16 | 46 |
|  | Mean | ~12 | ~11 | ~9.4 | ~14.4 |
|  | Mode | 7 | 7 | 13 | 11 |
|  | Minimum | 2 | 2 | 2 | 2 |
| Reduced Operational Cost | Maximum | 123 | 26 | 50 | 123 |
|  | Mean | ~17 | ~11.5 | ~21 | ~47 |
|  | Mode | 7 | 7 | 6 | 1 |
|  | Minimum | 1 | 2 | 1 | 1 |

Figure 10.20 presents the impact of Degree Centrality in the studied social ego networks: larger nodes indicate a higher Degree Centrality.

b)

a)

c)

Figure 10.20: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

The Ego Networks a) and b) present Activity and Stakeholder nodes with higher relevance, which is in accordance with the analysis presented earlier. Figure 10.21 presents the results for In-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders), for each Ego Network.

c)

a)

b)

I

c)

b)

a)

c)

b)

a)

II

III

Figure 10.21: In-Degree Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

As expected, the behaviour observed in the plots of Figure 10.21 are consistent with what was previously concluded, that Stakeholder nodes do not present incoming connections. The values of In-Degree Centrality for Innovation Outcome nodes are the same with those of their Degree Centrality (observed in Figures 10.19 I b) and 10.19 II b) in not presenting outgoing links.

Focusing on Activity nodes, Figure 10.21 I a) shows that the nodes of the Ego Network “Reduced Project Implementation Time” can present a higher number of links than the same nodes of the other two Ego Networks studied. Table 10.13 summarises the values presented in Figure 10.21 across the different node types.

Table 10.13: In-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 51 | 51 | 36 | 0 |
|  | Mean | ~10.3 | ~18 | ~16 | 0 |
|  | Mode | 0 | 2 | 36 | 0 |
|  | Minimum | 0 | 0 | 4 | 0 |
| Improved Procurement Activities | Maximum | 26 | 26 | 16 | 0 |
|  | Mean | ~6 | ~8.4 | ~9.4 | 0 |
|  | Mode | 0 | 5 | 13 | 0 |
|  | Minimum | 0 | 2 | 2 | 0 |
| Reduced Operational Cost | Maximum | 50 | 26 | 50 | 0 |
|  | Mean | ~8.5 | ~10 | 21 | 0 |
|  | Mode | 0 | 7 | 6 | 0 |
|  | Minimum | 0 | 2 | 1 | 0 |

Figure 10.22 presents the impact of In-Degree Centrality in the studied social ego networks: larger nodes indicate a higher In-Degree Centrality.

b)

a)

c)

Figure 10.22: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figure 10.23 shows the results for Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

b)

a)

c)

a)

b)

c)

I

b)

c)

a)

II

III

Figure 10.23: Out-Degree Centrality for Innovation Outcome ““Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 10.23 shows that across all the Innovation Outcomes analysed, every Innovation Outcome node presented an Out-Degree of zero, which is in accordance with what was previously noticed. Focusing on Figures 10.23 I, 10.23 II and 10.23 III, it can be observed that the outliers of Stakeholder nodes present a higher Out-Degree than Activity nodes. This could mean that those Stakeholder nodes have higher connectivity. Table 10.14 summarises the values presented in Figure 10.23 across the different node types.

Table 10.14: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 61 | 12 | 0 | 61 |
|  | Mean | ~11 | ~3 | 0 | ~22 |
|  | Mode | 0 | 0 | 0 | 19 |
|  | Minimum | 0 | 0 | 0 | 2 |
| Improved Procurement Activities | Maximum | 12 | 12 | 0 | 46 |
|  | Mean | ~6 | ~2.59 | 0 | ~14.4 |
|  | Mode | 0 | 0 | 0 | 2 |
|  | Minimum | 0 | 0 | 0 | 1 |
| Reduced Operational Cost | Maximum | 123 | 12 | 0 | 123 |
|  | Mean | ~9.5 | ~2.2 | 0 | ~47 |
|  | Mode | 1 | 1 | 0 | 1 |
|  | Minimum | 0 | 0 | 0 | 1 |

Figure 10.24 presents the impact of Out-Degree Centrality in the studied social ego networks: larger nodes indicate a higher Out-Degree Centrality.

b)

a)

c)

Figure 10.24: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

To summarise the conclusions related to the analysis of the Process Innovation Outcomes, Figure 10.25 presents the Degree, In-Degree and Out-Degree metrics in the same plots.

b)

a)

c)

Figure 10.25: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c))

Figure 10.25 shows that the Activity nodes of the Innovation Outcome “Reduced Project Implementation Time” present a wide value of In-Degree Centrality and some of them present high values of Out-Degree.

Table 10.15 shows the five nodes with higher Degree, In-Degree and Out-Degree centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”).

Table 10.15: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Networks

|  | Centrality Metric | Node Description | Type |
| --- | --- | --- | --- |
| Reduced Project Implementation Time | Degree | SH5 – Sr. Construction Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  |  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  |  | SH18 – Sr. HSE Engineer | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  | In-Degree | CC2990 – Mechanical Completion | Activity |
|  |  | CC3070 – Mechanical Completion | Activity |
|  |  | CC3260 – Mechanical Completion | Activity |
|  |  | CC1850 – Mechanical Completion - Compressor Station Guard House | Activity |
|  |  | EP1110 – IPF (SIL Review) | Activity |
|  | Out-Degree | SH5 – Sr. Construction Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  |  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  |  | SH18 – Sr. HSE Engineer | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
| Improved Procurement Activities | Degree | SH62 – Engineering Manager | Stakeholder |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH55 – Project Manager | Stakeholder |
|  |  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |
|  | In-Degree | J – Achieved industrial standards | Innovation Outcome |
|  |  | CC2990 – Mechanical Completion | Activity |
|  |  | CC3070 – Mechanical Completion | Activity |
|  |  | CC3260 – Mechanical Completion | Activity |
|  |  | CC2080 – Mechanical Completion - Substation | Activity |
|  | Out-Degree | SH62 – Engineering Manager | Stakeholder |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH55 – Project Manager | Stakeholder |
|  |  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | SH56 – Construction Manager | Stakeholder |

### Betweenness Centrality

Figure 10.26 presents the results for the Betweenness Centrality analysis of the Process Innovation Ego Networks.

c)

b)

a)

Figure 10.26: Betweenness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figures 10.26 a) presents outliers which have higher Betweenness Centrality values than the outliers of the other Ego Networks. This means that Ego Network “Reduced Project Implementation Time” has nodes which are more influential than the ones with higher Betweenness Centrality of the other two Ego Networks. Figure 10.27 presents the results for Betweenness Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

c)

b)

a)

I

II

c)

b)

a)

III

Figure 10.27: Betweenness Centrality for “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figures 10.27 I b), 10.27 I c), 10.27 II b) and 10.27 II c) present what was previously seen in other chapters that Innovation Outcome and Stakeholder nodes do not have the ability to build bridges in the Ego Network social networks. Table 10.16 summarises the values presented in Figure 10.27 across the different node types.

Table 10.16: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | ~523 | ~523 | 0 | 0 |
|  | Mean | ~18.4 | ~32 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Improved Procurement Activities | Maximum | ~130 | ~130 | 0 | 0 |
|  | Mean | ~6.3 | ~9.7 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Reduced Operational Cost | Maximum | ~92.1 | ~92.1 | 0 | 0 |
|  | Mean | ~7.98 | ~9.4 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 10.28 presents the impact of Betweenness Centrality in the studied social ego networks: larger nodes indicate a higher Betweenness Centrality.

c)

b)

a)

Figure 10.28: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Focusing on Figure 10.28, it can be observed that with this centrality metric, Activity nodes gain relevance in the network. Table 10.17 shows the five nodes with higher Betweenness centrality for the first two Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”).

Table 10.17: Five Nodes with Higher Betweenness Centrality for each Process Innovation Outcome

| Betweenness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Project Implementation Time | EP1120 | Activity |  | 90% Model Review |
|  | PM0006b | Activity | Document Review Management | Across the table approval for critical documents |
|  | PM0005b | Activity | Document Review Management | Reduced deliverable review cycle (From 10 to 3 days) |
|  | A29360 | Activity | Process Balance Documents | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in Philosophy ( Successor for Piping Tie-in Schedule & etc.) |
|  | A11060 | Activity | P&ID - Sales Gas Compressor | Issue as IFC |
| Improved Procurement Activities | PM0011 | Activity | Schedule Risk Analysis | Schedule Risk Analysis Workshop 5 |
|  | PM0007b | Activity | Schedule Risk Analysis | Schedule Risk Analysis Workshop 1 |
|  | A14720 | Activity | Specification for Pressure Vessels | Issue as IFC |
|  | A16610 | Activity | Instrument air package Data Sheets (air dry compressor) | Issue as IFC |
|  | PM0007 | Activity | Procurement Management | Allocation of Expeditors at Vendor Manufacturing locations |
| Reduced Operational Cost | A11060 | Activity | P&ID - Sales Gas Compressor | Issue as IFC |
|  | A19410 | Activity | Pipeline Design Basis | Issue as IFC |
|  | A17730 | Activity | Datasheets for Piping Components / SP Items/ Spring Hangers | Issue as IFC |
|  | A14930 | Activity | Mechanical Design Basis -Static Equipment | Issue as IFC |
|  | A11730 | Activity | P&ID - Nitrogen Generation Package | Issue as IFC |

### Closeness Centrality

Figure 10.29 presents the results for the Closeness Centrality analysis of the Process Innovation Ego Networks.

a)

b)

c)

Figure 10.29: Closeness Centrality of Innovation Outcome “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

The results of Closeness Centrality are quite similar across the three Ego Networks, with most of the nodes presenting values of 0 or 1, while the rest sits between 0.50 and 1.

The analysis of Closeness Centrality according to types of nodes is presented in Figure 10.30.

c)

a)

b)

b)

c)

I

a)

a)

c)

b)

II

III

Figure 10.30: Closeness Centrality for Innovation Outcome “Reduced Project Implementation Time” (I), “Improved Procurement Activities” (II) and “Reduced Operational Cost” (III) according to node type

Figure 10.30 I b) and 10.30 II b) show that Innovation Outcome nodes are generally distant from every other node in the network since their closeness is zero. Further, it is observed that some Activity nodes are peripheral in the network and that some of them tend to play a central role in it. This means they might have access to information from other nodes in the network. Table 10.18 summarises the values presented in Figure 10.30 across the different node types.

Table 10.18: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Project Implementation Time | Maximum | 1 | 1 | 0 | ~0.93 |
|  | Mean | ~0.49 | ~0.43 | 0 | ~0.62 |
|  | Mode | 0 | 1 | 0 | ~0.65 |
|  | Minimum | 0 | 0 | 0 | ~0.26 |
| Improved Procurement Activities | Maximum | 1 | 1 | 0 | ~0.86 |
|  | Mean | ~0.53 | ~0.53 | 0 | ~0.64 |
|  | Mode | 0 | 0 | 0 | ~0.66 |
|  | Minimum | 0 | 0 | 0 | ~0.50 |
| Reduced Operational Cost | Maximum | 1 | 1 | 0 | ~0.92 |
|  | Mean | ~0.57 | ~0.57 | 0 | ~0.68 |
|  | Mode | 1 | 1 | 0 | ~0.56 |
|  | Minimum | 0 | 0 | 0 | ~0.42 |

Figure 10.31 presents the impact of Closeness Centrality in the studied social ego networks: larger nodes indicate a higher Closeness Centrality.

b)

a)

c)

Figure 10.31: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Project Implementation Time” (a), “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figure 10.31 shows that Activity and Stakeholder nodes tend to gain relevance with this Distribution. Table 10.19 shows the five nodes with higher Closeness centrality for the three Process Innovation Outcomes (“Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”).

Table 10.19: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks

| Closeness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Project Implementation Time | CC1650 | Activity | Piling Civil and Steel Structure Works | Civil Final works -Pavings, etc.. |
|  | CC1270 | Activity | Substation Building | Civil Final works -Pavings, etc.. |
|  | CC1660 | Activity | Piping | Pipe Pre-fabrication - Lot 1 (CS 20", 6-10") |
|  | D.03 | Activity |  | Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas |
|  | D.05 | Activity |  | Complete installation of Air Coolers, Inlet Gas Filters, Suction/Interstage K.O. Drums & Pumps along with all auxiliary fa |
| Improved Procurement Activities | D.03 | Activity |  | Complete installation of Compressors along with all auxiliary facilities, internals, Lube Oil Skids, VFD Motor, Dry Gas |
|  | D.05 | Activity |  | Complete installation of Air Coolers, Inlet Gas Filters, Suction/Interstage K.O. Drums & Pumps along with all auxiliary fa |
|  | D.11 | Activity |  | Achieve MECHANICAL COMPLETION (MC 1) for Train 1 & 2 (NOTE-4) |
|  | E.01 | Activity |  | Complete Commissioning of Tr-1 & 2 Facilities and achieve "Gas-in" to Pipeline Network to meet Consumer demand (NOTE-4) |
|  | A1360 | Activity | Suction KO drum | Prepare and Issue MR |
| Reduced Operational Cost | A29360 | Activity | Process Balance Documents | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in Philosophy ( Successor for Piping Tie-in Schedule & etc.) |
|  | A1360 | Activity | Suction KO drum | Prepare and Issue MR |
|  | A1480 | Activity | Portable water tank | Prepare and Issue MR |
|  | A11060 | Activity | P&ID - Sales Gas Compressor | Issue as IFC |
|  | A11730 | Activity | P&ID - Nitrogen Generation Package | Issue as IFC |

### 10.3.5 Comparison of Centrality Metrics

Figure 10.32 presents an ensemble of the social network metrics which were analysed separately earlier: Degree Centrality, Betweenness Centrality and Closeness Centrality.

b)

a)

c)

Figure 10.32: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Project Implementation Time” (a) and “Improved Procurement Activities” (b) and “Reduced Operational Cost” (c)

Figure 10.32 a) shows that Activity nodes tend to have a wide range of both Betweenness, Closeness and Degree centrality. Figure 10.32 b) and 10.32 c) points to that there are a significant number of nodes which have a Closeness Centrality value above 0.50.

Considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network, the most influential Stakeholder nodes of Innovation Outcome “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost” are the ones present in Table 10.20.

Table 10.20: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time” and “Improved Procurement Activities’ Ego Networks

| Stakeholder Nodes |  |  |  |
| --- | --- | --- | --- |
| Innovation Outcome | Node | Degree | Closeness |
| Reduced Project Implementation Time | SH171 – Foreman-Instrument | 24 | 0.928571 |
|  | SH172 – I&C Technician | 24 | 0.928571 |
|  | SH175 – Helper | 24 | 0.928571 |
|  | SH78 – Safety Officer, HSE | 43 | 0.877193 |
|  | SH29 – Sr. Engineer, HSE | 47 | 0.861538 |
| Improved Procurement Activities | SH17 – Procurement Engineer | 24 | 0.852941 |
|  | SH72 – Sr. Electrical Engineer | 10 | 0.750000 |
|  | SH55 – Project Manager | 46 | 0.734694 |
|  | SH5 – Sr. Construction Engineer | 24 | 0.725490 |
|  | SH56 – Construction Manager | 24 | 0.725490 |
| Reduced Operational Cost | SH60 – QA/QC Manager | 83 | 0.919192 |
|  | SH16 – Sr.QA/QC Engineer | 30 | 0.875000 |
|  | SH28 – Sr. QA/QC Engineer | 29 | 0.871795 |
|  | SH68 – Engineer, Pipeline | 19 | 0.827586 |
|  | SH73 – Sr. Engineer I&C | 64 | 0.813725 |

In terms Activities influence on Innovation Outcomes “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost”, Table 10.21 presents those which have high Betweenness, high Closeness and high Degree.

Table 10.21: Five Activity nodes with High values of Degree and Closeness in the “Reduced Project Implementation Time”, “Improved Procurement Activities” and “Reduced Operational Cost’s Ego Networks

| Activity Nodes |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | WBS Name | Description | Degree | Closeness |
| Reduced Project Implementation Time |  | 90% Model Review | 45 | 0.761905 |
|  | Document Review Management | Across the table approval for critical documents | 43 | 0.583333 |
|  | Document Review Management | Reduced deliverable review cycle (From 10 to 3 days) | 42 | 0.538462 |
|  | Process Balance Documents | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in Philosophy ( Successor for Piping Tie-in Schedule & etc.) | 44 | 0.454545 |
|  | P&ID - Sales Gas Compressor | Issue as IFC | 22 | 0.565217 |
| Improved Procurement Activities | Schedule Risk Analysis | Schedule Risk Analysis Workshop 5 | 29 | 0.761905 |
|  | Schedule Risk Analysis | Schedule Risk Analysis Workshop 1 | 25 | 0.875000 |
|  | Specification for Pressure Vessels | Issue as IFC | 21 | 1.000000 |
|  | Instrument air package Data Sheets (air dry compressor) | Issue as IFC | 18 | 1.000000 |
|  | Procurement Management | Allocation of Expeditors at Vendor Manufacturing locations | 18 | 1.000000 |
| Reduced Operational Cost | P&ID - Sales Gas Compressor | Issue as IFC | 22 | 1.000000 |
|  | Pipeline Design Basis | Issue as IFC | 21 | 0.923077 |
|  | Datasheets for Piping Components / SP Items/ Spring Hangers | Issue as IFC | 20 | 1.000000 |
|  | Mechanical Design Basis -Static Equipment | Issue as IFC | 20 | 1.000000 |
|  | P&ID - Nitrogen Generation Package | Issue as IFC | 20 | 1.000000 |

## Study of Product Innovation Outcomes

### Product Innovation Outcomes’ Ego Networks

Table 10.22 presents the general characteristics of the Innovation Outcomes’ Ego Networks.

Table 10.22: Product Innovation Outcomes’ Information.

| Innovation Outcome | Label | Description | Total of Nodes | Total of Edges |
| --- | --- | --- | --- | --- |
| 3500 | A | Reduced Production Cost | 244 | 2097 |
| 3503 | D | Meets Health and Safety Requirements | 111 | 602 |
| 3509 | I | Achieved Industrial Standards | 466 | 4789 |

The numbers in Table 10.22 show that the “Achieved Industrial Standards” Ego Network is the biggest of the three presented, both in terms of nodes and of edges. It is followed by “Reduced Production Cost” and then “Meets Health and Safety Requirements”.

To further assess the characteristics of these Ego Networks, the plot in Figure 10.33 presents their distribution according to node types.

Figure 10.33: Distribution of Node Types for Product Innovation Outcomes’ Ego Networks

Figure 10.33 shows that Activity Nodes tend to have the biggest share in the nodes’ distribution for each of the three Innovation Outcomes Ego Networks. Figure 10.34 presents the Product Innovation Outcomes’ Ego Networks, created with Gephi software. The Fruchterman Reingold layout algorithm was used to improve visualisation.

b)

a)

c)

Figure 10.34: Ego Networks of Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

### Degree Centrality

Figure 10.35 presents the results for the Degree, In-Degree and Out-Degree Centrality analysis of the Product Innovation Ego Networks.

c)

b)

a)

c)

b)

a)

I

a)

II

c)

b)

III

Figure 10.35: Degree, In-Degree and Out-Degree Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 10.35 presents similar distributions of the Degree, In-Degree and Out-Degree. Indeed, all distributions are right skewed, meaning that most of the nodes of these Ego Networks present a low connectivity. Figure 10.35 I and 10.35 III shows that these are the two networks with higher values, which is consistent with the high number of edges they present. Figure 10.36 presents the results for Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

a)

b)

c)

c)

a)

b)

I

II

c)

b)

a)

III

Figure 10.36: Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

The plots of Figures 10.36 I b), 10.36 II b) and 10.36 III b) show that Innovation Outcome nodes present similar distributions: basically, there not two nodes with the same number of connections. In terms of the other types of nodes, Figure 10.36 shows that the differences are those which have been pointed out on the analysis of Figure 10.35.

Table 10.23 summarises the values presented in Figure 10.36 across the different node types.

Table 10.23: Degree Centrality relevant values of the Product Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 102 | 36 | 63 | 102 |
|  | Mean | ~17.2 | ~13.2 | ~26.7 | ~27.3 |
|  | Mode | 8 | 8 | 16 | 7 |
|  | Minimum | 1 | 1 | 2 | 2 |
| Meets Health and Safety Requirements | Maximum | 50 | 50 | 16 | 32 |
|  | Mean | ~10.9 | ~15.1 | 7 | ~8.3 |
|  | Mode | 3 | 14 | 3 | 3 |
|  | Minimum | 1 | 2 | 1 | 1 |
| Achieved Industrial Standards | Maximum | 210 | 50 | 125 | 210 |
|  | Mean | ~20.6 | ~14.7 | ~32 | ~38.9 |
|  | Mode | 6 | 6 | 13 | 35 |
|  | Minimum | 1 | 2 | 3 | 1 |

Figure 10.37 presents the impact of Degree Centrality in the studied social ego networks: larger nodes indicate a higher Degree Centrality.

b)

a)

c)

Figure 10.37: Ego Network affected by Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 10.38 shows the results for In-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

I

c)

b)

a)

a)

c)

b)

II

III

Figure 10.38: In-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Once again, Stakeholder nodes do not present any incoming connection, as it is possible to observe in Figures 10.38 I c), 10.38 II c) and 10.38 III c). Table 10.24 summarises the values presented in Figure 10.38 across the different node types.

Table 10.24: In-Degree Centrality relevant values of the Process Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 63 | 32 | 63 | 0 |
|  | Mean | ~8.6 | ~11.2 | ~26.7 | 0 |
|  | Mode | 0 | 7 | 16 | 0 |
|  | Minimum | 0 | 0 | 2 | 0 |
| Meets Health and Safety Requirements | Maximum | 46 | 46 | 16 | 0 |
|  | Mean | ~5.43 | ~13.2 | 7 | 0 |
|  | Mode | 0 | 10 | 3 | 0 |
|  | Minimum | 0 | 2 | 1 | 0 |
| Achieved Industrial Standards | Maximum | 125 | 46 | 125 | 0 |
|  | Mean | ~10.3 | ~13 | ~31.9 | 0 |
|  | Mode | 0 | 7 | 13 | 0 |
|  | Minimum | 0 | 1 | 3 | 0 |

Figure 10.39 presents the impact of In-Degree Centrality in the studied social ego networks: larger nodes indicate a higher In-Degree Centrality.

b)

a)

c)

Figure 10.39: Ego Network affected by In-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

As expected, it is observed that with this distribution, Stakeholder and some Innovation Outcome nodes tend to gain relevance in the networks of Figure 10.39. Figure 10.40 shows the results for Out-Degree Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

a)

b)

b)

c)

I

a)

a)

b)

II

c)

III

Figure 10.40: Out-Degree Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Figure 10.40 shows that, across all the Innovation Outcomes analysed, every Innovation Outcome node presented an Out-Degree of zero. This comes in line with what was previously observed. It also shows that Activity nodes tend to have low Out-Degree values. Table 10.25 summarises the values presented in Figure 10.40 across the different node types.

Table 10.25: Out-Degree Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 102 | 12 | 0 | 102 |
|  | Mean | ~8.6 | ~2.1 | 0 | ~27.3 |
|  | Mode | 1 | 1 | 0 | 7 |
|  | Minimum | 0 | 0 | 0 | 2 |
| Meets Health and Safety Requirements | Maximum | 32 | 12 | 0 | 32 |
|  | Mean | ~5,43 | ~1.84 | 0 | ~8.3 |
|  | Mode | 0 | 0 | 0 | 3 |
|  | Minimum | 0 | 0 | 0 | 1 |
| Achieved Industrial Standards | Maximum | 210 | 12 | 0 | 210 |
|  | Mean | ~10.3 | ~1.7 | 0 | ~39 |
|  | Mode | 0 | 0 | 0 | 35 |
|  | Minimum | 0 | 0 | 0 | 1 |

Figure 10.41 presents the impact of Out-Degree Centrality in the studied social ego networks: larger nodes indicate a higher Out-Degree Centrality.

b)

a)

c)

Figure 10.41: Ego Networks affected by Out-Degree Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

To summarise the conclusions related to the analysis of the Process Innovation Outcomes, Figure 10.42 presents the Degree, In-Degree and Out-Degree metrics in the same plots.

b)

a)

c)

Figure 10.42: Process Innovation Outcomes Ego Networks summary of Degree Centrality values (“Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c))

Observing Figure 10.42 a) and c), one can conclude that Activity nodes tend to have high In-Degree values and a significant value of Out-Degree centrality. On the other hand, Activity nodes in Figure 10.42 c) tend to present low values of Out-Degree value. This is in accordance with what was previously observed in this subsection.

Table 10.26 shows the five nodes with higher Degree, In-Degree and Out-Degree centrality for the three Process Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”).

Table 10.26: Five Nodes with Higher Degree, In-Degree and Out-Degree Centrality in the Product Innovation Outcomes’ Ego Network

|  | Centrality Metric | Node Description | Type |
| --- | --- | --- | --- |
| Reduced Production Cost | Degree | SH62 – Engineering Manager | Stakeholder |
|  |  | SH55 – Project Manager | Stakeholder |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH63 – Sr. Process Engineer | Stakeholder |
|  |  | SH15 – Sr.Piping & Pipeline Engineer | Stakeholder |
|  | In-Degree | J – Achieved industrial standards | Innovation Outcome |
|  |  | A – Reduced Production Cost | Innovation Outcome |
|  |  | CC2320 – All Equipment Installation | Activity |
|  |  | CC1592 – Fire water Tank - Final Testing (NDT, RT etc.) | Activity |
|  |  | A4180 – Hot Tap work (Preparation and Execution) | Activity |
|  | Out-Degree | SH62 – Engineering Manager | Stakeholder |
|  |  | SH55 – Project Manager | Stakeholder |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH63 – Sr. Process Engineer | Stakeholder |
|  |  | SH15 – Sr.Piping & Pipeline Engineer | Stakeholder |
| Meets Health and Safety Requirements | Degree | EP1110 – IPF (SIL Review) | Activity |
|  |  | EP1120 – 90% Model Review | Activity |
|  |  | EP1100 – 60% Model Review | Activity |
|  |  | CC1850 – Mechanical Completion - Compressor Station Guard House | Activity |
|  |  | G1050 – 30% Model Review | Activity |
|  | In-Degree | EP1110 – IPF (SIL Review) | Activity |
|  |  | CC1850 – Mechanical Completion - Compressor Station Guard House | Activity |
|  |  | EP1100 – 60% Model Review | Activity |
|  |  | EP1120 – 90% Model Review | Activity |
|  |  | CC1800 – Mechanical Completion - Control Room | Activity |
|  | Out-Degree | SH55 – Project Manager | Stakeholder |
|  |  | SH18 – Sr. HSE Engineer | Stakeholder |
|  |  | SH62 – Engineering Manager | Stakeholder |
|  |  | SH1 – Senior Project Manager/Project Manager | Stakeholder |
|  |  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
| Achieved Industrial Standards | Degree | SH55 – Project Manager | Stakeholder |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  |  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | SH62 – Engineering Manager | Stakeholder |
|  | In-Degree | J – Achieved industrial standards | Innovation Outcome |
|  |  | EP1110 – IPF (SIL Review) | Activity |
|  |  | CC2990 – Mechanical Completion | Activity |
|  |  | CC2120 – HIPS Installation | Activity |
|  |  | CC2550 – Mechanical Completion - Custody Transfer Area | Activity |
|  | Out-Degree | SH55 – Project Manager | Stakeholder |
|  |  | SH60 – QA/QC Manager | Stakeholder |
|  |  | SH76 – Sr. QA/QC Engineer | Stakeholder |
|  |  | SH59 – Cost Control Manager/Procurement Engineer | Stakeholder |
|  |  | SH62 – Engineering Manager | Stakeholder |

### Betweenness Centrality

a)

c)

b)

Figure 10.43 presents the results for the Betweenness Centrality analysis of the Product Innovation Ego Networks.

Figure 10.43: Betweenness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

The plots of Figure 10.43 show that the results are consistent with what is expected, that is a few nodes with a high value of Betweenness Centrality, while most of them have a zero value.

Figure 10.44 presents the results for Betweenness Centrality according to the node types (Activities, Innovation Outcomes and Stakeholders).

c)

b)

a)

b)

I

c)

a)

c)

b)

II

a)

III

Figure 10.44: Betweenness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

For all the plots of Figure 10.44, Innovation Outcome and Stakeholder nodes do not have a Betweenness Centrality value above zero, which is in line with what was observed before. Activity nodes tend to present low Betweenness value in general, some have high influence in the network. Table 10.27 summarises the values presented in Figure 10.44 across the different node types.

Table 10.27: Betweenness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | ~90.3 | ~90.3 | 0 | 0 |
|  | Mean | ~8.4 | ~11.73 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Meets Health and Safety Requirements | Maximum | ~447.3 | ~447.3 | 0 | 0 |
|  | Mean | ~13.2 | ~33.9 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |
| Achieved Industrial Standards | Maximum | ~713.8 | ~713.8 | 0 | 0 |
|  | Mean | ~19.5 | ~25.8 | 0 | 0 |
|  | Mode | 0 | 0 | 0 | 0 |
|  | Minimum | 0 | 0 | 0 | 0 |

Figure 10.45 presents the impact of Betweenness Centrality in the studied social ego networks: larger nodes indicate a higher Betweenness Centrality.

b)

a)

c)

Figure 10.45: Ego Networks affected by Betweenness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 10.45 show that Activity nodes gain relevance with the Centrality metric. Table 10.28 shows the five nodes with higher Betweenness centrality for the three Product Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”).

Table 10.28: Five Nodes with Higher Betweenness Centrality for each Product Innovation Outcome

| Betweenness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Production Cost | A1340 | Activity | Discharged Cooler | Prepare and Issue MR |
|  | A4180 | Activity | Piping | Hot Tap work (Preparation and Execution) |
|  | A19410 | Activity | Pipeline Design Basis | Issue as IFC |
|  | A1350 | Activity | Discharged Cooler | Issue PO |
|  | A4174 | Activity | Piping | Pipeline laying and testing - 30 " - Field Welding Testing (NDT..RE etc.) |
| Meets Health and Safety Requirements | EP1120 | Activity |  | 90% Model Review |
|  | EP1110 | Activity |  | IPF (SIL Review) |
|  | EP1100 | Activity |  | 60% Model Review |
|  | G1050 | Activity |  | 30% Model Review |
|  | PM0012 | Activity |  | 30% Model Review |
| Achieved Industrial Standards | EP1120 | Activity |  | 90% Model Review |
|  | CC1660 | Activity |  | Pipe Pre-fabrication - Lot 1 (CS 20", 6-10") |
|  | EP1110 | Activity |  | IPF (SIL Review) |
|  | A31720 | Activity | Piping | Piping Pre-fabrication (CS 20" and above) |
|  | EP1100 | Activity |  | 60% Model Review |

### Closeness Centrality

Figure 10.46 presents the results for the Closeness Centrality analysis of the Process Innovation Ego Networks.

a)

b)

c)

Figure 10.46: Closeness Centrality of Innovation Outcome “Reduced Production Cost” (a), “Improved Procurement Activities” (b) and “Achieved Industrial Standards” (c)

The plots in Figure 10.46 present a similar pattern: there is a significant number of nodes with zero Closeness, but the rest of them tend to present a closeness centrality higher than 0.25. These results are in line with what was previously observed.

Figure 10.47 presents the results for Closeness Centrality according to the node type.

a)

b)

c)

I

c)

b)

a)

II

c)

b)

a)

III

Figure 10.47: Closeness Centrality for Innovation Outcome “Reduced Production Cost” (I), “Meets Health and Safety Requirements” (II) and “Achieved Industrial Standards” (III) according to node type

Figures 10.47 I b), 10.47 II b) and 10.47 III b) show that Innovation Outcome have zero closeness centrality, like was observed before for the other phases of the EPC Project.

Figures 10.47 I c), 10.47 II c) and 10.47 III c) show that Stakeholders tend to play a central role in the Ego Networks here studied, which is in accordance with what was previously observed. Table 10.29 summarises the values presented in Figure 10.47 across the different node types.

Table 10.29: Closeness Centrality relevant values of the Innovation Outcomes’ Ego Networks, according to node types (Activity, Innovation Outcome and Stakeholder)

| Innovation Outcome | Metric | Global | Activities | Innovation Outcomes | Stakeholders |
| --- | --- | --- | --- | --- | --- |
| Reduced Production Cost | Maximum | 1 | 1 | 0 | ~0.91 |
|  | Mean | ~0.59 | ~0.56 | 0 | ~0.72 |
|  | Mode | 1 | 1 | 0 | ~0.67 |
|  | Minimum | 0 | 0 | 0 | ~0.44 |
| Meets Health and Safety Requirements | Maximum | 1 | 1 | 0 | ~0.86 |
|  | Mean | ~0.50 | ~0.44 | 0 | ~0.55 |
|  | Mode | 0 | 0 | 0 | ~0.53 |
|  | Minimum | 0 | 0 | 0 | ~0.32 |
| Achieved Industrial Standards | Maximum | 1 | 1 | 0 | ~0.97 |
|  | Mean | ~0.53 | ~0.52 | 0 | ~0.58 |
|  | Mode | 0 | 0 | 0 | ~0.79 |
|  | Minimum | 0 | 0 | 0 | ~0.22 |

Figure 10.48 presents the impact of Closeness Centrality in the studied social ego networks: larger nodes indicate a higher Closeness Centrality.

a)

b)

c)

Figure 10.48: Ego Networks affected by Closeness Centrality for Innovation Outcomes “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 10.48 shows that Activity nodes gain relevance on the Networks presented and that they are followed by Stakeholder nodes. Table 10.30 shows the five nodes with higher Closeness centrality for the three Product Innovation Outcomes (“Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”).

Table 10.30: Five Nodes with Higher Closeness Centrality for this Innovation Outcomes’ Ego Networks

| Closeness Centrality |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | Node | Type | WBS Task Name | Project Activity Description |
| Reduced Production Cost | B.02 | Activity |  | Issue Purchase Orders for Air Coolers, Metering Skid Package and K.O Drums (NOTE-3) |
|  | D.10 | Activity |  | Complete Hydro testing of Pipeline including Drying & Purging |
|  | A29360 | Activity | Process Balance Documents | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) 7) Tie-in Philosophy ( Successor for Piping Tie-in Schedule & etc.) |
|  | A1360 | Activity | Suction KO drum | Prepare and Issue MR |
|  | A1480 | Activity | Portable water tank | Prepare and Issue MR |
| Meets Health and Safety Requirements | A.01 | Activity |  | Complete HAZOP / SIL Reviews for all facilities and submit Reports - ICR |
|  | CC1650 | Activity | Piling Civil and Steel Structure Works | Civil Final works -Pavings, etc.. |
|  | CC1660 | Activity | Piping | Pipe Pre-fabrication - Lot 1 ( CS 20", 6-10") |
|  | CC1730 | Activity | Piping | Pipe Pre-fabrication - Lot 1 ( CS 20", 6-10") |
|  | A.02 | Activity | Piping | Pipe Pre-fabrication - Lot 1 ( CS 20", 6-10") |
| Achieved Industrial Standards | A.01 | Activity |  | Complete HAZOP / SIL Reviews for all facilities and submit Reports - ICR |
|  | D.10 | Activity |  | Complete Hydro testing of Pipeline including Drying & Purging |
|  | A1360 | Activity | Suction KO drum | Prepare and Issue MR |
|  | A1420 | Activity | Flare package | Prepare and Issue MR |
|  | A1480 | Activity | Portable water tank | Prepare and Issue MR |

### Comparison of Centrality Metrics

Figure 10.49 presents an ensemble of the social network metrics that were analysed separately earlier: Degree Centrality, Betweenness Centrality and Closeness Centrality.

a)

b)

c)

Figure 10.49: Ego Networks summary of Centrality metrics: Innovation Outcome “Reduced Production Cost” (a), “Meets Health and Safety Requirements” (b) and “Achieved Industrial Standards” (c)

Figure 10.49 shows that most of the nodes across all the three Ego Networks present a Closeness Centrality higher than 0.25. Also, across all three Innovation Outcomes, there are some Activity nodes which present high value for the three centrality metrics analysed. Considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network, the most influential Stakeholder nodes of Innovation Outcome “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards” are the ones present in Table 10.31.

Table 10.31: Five Stakeholder nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards’ Ego Networks

| Stakeholder Nodes |  |  |  |
| --- | --- | --- | --- |
| Innovation Outcome | Description | Degree | Closeness |
| Reduced Production Cost | SH76 – Sr. QA/QC Engineer | 64 | 0.910256 |
|  | SH55 – Project Manager | 95 | 0.892562 |
|  | SH60 – QA/QC Manager | 93 | 0.890756 |
|  | SH5 – Sr. Construction Engineer | 27 | 0.885714 |
|  | SH56 – Construction Manager | 27 | 0.885714 |
| Meets Health and Safety Requirements | SH70 – Civil Engineer | 10 | 0.857143 |
|  | SH126 – Subcontractor-F&G | 10 | 0.857143 |
|  | SH55 – Project Manager | 32 | 0.762712 |
|  | SH18 – Sr. HSE Engineer | 27 | 0.728814 |
|  | SH78 – Safety Officer, HSE | 9 | 0.714286 |
| Achieved Industrial Standards | SH76 – Sr. QA/QC Engineer | 188 | 0.965347 |
|  | SH17 – Procurement Engineer | 70 | 0.948718 |
|  | SH78 – Safety Officer, HSE | 65 | 0.933333 |
|  | SH29 – Sr. Engineer, HSE | 70 | 0.916667 |
|  | SH77 – Sr. Engineer, HSE | 68 | 0.895349 |

In terms Activities influence on Innovation Outcomes “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”, Table 10.32 presents those which have high Betweenness, high Closeness and high Degree.

Table 10.32: Five Activity nodes with High values of Degree and Closeness in the “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards’ Ego Networks

| Activity Nodes |  |  |  |  |
| --- | --- | --- | --- | --- |
| Innovation Outcome | WBS Name | Description | Degree | Closeness |
| Reduced Production Cost | Discharged Cooler | Prepare and Issue MR | 15 | 0.600000 |
|  | Piping | Hot Tap work (Preparation and Execution) | 36 | 1.000000 |
|  | Pipeline Design Basis | Issue as IFC | 21 | 0.923077 |
|  | Pipeline Design Basis | Issue as IFC | 11 | 1.000000 |
|  | Piping | Pipeline laying and testing - 30 " - Field Welding Testing (NDT..RE etc.) | 34 | 0.769231 |
| Meets Health and Safety Requirements |  | 90% Model Review | 45 | 0.928571 |
|  |  | IPF (SIL Review) | 50 | 0.435897 |
|  |  | 60% Model Review | 38 | 0.560000 |
|  |  | 30% Model Review | 33 | 0.405405 |
|  | HSE Walk down | HSE Management Walk down (Week 25-Week67) | 25 | 1.000000 |
| Achieved Industrial Standards |  | 90% Model Review | 38 | 0.377358 |
|  | Piping | Pipe Pre-fabrication - Lot 1 (CS 20", 6-10") | 33 | 0.355556 |
|  | Piping | IPF (SIL Review) | 50 | 0.260870 |
|  | Piping | Piping Pre-fabrication (CS 20" and above) | 37 | 0.428571 |
|  |  | 60% Model Review | 37 | 0.295775 |

## Results Triangulation

According to Saunders et al. (2012), it is common in recent studies to perform Triangulation. The term triangulation indicates the use of primary and secondary data and it is used to increase the credibility and validity of research findings Cohen et al. (2017). Triangulation study was performed to understand the level of agreement among project stakeholders of the social network study findings. Since the study objective is to explore the influence of project stakeholders in an EPC project environment, it was therefore chosen as the most appropriate setting to perform the triangulation study.

In order to validate the data, the researcher decided to distribute Questionnaire Survey to a wider population of project stakeholders (project alpha). The survey was circulated to more than 300 persons and the feedback was received from 63 people at a response rate of 21%.  While Bennett and Nair (2010) indicated that a response rate of 30% is considered reliable, Walstrom and Wilson (1997) confirmed in their research that a response of 14.4% is acceptable to obtain reliable data from certain population.

The outcome of this study, exploring the influence of stakeholders on process and product innovation in EPC projects, was produced in two parts. The first part objective was to explore the level of influence on process innovation, while the second part was to explore the level of influence on product innovation.

The six innovation outcomes identified in the literature were selected to form the study questionnaire. Whereas the first three questions were related to stakeholders impact on process innovation outcomes (reduction of the project duration, improving the procurement activities and reducing the project cost), the last three questions were related to stakeholders impact on product innovation outcomes (reducing production cost, complying with health and safety requirements and achieving the industrial standards). The results for the stakeholders’ impact were averaged and ranked as shown in Figure 10.50.

The analysis of Process Innovation Outcomes and Product Innovation Outcomes show that Project Manager and Sr. QA/QC Engineer are the stakeholders that contribute most towards Product Innovation Outcomes while Project manager and Engineering Manager contribute most towards Process Innovation outcomes.  The Triangulation study performed to identify the biggest contributors on Process and Product Innovation during the entire EPC duration also ranked Project Manager and Sr. QA/QC Engineer as the highest contributing stakeholders on Product Innovation Outcomes. Project Manager and Engineering Manager were confirmed as most contributing stakeholders on Process Innovation Outcomes (Figure 10.50).

Therefore, the outcome of this activity validates to a great extent the findings of the social network analysis study.

Figure 10.50 Stakeholders ranked highest in terms of contribution to Product and Process Innovation

## Summary

In this chapter, an analysis of the social network of Activities, Stakeholders and Innovation Outcomes of the EPC project was performed using the same format used for Engineering, Procurement and Construction Phases. It was observed that some Activity nodes tend to present a high Betweenness Centrality and that some Stakeholder nodes tend to present a high Closeness Centrality. After an initial overview of the EPC Social Network, this chapter presented the detailed analysis for the Innovation Outcomes. This analysis was divided in two sections, Process Innovation Outcomes and Product Innovation Outcomes, as was done in previous chapters. It was observed that Project Manager and Sr. QA/QC Engineer are the stakeholders that present a high influence on Innovation Outcomes. Results from the quantitative survey confirmed Project manager and Sr. QA/QC Engineer as the highest  ranked stakeholders influencing innovation outcomes.

# Discussion

## Introduction

This chapter presents a discussion of the main research questions addressed in this thesis. Throughout the following sections, a discussion on the findings and an interpretation of the results of the previous chapter will be addressed. Each of the seven research questions will have a dedicated section. Given the fact that the analysis on the Innovation Outcomes was grouped into Product and Process Innovation, there will be similar sections in this chapter, each for the explanation of each group’s results.

## Research Question 1

“Who are the most influential stakeholders on process innovation in EPC project during the entire project as well as each phase of the project?”

The first research question focuses on identifying the most influential stakeholders on process innovation. This identification was previously performed based on different Social Network Analysis metrics across four different chapters: one regarding the Social Network formed by the Activities, Innovation Outcomes and Stakeholders of the Engineering Phase, the Procurement Phase, the Construction Phase and finally the whole EPC Project.

Of the three metrics calculated for all the nodes of all the Innovation Outcomes’ Ego Networks and of the EPC Social Network two, namely Degree Centrality and Closeness Centrality, allowed the identification of the most influential Stakeholders. This is because Stakeholder nodes do not present a value of Betweenness Centrality higher than zero. This occurs because in this EPC project, Stakeholders typically interact with Activity or Innovation Outcome nodes as a way of starting information flow that ends in Innovation. For instance, in the Engineering Phase Ego Network of Product Innovation Outcome “Reduced Production Cost”, Stakeholder SH68 (“Engineer, Pipeline”) interacts directly with Activity Node A20390 (“Data Sheet for pipeline Manual valve - Issue as IFC”) which can generate Innovation. In other words, the Stakeholder is always someone who initiates the information flow and interaction which can result in Innovation. This means that these types of nodes cannot play the role of bridges in any social network of this EPC Project. This means that the Betweenness Centrality is always zero for Stakeholder nodes. This was widely seen for the analysis in the Engineering Phase, Procurement Phase, Construction Phase and EPC Analysis’ chapters.

With Betweenness Centrality excluded to measure influence, two other metrics left are Degree and Closeness Centrality. The first, as explained before, is the number of connections between a certain node and the other nodes in the Social Network, which can then be divided into In-Degree Centrality (incoming links) and Out-Degree Centrality (outgoing connections). The second measures the way in which a node is central in the network, meaning that a high value of Closeness Centrality implies a high capability of accessing information as processes tend to flow through the node. Based on these two metrics, a simple ranking was built considering that Degree Centrality played a more important role on it since Ego Networks tend to be small in terms of number of nodes. In that regard, the more connections a Stakeholder presents, the more influence it can present. Closeness Centrality can also play an important role as it can be associated with the quality of Innovation created since it can be generated with a clearer view of flow of information on the network.

### Most Influential Stakeholders on Process Innovation in the Engineering Phase

Focusing on the Engineering Phase, the results on Table 7.22 were expanded on Table 11.1. This table presents the Top 10 most influential Stakeholders, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Stakeholders was based on the average value that each Stakeholder node presented across the three Ego Networks of Process Innovation of the Engineering Phase.

Table 11.1: Top Ten Most Influential Stakeholders on Process Innovation in the Engineering Phase

| Node | Reduced Project Implementation Time |  | Improved Procurement Activities |  | Reduced Operational Cost |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| SH62 | 54 | 0.92 | 12 | 0.8 | 121 | 0.96 | 62 | 0.89 |
| SH63 | 53 | 0.91 | 7 | 0.73 | 108 | 0.93 | 56 | 0.86 |
| SH67 | 38 | 0.88 | 6 | 0.69 | 82 | 0.93 | 42 | 0.83 |
| SH73 | 32 | 0.80 | 7 | 0.73 | 64 | 0.87 | 34 | 0.80 |
| SH65 | 30 | 0.75 | 7 | 0.73 | 66 | 0.79 | 34 | 0.76 |
| SH72 | 29 | 0.76 | 10 | 0.78 | 51 | 0.82 | 30 | 0.79 |
| SH15 | 10 | 0.47 | - | - | 45 | 0.55 | 27.5 | 0.51 |
| SH55 | 16 | 0.57 | 8 | 0.75 | 56 | 0.77 | 26 | 0.70 |
| SH64 | 30 | 0.77 | 3 | 0.64 | 45 | 0.8 | 26 | 0.73 |
| SH60 | 13 | 0.76 | 8 | 0.75 | 54 | 0.94 | 25 | 0.82 |

Table 11.1 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.2 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.2: Top Ten Most Influential Stakeholders on Process Innovation in the Engineering Phase - Summary

| Stakeholder Nodes |  | Average Values |  |
| --- | --- | --- | --- |
| Label | Description | Degree Centrality | Closeness Centrality |
| SH62 | Engineering Manager | 62 | 0.89 |
| SH63 | Sr. Process Engineer | 56 | 0.86 |
| SH67 | Senior Engineer, Piping | 42 | 0.83 |
| SH73 | Sr. Engineer I&C | 34 | 0.80 |
| SH65 | Senior Engineer, Static Equipment | 34 | 0.76 |
| SH72 | Sr. Electrical Engineer | 30 | 0.79 |
| SH15 | Sr.Piping & Pipeline Engineer | 27.5 | 0.51 |
| SH55 | Project Manager | 26 | 0.70 |
| SH64 | Senior Engineer, Rotating Equipment | 26 | 0.73 |
| SH60 | QA/QC Manager | 25 | 0.82 |

Table 11.2 shows that the Engineering Manager is the most influential Stakeholder on Process Innovation in the Engineering Phase. This result is understandable since the Engineering Manager is typically in charge of many Engineering Tasks and in contact with many other Stakeholders. With a high number of interactions and the central position on the Network of the Engineering Phase, the Engineering Manager has a very informed view of the Network, being able to detect opportunities to innovate, across the many tasks he is connected to. Given Hau et al.’s (2013) perspective that knowledge in an organization resides in a network of social relationships, and Kim et al.’s (2012) view that it is embedded in work routines, as the Engineering manager interacts with more project stakeholders, knowledge sharing ensues and in process enhancing that position’s influence on innovation.

### Most Influential Stakeholders on Process Innovation in the Procurement Phase

Following the procedure of the previous subsection and focusing now on the Procurement Phase, the results on Table 8.19 were expanded on Table 11.3. This table presents the Top 10 most influential Stakeholders, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Stakeholders was based on the average value that each Stakeholder node presented across the three Ego Networks of Process Innovation of the Procurement Phase.

Table 11.3: Top Ten Most Influential Stakeholders on Process Innovation in the Procurement Phase

| Node | Reduced Project Implementation Time |  | Improved Procurement Activities |  | Reduced Operational Cost |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| SH59 | 25 | 0.88 | 24 | 0.90 | - | - | 24.5 | 0.88 |
| SH17 | 23 | 0.87 | 23 | 0.87 | - | - | 23 | 0.87 |
| SH1 | 17 | 0.69 | 17 | 0.69 | - | - | 17 | 0.69 |
| SH55 | 10 | 0.59 | 9 | 0.58 | - | - | 9.5 | 0.59 |
| SH54 | 7 | 0.56 | 7 | 0.56 | - | - | 7 | 0.56 |
| SH2 | 3 | 0.54 | 3 | 0.54 | - | - | 3 | 0.54 |
| SH4 | 3 | 0.54 | 3 | 0.54 | - | - | 3 | 0.54 |
| SH16 | - | - | - | - | 2 | 0.58 | 2 | 0.58 |
| SH28 | - | - | - | - | 2 | 0.58 | 2 | 0.58 |
| SH37 | - | - | - | - | 1 | 0.57 | 1 | 0,57 |

Table 11.3 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.4 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.4: Top Ten Most Influential Stakeholders on Process Innovation in the Procurement Phase - Summary

| Stakeholder Nodes |  | Average Values |  |
| --- | --- | --- | --- |
| Label | Description | Degree Centrality | Closeness Centrality |
| SH59 | Cost Control Manager/Procurement Engineer | 24.5 | 0.88 |
| SH17 | Procurement Engineer | 23 | 0.87 |
| SH1 | Senior Project Manager/Project Manager | 17 | 0.69 |
| SH55 | Project Manager | 9.5 | 0.59 |
| SH54 | Project Director | 7 | 0.56 |
| SH2 | Sr. Project Engineer | 3 | 0.54 |
| SH4 | Sr. Planning Engineer | 3 | 0.54 |
| SH16 | Sr.QA/QC Engineer | 2 | 0.58 |
| SH28 | Sr. QA/QC Engineer | 2 | 0.58 |
| SH37 | Senior Engineer, Piping | 1 | 0.57 |

Table 11.4 shows that the Cost Control Manager/Procurement Engineer is the most influential Stakeholder on Process Innovation in the Procurement Phase. This result is understandable, since this role belongs to a Stakeholder who has influence in decision making in the Procurement Phase of an EPC Project. The Cost Control Manager/Procurement Engineer presents a high number of connections and is a central figure in the Social Network of this Phase, which means that this Stakeholder has access to many tasks and a high visibility of the information flowing in it. Linking the high number of connections to influence on innovation is consistent with Hau et al. (2013) and Kim et al. (2012) as already alluded to in the case of the Engineering Manager during the Engineering Phase. That the highest level of influence has moved to Cost Control Manager / Procurement Engineer confirm Eyiah-Botwe, Aigbavboa and Thwala’s (2016) and Olander (2006) view that because of the complexity of projects, a stakeholder’s influence may change across the various phases.

### Most Influential Stakeholders on Process Innovation in the Construction Phase

Following the procedure of the previous subsections and focusing now on the Construction Phase, the results on Table 9.19 were expanded on Table 11.5. This table presents the Top 10 most influential Stakeholders, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Stakeholders was based on the average value that each Stakeholder node presented across the three Ego Networks of Process Innovation of the Construction Phase.

Table 11.5: Top Ten Most Influential Stakeholders on Process Innovation in the Construction Phase

| Node | Reduced Project Implementation Time |  | Improved Procurement Activities |  | Reduced Operational Cost |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| SH5 | 52 | 0.91 | 23 | 0.87 | - | - | 37.5 | 0.89 |
| SH56 | 51 | 0.89 | 23 | 0.87 | - | - | 37 | 0.88 |
| SH18 | 36 | 0.88 | - | - | - | - | 36 | 0.88 |
| SH29 | 35 | 0.86 | - | - | - | - | 35 | 0.86 |
| SH76 | 35 | 0.86 | - | - | - | - | 35 | 0.86 |
| SH77 | 35 | 0.86 | - | - | - | - | 35 | 0.86 |
| SH78 | 35 | 0.86 | - | - | - | - | 35 | 0.86 |
| SH16 | 32 | 0.85 | - | - | - | - | 32 | 0.85 |
| SH28 | 32 | 0.82 | - | - | - | - | 32 | 0.82 |
| SH79 | 31 | 0.82 | - | - | - | - | 31 | 0.82 |

Table 11.5 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.6 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.6: Top Ten Most Influential Stakeholders on Process Innovation in the Construction Phase - Summary

| Stakeholder Nodes |  | Average Values |  |
| --- | --- | --- | --- |
| Label | Description | Degree Centrality | Closeness Centrality |
| SH5 | Sr. Construction Engineer | 37.5 | 0.89 |
| SH56 | Construction Manager | 37 | 0.88 |
| SH18 | Sr. HSE Engineer | 36 | 0.88 |
| SH29 | Sr. Engineer, HSE | 35 | 0.86 |
| SH76 | Sr. QA/QC Engineer | 35 | 0.86 |
| SH77 | Sr. Engineer, HSE | 35 | 0.86 |
| SH78 | Safety Officer, HSE | 35 | 0.86 |
| SH16 | Sr.QA/QC Engineer | 32 | 0.85 |
| SH28 | Sr. QA/QC Engineer | 32 | 0.82 |
| SH79 | QA/QC Inspector-Civil | 31 | 0.82 |

Table 11.6 shows that the Sr. Construction Engineer is the most influential Stakeholder in the Construction Phase. Looking at the results of the previous subsections, this was expected, as the Sr. Construction Engineer is a stakeholder which has many connections and direct interventions on many tasks, thus allowing him to have a clear view of the information flowing on the Network. The access to the information and to the other nodes create an environment in which innovation can occur. The findings confirm Hau et al. (2013) and Kim et al. (2012) as observed for Engineering and Procurement Phases. Further they confirm the context sensitivity and therefore fluidity of stakeholder influence as noted by Eyiah-Botwe, Aigbavboa and Thwala (2016) and Olander (2006).

### Most Influential Stakeholders on Process Innovation in the EPC Project

Following the procedure of the previous subsections and focusing now on the whole EPC Project, the results on Table 9.19 were expanded on Table 11.5. This table presents the Top 10 most influential Stakeholders, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Stakeholders was based on the average value that each Stakeholder node presented across the three Ego Networks of Process Innovation of the EPC Project.

Table 11.7: Top Ten Most Influential Stakeholders on Process Innovation in the EPC Project

| Node | Reduced Project Implementation Time |  | Improved Procurement Activities |  | Reduced Operational Cost |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| SH62 | 54 | 0.75 | 12 | 0.70 | 123 | 0.81 | 63 | 0.75 |
| SH55 | 54 | 0.64 | 46 | 0.73 | 86 | 0.81 | 62 | 0.73 |
| SH63 | 53 | 0.74 | 7 | 0.64 | 108 | 0.79 | 56 | 0.72 |
| SH76 | 55 | 0.85 | - | - | - | - | 55 | 0.85 |
| SH15 | 21 | 0.53 | - | - | 75 | 0.62 | 48 | 0.57 |
| SH29 | 47 | 0.86 | - | - | - | - | 47 | 0.86 |
| SH1 | 60 | 0.66 | 46 | 0.66 | 33 | 0.47 | 46 | 0.60 |
| SH59 | 41 | 0.56 | 37 | 0.69 | 56 | 0.72 | 45 | 0.66 |
| SH78 | 43 | 0.88 | - | - | - | - | 43 | 0.88 |
| SH5 | 61 | 0.79 | 24 | 0.73 | - | - | 43 | 0.76 |

Table 11.7 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.8 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.8: Top Ten Most Influential Stakeholders on Process Innovation in the EPC Project - Summary

| Stakeholder Nodes |  | Average Values |  |
| --- | --- | --- | --- |
| Label | Description | Degree Centrality | Closeness Centrality |
| SH62 | Engineering Manager | 63 | 0.75 |
| SH55 | Project Manager | 62 | 0.73 |
| SH63 | Sr. Process Engineer | 56 | 0.72 |
| SH76 | Sr. QA/QC Engineer | 55 | 0.85 |
| SH15 | Sr.Piping & Pipeline Engineer | 48 | 0.57 |
| SH29 | Sr. Engineer, HSE | 47 | 0.86 |
| SH1 | Senior Project Manager/Project Manager | 46 | 0.60 |
| SH59 | Cost Control Manager/Procurement Engineer | 45 | 0.66 |
| SH78 | Safety Officer, HSE | 43 | 0.88 |
| SH5 | Sr. Construction Engineer | 43 | 0.76 |

From Table 11.8 results it can be observed that Engineering Manager is the most influential Stakeholder node in the whole EPC Social Network. He/she is followed closely by the Project Manager. The fact that these two Stakeholders present high influence in the network regarding innovation is understandable since they are top decision makers in the EPC Project. Being in this position allows them to have direct access to several different tasks as well as access to information flow that can lead to Innovation. This is consistent with Shokri et al. (2015) view that in an EPC project, the state of relationships as seen through communication, coordination and collaboration affect stakeholder influence on innovation. The informed positions of the two stakeholders (Engineering Manager and Project Manager) are derived from interfacing with many other project stakeholders which increases the positions’ social capital through information sharing. Shen et al. (2018) underline the importance of information sharing among network stakeholders, which includes interface management and conflict resolution for innovation to occur.  The two positions therefore confirm Prester et al.’s (2016) view that process innovation is derived from internal social capital.

### Summary

To summarise Research Question 1, it is important to note that the conclusions reached in the previous subsections point that top decision makers in an EPC Project tend to be the ones with more influence in the network built with all the activities and stakeholders participating in the project. In this instance, it is decision makers responsible for the three process innovation outcomes identified as reduced implementation time, improved procurement activities and reduced operational cost. This is in line with their capability to have direct access to a high and wide range of activities, as well as be in constant contact with the information flowing throughout the network, a situation which in literature has been associated with influencing process innovation. This conclusion is valid both if the analysis is separated by Phases and if considered as a whole project. The only change is that in the first option, top decision makers related to each phase’s line of work are the ones showing a higher influence on the phase’s network. This means that Process Innovation in an EPC Project can occur at a macro level, considering top decision makers of the EPC Project heavily involved in it, and at a micro level, considering the EPC Project work divided by its phases. This confirms Hassan Al-Ali’s (2017) view that innovation depends on individuals within the network of stakeholders sharing information which constitutes that network’s social capital. Each phase of the EPC project has social networks specific to it and in which some stakeholders have access to more information than others making them the most influential on process innovation in that network. Further, the findings confirm Jonas et al. (2018) finding that a stakeholder’s position in the hierarchy influences their engagement and therefore level of influence.

## Research Question 2

“Who are the most influential stakeholders on product innovation in EPC project during the entire project as well as each phase of the project?”

The second research question focuses on identifying the most influential stakeholders on product innovation. According to the classification made for this EPC Project, the Product Innovation Outcomes are the following: “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”. These three Innovation Outcomes were studied in the previous four chapters based on different Social Network Analysis metrics namely Degree Centrality, Closeness Centrality and Betweenness Centrality. Based on explained observations, Betweenness Centrality was excluded from the metrics which allowed the identification of the most influential Stakeholders on the Engineering, Procurement and Construction Phases and on the EPC Project as a whole. This was because Betweenness Centrality had always presented a zero value as addressed in the previous section of this Chapter.

A simple ranking was built from the other two metrics. Degree Centrality played a more important role on the ranking since Ego Networks tend to be small in terms of number of nodes. In that regard, the more connections a Stakeholder presents the more influence they have. Closeness Centrality can also play an important role and can be associated with the quality of Innovation created since it can be generated with a clearer view of information flow on the network.

### Most Influential Stakeholders on Product Innovation in the Engineering Phase

Focusing on the Engineering Phase, the results on Table 7.33 were expanded on Table 11.9. This table presents the Top 10 most influential Stakeholders considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Stakeholders was based on the average value that each Stakeholder node presented across the three Ego Networks of Product Innovation of the Engineering Phase.

Table 11.9: Top Ten Most Influential Stakeholders on Product Innovation in the Engineering Phase

| Node | Reduced Production Cost |  | Meets Health and Safety Requirements |  | Achieved Industrial Standards |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| SH62 | 54 | 0.75 | 12 | 0.70 | 123 | 0.81 | 63 | 0.75 |
| SH55 | 54 | 0.64 | 46 | 0.73 | 86 | 0.81 | 62 | 0.73 |
| SH63 | 53 | 0.74 | 7 | 0.64 | 108 | 0.79 | 56 | 0.72 |
| SH76 | 55 | 0.85 | - | - | - | - | 55 | 0.85 |
| SH15 | 21 | 0.53 | - | - | 75 | 0.62 | 48 | 0.57 |
| SH29 | 47 | 0.86 | - | - | - | - | 47 | 0.86 |
| SH1 | 60 | 0.66 | 46 | 0.66 | 33 | 0.47 | 46 | 0.60 |
| SH59 | 41 | 0.56 | 37 | 0.69 | 56 | 0.72 | 45 | 0.66 |
| SH78 | 43 | 0.88 | - | - | - | - | 43 | 0.88 |
| SH5 | 61 | 0.79 | 24 | 0.73 | - | - | 43 | 0.76 |

Table 11.9 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.10 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.10: Top Ten Most Influential Stakeholders on Product Innovation in the Engineering Phase - Summary

| Stakeholder Nodes |  | Average Values |  |
| --- | --- | --- | --- |
| Label | Description | Degree Centrality | Closeness Centrality |
| SH62 | Engineering Manager | 63 | 0.75 |
| SH55 | Project Manager | 62 | 0.73 |
| SH63 | Sr. Process Engineer | 56 | 0.72 |
| SH76 | Sr. QA/QC Engineer | 55 | 0.85 |
| SH15 | Sr.Piping & Pipeline Engineer | 48 | 0.57 |
| SH29 | Sr. Engineer, HSE | 47 | 0.86 |
| SH1 | Senior Project Manager/Project Manager | 46 | 0.60 |
| SH59 | Cost Control Manager/Procurement Engineer | 45 | 0.66 |
| SH78 | Safety Officer, HSE | 43 | 0.88 |
| SH5 | Sr. Construction Engineer | 43 | 0.76 |

As in the case of Process Innovation, the most influential Stakeholder in the Engineering Phase of product innovation is the Engineering Manager. The justification for this result is like the one presented in the previous section, especially because the Social Network Metrics are similar in both cases. So, it can be concluded that the Engineering Manager is someone who can have direct influence on Innovation, both in terms of Product and Process, due to the fact that he has many connections and a high visibility of information flow on the Engineering Phase Network. This is consistent with Scafuto et al. (2018) view that there is a connection between process innovation and product innovation as the latter can be used as an outcome of the former. In this instance, since the Engineering Manager was found to have the biggest influence on process innovation in the Engineering phase, it is a natural progression for the same influence to extend to product innovation.

### Most Influential Stakeholders on Product Innovation in the Procurement Phase

Focusing on the Procurement Phase, the results on Table 8.30 were expanded on Table 11.11. This table presents the Top 10 most influential Stakeholders, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Stakeholders was based on the average value that each Stakeholder node presented across the three Ego Networks of Product Innovation of the Procurement Phase.

Table 11.11: Top Ten Most Influential Stakeholders on Product Innovation in the Procurement Phase

| Node | Reduced Production Cost |  | Meets Health and Safety Requirements |  | Achieved Industrial Standards |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| SH60 | - | - | - | - | 98 | 0,97 | 98 | 0,97 |
| SH55 | - | - | 4 | 0,83 | 99 | 0,99 | 51,5 | 0,91 |
| SH76 | - | - | 2 | 0,63 | 98 | 0,99 | 50 | 0,81 |
| SH37 | - | - | - | - | 50 | 0,67 | 50 | 0,67 |
| SH17 | 23 | 0,87 | - | - | 49 | 0,98 | 36 | 0,93 |
| SH16 | - | - | 1 | 0,56 | 52 | 0,67 | 26,5 | 0,61 |
| SH15 | - | - | 1 | 0,60 | 51 | 0,67 | 26 | 0,64 |
| SH59 | 25 | 0,88 | - | - | - | - | 25 | 0,88 |
| SH28 | - | - | 1 | 0,56 | 48 | 0,67 | 24,5 | 0,61 |
| SH54 | - | - | - | - | 21 | 0,96 | 21 | 0,96 |

Table 11.11 presents the Labels of the nodes instead of their descriptions to facilitate visualisation. Table 11.12 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.12: Top Ten Most Influential Stakeholders on Product Innovation in the Procurement Phase - Summary

| Stakeholder Nodes |  | Average Values |  |
| --- | --- | --- | --- |
| Label | Description | Degree Centrality | Closeness Centrality |
| SH60 | QA/QC Manager | 98 | 0.97 |
| SH55 | Project Manager | 51.5 | 0.91 |
| SH76 | Sr. QA/QC Engineer | 50 | 0.81 |
| SH37 | Senior Engineer, Piping | 50 | 0.67 |
| SH17 | Procurement Engineer | 49 | 0.98 |
| SH16 | Sr.QA/QC Engineer | 26.5 | 0.61 |
| SH15 | Sr.Piping & Pipeline Engineer | 26 | 0.64 |
| SH59 | Cost Control Manager/Procurement Engineer | 25 | 0.88 |
| SH28 | Sr. QA/QC Engineer | 24.5 | 0.61 |
| SH54 | Project Director | 21 | 0,96 |

Contrary to what happened in the previous subsection, the results here are different from those of Process Innovation in the Procurement Phase. The Cost Control Manager/Procurement Engineer is also on the Top 10 most influential Stakeholders, however there are many others with higher ranking in terms of influence, considering the metrics applied in this thesis. This is explainable by the fact that the focus here is on Product Innovation and so the quality of the product seems to be one of the most important traits for the Procurement Phase so the QA/QC Manager gains relevance. In fact, this node presents 98 connections to other nodes and a very central role in the network. This confirms Prester et al.’s (2016) findings that the highest impact on product innovation involves external social capital. Kahn (2018) explained this as resulting from product innovation’s involving multiple things such as providing a new product, significantly changing the characteristics of a product, product improvements, line extensions; new markets and new uses. Further, that the most influential position is closely contested by three position holders confirms Marin and Wellman’s (2011) view that when employees from different organisations work in conjunction, this creates a convergence of different forms of knowledge leading to innovation.

### Most Influential Stakeholders on Product Innovation in the Construction Phase

Focusing on the Construction Phase, the results on Table 9.19 were expanded on Table 11.13. This table presents the Top 10 most influential Stakeholders, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Stakeholders was based on the average value that each Stakeholder node presented across the three Ego Networks of Product Innovation of the Construction Phase.

Table 11.13: Top Ten Most Influential Stakeholders on Product Innovation in the Construction Phase

| Node | Reduced Production Cost |  | Meets Health and Safety Requirements |  | Achieved Industrial Standards |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| SH76 | 98 | 0.99 | - | - | 98 | 0.99 | 98 | 0.99 |
| SH60 | 98 | 0.97 | - | - | 98 | 0.97 | 98 | 0.97 |
| SH55 | 99 | 0.99 | 10 | 0.59 | 99 | 0.99 | 69.3 | 0.86 |
| SH16 | 52 | 0.67 | - | - | 52 | 0.67 | 52 | 0.67 |
| SH15 | 51 | 0.67 | - | - | 51 | 0.67 | 51 | 0.67 |
| SH37 | 50 | 0.67 | - | - | 50 | 0.67 | 50 | 0.67 |
| SH28 | 48 | 0.67 | - | - | 48 | 0.67 | 48 | 0.67 |
| SH17 | 49 | 0.98 | 23 | 0.87 | 49 | 0.98 | 40.3 | 0.94 |
| SH33 | 18 | 0.65 | - | - | 18 | 0.65 | 18 | 0.65 |
| SH42 | 17 | 0.66 | - | - | 17 | 0.66 | 17 | 0.66 |

Table 11.13 presents the Labels of the nodes instead of their descriptions to facilitate visualisation. Table 11.14 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.14: Top Ten Most Influential Stakeholders on Product Innovation in the Construction Phase - Summary

| Stakeholder Nodes |  | Average Values |  |
| --- | --- | --- | --- |
| Label | Description | Degree Centrality | Closeness Centrality |
| SH76 | Sr. QA/QC Engineer | 98 | 0.99 |
| SH60 | QA/QC Manager | 98 | 0.97 |
| SH55 | Project Manager | 69.3 | 0.86 |
| SH16 | Sr.QA/QC Engineer | 52 | 0.67 |
| SH15 | Sr.Piping & Pipeline Engineer | 51 | 0.67 |
| SH37 | Senior Engineer, Piping | 50 | 0.67 |
| SH28 | Sr. QA/QC Engineer | 48 | 0.67 |
| SH17 | Procurement Engineer | 40.3 | 0.94 |
| SH33 | Sr. Process Engineer | 18 | 0.65 |
| SH42 | Sr. Electrical Engineer | 17 | 0.66 |

Once again, the most influential Stakeholder differs from that of Process Innovation for the Construction Phase. In subsection 11.2.3, it was explained why the Sr. Construction Engineer was the most influential Stakeholder in terms of Process Innovation. Here, as the focus is on Product, the result is more like the one presented on the previous subsection than on the Process Innovation. Given that, quality of the product seems to play an important role in Product Innovation, the Sr. QA/QC Engineer is the most influential Stakeholder in the Construction Phase. This is understandable, since construction requires Engineering, and hence this Stakeholder is higher than the QA/QC Manager in the ranking of Table 11.14. The Sr. QA/QC Engineer presents a significant number of connections in the Network, as well as a very central position in it, which facilitates his/her influence in Innovation Outcomes. The findings confirm the already noted Eyiah-Botwe, Aigbavboa and Thwala’s (2016) observation on the flexibility of stakeholder influence based on the phase of a project.

### Most Influential Stakeholders on Product Innovation in the EPC Project

Following the procedure of the previous subsections and focusing now on the whole EPC Project, the results on Table 10.31 were expanded on Table 11.15. This table presents the Top 10 most influential Stakeholders, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Stakeholders was based on the average value that each Stakeholder node presented across the three Ego Networks of Product Innovation of the EPC Project.

Table 11.15: Top Ten Most Influential Stakeholders on Product Innovation in the EPC Project

| Node | Reduced Production Cost |  | Meets Health and Safety Requirements |  | Achieved Industrial Standards |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| SH55 | 54 | 0.64 | 32 | 0.76 | 210 | 0.69 | 99 | 0.70 |
| SH76 | 55 | 0.85 | 15 | 0.70 | 188 | 0.97 | 86 | 0.84 |
| SH60 | 15 | 0.55 | 20 | 0.67 | 209 | 0.73 | 81 | 0.65 |
| SH62 | 54 | 0.75 | 23 | 0.66 | 141 | 0.61 | 73 | 0.67 |
| SH59 | 41 | 0.56 | 20 | 0.49 | 144 | 0.51 | 68 | 0.52 |
| SH16 | 47 | 0.77 | 10 | 0.55 | 138 | 0.76 | 65 | 0.69 |
| SH28 | 38 | 0.74 | 10 | 0.54 | 133 | 0.76 | 60 | 0.68 |
| SH18 | 58 | 0.65 | 27 | 0.73 | 86 | 0.88 | 57 | 0.75 |
| SH15 | 21 | 0.53 | 8 | 0.59 | 128 | 0.55 | 52 | 0.56 |
| SH56 | 61 | 0.78 | 18 | 0.67 | 67 | 0.85 | 49 | 0.76 |

Table 11.15 presents the Labels of the nodes instead of their descriptions to facilitate visualisation. Table 11.16 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.16: Top Ten Most Influential Stakeholders on Product Innovation in the EPC Project - Summary

| Stakeholder Nodes |  | Average Values |  |
| --- | --- | --- | --- |
| Label | Description | Degree Centrality | Closeness Centrality |
| SH55 | Project Manager | 99 | 0.70 |
| SH76 | Sr. QA/QC Engineer | 86 | 0.84 |
| SH60 | QA/QC Manager | 81 | 0.65 |
| SH62 | Engineering Manager | 73 | 0.67 |
| SH59 | Cost Control Manager/Procurement Engineer | 68 | 0.52 |
| SH16 | Sr.QA/QC Engineer | 65 | 0.69 |
| SH28 | Sr. QA/QC Engineer | 60 | 0.68 |
| SH18 | Sr. HSE Engineer | 57 | 0.75 |
| SH15 | Sr.Piping & Pipeline Engineer | 52 | 0.56 |
| SH56 | Construction Manager | 49 | 0.76 |

According to the metrics chosen and the results presented above, the most influential Stakeholder in the EPC Project for Product Innovation is the Project Manager. Table 11.16 shows that high in the ranking are also Stakeholders working in the Quality area, which is according to what was previously seen that quality aspects are highly relevant when dealing with Product Innovation.  Quality related Stakeholders therefore gain relevance in the Network. Further, the Project Manager is someone who has an important role in decision making in an EPC Project, for that reason this Stakeholder is highly ranked in other results tables across this and the previous sections meaning that he/she plays an important role in innovation, specifically in Product Innovation.  The Project Manager’s most influential position confirms that the level of influence on innovation in a project results from a stakeholder’s decision making position in the hierarchy determines (Jonas et al., 2018);  their state of relationships with other stakeholders (Shokri et al., 2015); and the  quantity of connections they have (Hau et al., 2013; Kim et al.,  2012).

### Summary

To summarise Research Question 2, it is important to note that the conclusions reached in the previous subsections indicate that top decision makers in an EPC Project tend to be the ones with more influence in the network.  This is in line with what was observed and explained in the previous section, for Process Innovation. This conclusion is also valid if the analysis is separated by Phases as well as if considering the project as a whole. In this case of Product Innovation, Quality area decision makers were more prominent. This indicates that in an EPC project influence on innovation shifts depending on the phase being focused on.  The findings contradict those by Prester et al. (2016) where external social capital was found to have the highest impact on product innovation.

## Research Question 3

“What is the most influential activity for each phase of EPC project as well as during the entire project on process innovation?”

After answering the first two Research Questions related to Stakeholder nodes, the third question refers to Activity nodes, focusing on the most influential ones on Process Innovation. The identification of these nodes was previously performed based on different Social Network Analysis metrics across four different chapters: one regarding the Social Network formed by the Activities, Innovation Outcomes and Stakeholders of the Engineering Phase, the Procurement Phase, the Construction Phase and finally the whole EPC Project. The procedure was similar to the one followed for identifying the most influential Stakeholder nodes. The exception was that because in Activity nodes the Betweenness Centrality metric presented values different from zero, these were not incorporated in the ranking leading to the most influential nodes. In fact, following the example mentioned in section 11.2, one understands why Activity nodes present the ability to build bridges in the several networks analysed here. The Engineering Phase Ego Network of Product Innovation Outcome, “Reduced Production Cost”, Stakeholder SH68 – “Engineer, Pipeline” – interacts directly with Activity Node A20390 – “Data Sheet for pipeline Manual valve - Issue as IFC” –, which can generate Innovation. In other words, the Activity always bridges the flow of information and interaction which can end in Innovation coming from that Activity and even from other Activity nodes. This means that Betweenness Centrality can differ from zero, as it was widely seen previously in the Engineering Phase, Procurement Phase, Construction Phase and EPC Analysis’ chapters. Despite this, Betweenness Centrality was also excluded for the analysis of Activity nodes influence to maintain the congruence with the procedure used for Stakeholder nodes. Given that two other metrics, Degree and Closeness Centrality, are left.

Based on this metrics, a simple ranking was built considering that Degree Centrality played a more important role on it since Ego Networks tend to be small in terms of number of nodes. In that regard, the more connections a Stakeholder presents, the more influence they exert. Closeness Centrality can also play an important role since it can be generated with a clearer view of network  information flow, and can be associated with the quality of Innovation created,

### Most Influential Activities on Process Innovation in the Engineering Phase

Focusing on the Engineering Phase, the results on Table 7.23 were expanded on Table 11.17. This table presents the Top 10 most influential Activities, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Activities was based on the average value that each Activities node presented across the three Ego Networks of Process Innovation of the Engineering Phase.

Table 11.17: Top Ten Most Influential Activities on Process Innovation in the Engineering Phase

| Node | Reduced Project Implementation Time |  | Improved Procurement Activities |  | Reduced Operational Cost |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen |
| EP1110 | 42 | 0.55 | - | - | 50 | 0.75 | 46 | 0.65 |
| A29360 | 44 | 1 | - | - | - | - | 44 | 1 |
| PM0005b | 42 | 0.63 | - | - | - | - | 42 | 0.63 |
| PM0006b | 42 | 0.63 | - | - | - | - | 42 | 0.63 |
| EP1120 | 37 | 1 | - | - | - | - | 37 | 1 |
| EP1100 | 38 | 0.83 | - | - | 35 | 1 | 36,5 | 0.92 |
| G1050 | 33 | 0.67 | - | - | - | - | 33 | 0.67 |
| A15130 | - | - | - | - | 28 | 0.56 | 28 | 0.56 |
| A15690 | - | - | - | - | 26 | 0.56 | 26 | 0.56 |
| A29520 | - | - | 13 | 0 | 38 | 0 | 25.5 | 0.00 |

Table 11.17 presents the Labels of the nodes instead of their descriptions to facilitate visualisation. Table 11.18 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.18: Top Ten Most Influential Activity on Process Innovation in the Engineering Phase - Summary

| Activity Nodes |  |  | Average Values |  |
| --- | --- | --- | --- | --- |
| Label | WBS Name | Description | Degree | Closen. |
| EP1110 |  | IPF (SIL Review) | 46 | 0.65 |
| A29360 | Process Balance Documents | Issue as IFC 1) Process Flow Diagram 2) Utility Flow Diagram 3) Block Flow Diagram 4) Process Design Basis & Process Description 5) All other P&IDs 6) Line List (Predecessor for data sheets, tie in list, isometrics & critical line list) | 44 | 1 |
| PM0005b | Document Review Management | Reduced deliverable review cycle (From 10 to 3 days) | 42 | 0.63 |
| PM0006b | Document Review Management | Across the table approval for critical documents | 42 | 0.63 |
| EP1120 |  | 90% Model Review | 37 | 1 |
| EP1100 |  | 60% Model Review | 36,5 | 0.92 |
| G1050 |  | 30% Model Review | 33 | 0.67 |
| A15130 | Sales Gas Compressor After Cooler Data Sheets | Receive Company Approval | 28 | 0.56 |
| A15690 | Instrument air receiver Data Sheets | Receive Company Approval | 26 | 0.56 |
| A29520 | Mechanical (Static/Package unit) Balance Documents | Issue as IFC | 25.5 | 0.00 |

The most influential Activity node in the Engineering Phase is the node EP1110 which has a description “IPF (SIL Review)”. This Activity has many connections with other nodes and presents a medium Closeness Centrality, which means that this Activity has access to important information flow. Also, this Activity has a broad range of connections, since it does not belong to a specific WBS task. This means that this Activity has access to other activities and nodes belonging to different sectors of the Engineering Phase. Thus, this makes it influential in the network, in terms of Process Innovation.

### Most Influential Activities on Process Innovation in the Procurement Phase

Focusing on the Procurement Phase, the results on Table 8.19 were expanded on Table 11.19. This table presents the Top 10 most influential Activities, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Activities was based on the average value that each Activities node presented across the three Ego Networks of Process Innovation of the Procurement Phase.

Table 11.19: Top Ten Most Influential Activities on Process Innovation in the Procurement Phase

| Node | Reduced Project Implementation Time |  | Improved Procurement Activities |  | Reduced Operational Cost |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| PM0005 | 19 | 1 | 19 | 1 | - | - | 19 | 1 |
| PM0006 | 19 | 1 | 19 | 1 | - | - | 19 | 1 |
| PM0007 | 18 | 1 | 18 | 1 | - | - | 18 | 1 |
| A5980 | - | - | - | - | 14 | 1 | 14 | 1 |
| PM0001 | 12 | 0.91 | 12 | 0.91 | - | - | 12 | 0.91 |
| PM0002 | 11 | 1 | 11 | 1 | - | - | 11 | 1 |
| C.01 | 9 | 0 | 9 | 0 | - | - | 9 | 0 |
| PM0004 | 8 | 1 | 8 | 1 | - | - | 8 | 1 |
| C.02 | 8 | 0 | 8 | 0 | - | - | 8 | 0 |
| C.03 | 8 | 0 | 8 | 0 | - | - | 8 | 0 |

Table 11.19 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.20 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.20: Top Ten Most Influential Activity on Process Innovation in the Procurement Phase - Summary

| Activity Nodes |  |  | Average Values |  |
| --- | --- | --- | --- | --- |
| Label | WBS Name | Description | Degree | Closen. |
| PM0005 | Procurement Management | Weekly Procurement expediting meetings with CONTRACTOR and VENDORS | 19 | 1 |
| PM0006 | Procurement Management | Daily Procurement Meetings with Vendors | 19 | 1 |
| PM0007 | Procurement Management | Allocation of Expeditors at Vendor Manufacturing locations | 18 | 1 |
| A5980 | RBI Study | Prepare and Issue MR | 14 | 1 |
| PM0001 | Vendor Management | Factory Visit 1 (Critical Equipment-Compressor Package, Instrument Air Package, Flare Package) | 12 | 0.91 |
| PM0002 | Vendor Management | Factory Visit 2 (33kv Gis Switchgear, ICS,HIPS,Metering Skid) | 11 | 1 |
| C.01 |  | Receive Gas Compressor Packages (Tag # 834-K-101/K-201/K-301) at site | 9 | 0 |
| PM0004 | Vendor Management | Factory Visit 4 (Piping material-Valves,fittings) | 8 | 1 |
| C.02 |  | Receive Air Coolers, Metering Skid Package, K.O Drums and Air Compressor & Dryer Package at site | 8 | 0 |
| C.03 |  | Receive 33kV & 11kV Switchgears and 33kV/11kV Transformers Instrument Control System (ICS) and HIPS Equipment at site | 8 | 0 |

According to the results presented above, the PM0005 Activity node is the most influential node regarding Process Innovation in the Procurement Phase Social Network. This node is related to the WBS Task “Procurement Management” and its description is “Weekly Procurement expediting meetings with Contractor and Vendors”, which means that this is a recurrent task of Procurement Management that connects many Stakeholders in the EPC Project, as well as many Activities since the description shows that this is a general task. Because this Activity presents an important number of connections (note that the numbers for the Procurement Phase are usually lower as the Network itself is small) to other nodes in the three Process Innovation Outcomes’ Social Networks is perfectly reasonable.

### Most Influential Activities on Process Innovation in the Construction Phase

Focusing on the Construction Phase, the results on Table 9.20 were expanded on Table 11.21. This table presents the Top 10 most influential Activities considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Activities was based on the average value that each Activities node presented across the three Ego Networks of Process Innovation of the Construction Phase.

Table 11.21: Top Ten Most Influential Activities on Process Innovation in the Construction Phase

| Node | Reduced Project Implementation Time |  | Improved Procurement Activities |  | Reduced Operational Cost |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| CC1592 | 35 | 0.83 | - | - | - | - | 35 | 0.83 |
| A4180 | 35 | 0.69 | - | - | - | - | 35 | 0.69 |
| CC1591 | 34 | 0.75 | - | - | - | - | 34 | 0.75 |
| A4174 | 34 | 0.57 | - | - | - | - | 34 | 0.57 |
| CC1590C | 34 | 0.38 | - | - | - | - | 34 | 0.38 |
| CC1588A | 34 | 0.23 | - | - | - | - | 34 | 0.23 |
| CC2320 | 33 | 1.00 | - | - | - | - | 33 | 1.00 |
| A4175 | 33 | 0.67 | - | - | - | - | 33 | 0.67 |
| CC1590G | 33 | 0.50 | - | - | - | - | 33 | 0.50 |
| CC1590E | 33 | 0.40 | - | - | - | - | 33 | 0.40 |

Table 11.21 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.22 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.22: Top Ten Most Influential Activity on Process Innovation in the Construction Phase - Summary

| Activity Nodes |  |  | Average Values |  |
| --- | --- | --- | --- | --- |
| Label | WBS Name | Description | Degree | Closen. |
| CC1592 | Mechanical (Equipment) | Fire water Tank - Final Testing (NDT, RT etc.) | 35 | 0.83 |
| A4180 | Piping | Hot Tap work (Preparation and Execution) | 35 | 0.69 |
| CC1591 | Mechanical (Equipment) | Fire water Tanks - Welding, Testing (NDT, RT etc.) - Level 5 | 34 | 0.75 |
| A4174 | Piping | Pipeline laying and testing - 30 " - Field Welding Testing (NDT..RE etc.) | 34 | 0.57 |
| CC1590C | Mechanical (Equipment) | Fire water Tanks - Welding, Testing | 34 | 0.38 |
| CC1588A | Mechanical (Equipment) | Fire water Tanks - Welding, Testing (NDT, RT etc.) - Baseplate | 34 | 0.23 |
| CC2320 | Mechanical (Equipment) | All Equipment Installation | 33 | 1.00 |
| A4175 | Piping | Cold Tie-in (Preparation and Execution) | 33 | 0.67 |
| CC1590G | Mechanical (Equipment) | Fire water Tanks - Welding, Testig | 33 | 0.50 |
| CC1590E | Mechanical (Equipment) | Fire water Tanks - Welding, Testing (NDT, RT etc.) | 33 | 0.40 |

Observing Table 11.22, in the Construction Phase, it is can be observed that the Activity CC1592 – Fire water Tank – Final Testing (NDT, RT etc.) is the most influential Activity in the Social Network. Indeed, this Activity node presents the highest aggregate value of the ranking, with links to other 35 nodes and a high closeness in the Network. Table 11.22 also shows that the most influential Activities in the Construction Phase Social Network regarding Process Innovation are related to Piping and Mechanical Equipment, which is in line with the importance of this sectors in an EPC Project for Oil and Gas. In other words, these activities are very influential because they are crucial. If something goes bad in the Piping or Tanks, problems may arise. It is therefore reasonable that if innovation happens here, the impacts would be big.

### Most Influential Activities on Process Innovation in the EPC Project

Following the procedure of the previous subsections and focusing now on the whole EPC Project, the results on Table 10.21 were expanded on Table 11.23. This table presents the Top 10 most influential Activities, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Activities was based on the average value that each Activities node presented across the three Ego Networks of Process Innovation of the EPC Project.

Table 11.23: Top Ten Most Influential Activities on Process Innovation in the EPC Project

| Node | Reduced Project Implementation Time |  | Improved Procurement Activities |  | Reduced Operational Cost |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| EP1110 | 47 | 0.37 | - | - | - | - | 47 | 0.37 |
| EP1120 | 45 | 0.76 | - | - | - | - | 45 | 0.76 |
| CC1850 | 45 | 0 | - | - | - | - | 45 | 0 |
| CC1670 | 42 | 0.6 | - | - | - | - | 42 | 0.60 |
| CC2910 | 42 | 0 | - | - | - | - | 42 | 0 |
| CC3070 | 52 | 0.75 | 27 | 0.75 | - | - | 39,5 | 0.75 |
| CC2990 | 52 | 0.67 | 27 | 0.67 | - | - | 39,5 | 0.67 |
| EP1100 | 38 | 0.49 | - | - | - | - | 38 | 0.49 |
| CC1592 | 35 | 0.83 | - | - | - | - | 35 | 0.83 |
| A29360 | 44 | 0.46 | - | - | 26 | 1 | 35 | 0.73 |

Table 11.23 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.24 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.24: Top Ten Most Influential Activity on Process Innovation in the EPC Project - Summary

| Activity Nodes |  |  | Average Values |  |
| --- | --- | --- | --- | --- |
| Label | WBS Name | Description | Degree | Closen. |
| EP1110 |  | IPF (SIL Review) | 47 | 0.37 |
| EP1120 |  | 90% Model Review | 45 | 0.76 |
| CC1850 | Mechanical Completion Other Area | Mechanical Completion - Compressor Station Guard House | 45 | 0 |
| CC1670 | Commissioning | HVAC commissioning (Control Room) | 42 | 0.60 |
| CC2910 | Commissioning | Fire water pump / system commissioning | 42 | 0 |
| CC3070 | Mechanical Completion Train 2 | Mechanical Completion | 39,5 | 0.75 |
| CC2990 | Mechanical Completion Train 1 | Mechanical Completion | 39,5 | 0.67 |
| EP1100 |  | 60% Model Review | 38 | 0.49 |
| CC1592 | Mechanical (Equipment) | Fire water Tank - Final Testing (NDT, RT etc.) | 35 | 0.83 |
| A29360 | Process Balance Documents | Issue as IFC Process Flow Diagram | 35 | 0.73 |

Similar, to what was observed in the Engineering Phase of this section, Activity EP1110 – IPF (SIL Review) is also the most influential Activity on Process Innovation for the EPC Project as a whole. This Activity ranked higher in Table 11.24 and presents a high number of connections and has a highly central position in the Network.

### Summary

To summarise Research Question 3, it is important to note that the conclusions reached in the previous subsections point to cross-sectional Activities being the most influential in each of the three Phases and the EPC Project itself. This means in line with what was observed and explained in the previous sections, for Stakeholder nodes, nodes which rank higher in the hierarchy of the EPC Project (in terms of decision making or cross-sectional activities) are also those which have higher influence in terms of Process Innovation.

## Research Question 4

“What is the most influential activity for each phase of EPC project as well as during the entire project on product innovation?”

The fourth research question focuses on identifying the most influential activities on product innovation. According to the classification made for this EPC Project, the Product Innovation Outcomes are the following: “Reduced Production Cost”, “Meets Health and Safety Requirements” and “Achieved Industrial Standards”. These three Innovation Outcomes were studied in the previous four chapters and the results are going to be discussed in this section. The results will be presented in the following subsections under each Phase of the EPC Project, and for the whole project. As before, they will be based on the average Degree and Closeness Centrality metrics each of the nodes presented on each of the Innovation Outcomes’ Ego Networks.

### Most Influential Activities on Product Innovation in the Engineering Phase

Focusing on the Engineering Phase, the results on Table 7.34 were expanded on Table 11.25. This table presents the Top 10 most influential Activities considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Activities was based on the average value that each Activities node presented across the three Ego Networks of Process Innovation of the Engineering Phase.

Table 11.25: Top Ten Most Influential Activities on Product Innovation in the Engineering Phase

| Node | Reduced Production Cost |  | Meets Health and Safety Requirements |  | Achieved Industrial Standards |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| EP1110 | - | - | 50 | 0.60 | 50 | 0.75 | 50 | 0.68 |
| EP1100 | - | - | 38 | 0.83 | 35 | 1 | 36.5 | 0.92 |
| A29520 | 25 | 0 | - | - | 38 | 0 | 31.5 | 0 |
| G1060 | - | - | 23 | 0.50 | 20 | 0.70 | 21.5 | 0.60 |
| A19410 | 21 | 0.92 | - | - | 21 | 0.92 | 21 | 0.92 |
| A15130 | 13 | 0.56 | - | - | 28 | 0.56 | 20.5 | 0.56 |
| A14930 | 20 | 1 | - | - | 20 | 1 | 20 | 1 |
| A29680 | 19 | 0 | - | - | 20 | 0 | 19.5 | 0 |
| A16670 | 13 | 0.56 | - | - | 25 | 0.56 | 19 | 0.56 |
| A15690 | 12 | 0.56 | - | - | 26 | 0.56 | 19 | 0.56 |

Table 11.25 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.26 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.26: Top Ten Most Influential Activity on Product Innovation in the Engineering Phase - Summary

| Activity Nodes |  |  | Average Values |  |
| --- | --- | --- | --- | --- |
| Label | WBS Name | Description | Degree | Closen. |
| EP1110 |  | IPF (SIL Review) | 50 | 0.68 |
| EP1100 |  | 60% Model Review | 36.5 | 0.92 |
| A29520 | Mechanical (Static/Package unit) Balance Documents | Issue as IFC | 31.5 | 0 |
| G1060 |  | HAZOP | 21.5 | 0.60 |
| A19410 | Pipeline Design Basis | Issue as IFC | 21 | 0.92 |
| A15130 | Sales Gas Compressor After Cooler Data Sheets | Receive Company Approval | 20.5 | 0.56 |
| A14930 | Mechanical Design Basis -Static Equipment | Issue as IFC | 20 | 1 |
| A29680 | Piping Balance Documents | Issue as IFC | 19.5 | 0 |
| A16670 | Instrument air package Data Sheets (dryer) | Receive Company Approval | 19 | 0.56 |
| A15690 | Instrument air receiver Data Sheets | Receive Company Approval | 19 | 0.56 |

As it was seen in the Process Innovation results in section 11.4.1, the most influential Activity node in the Engineering Phase is the node EP1110 which has a description “IPF (SIL Review)”. This Activity has many connections with other nodes and presents a medium Closeness Centrality, which means that this Activity has access to important information flow. Also, this Activity has a broad range of connections, since it does not belong to a specific WBS task. This means that this Activity has access to other activities and nodes belonging to different sectors of the Engineering Phase.

### Most Influential Activities on Product Innovation in the Procurement Phase

Focusing on the Procurement Phase, the results on Table 8.19 were expanded on Table 11.27. This table presents the Top 10 most influential Activities, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Activities was based on the average value that each Activities node presented across the three Ego Networks of Product Innovation of the Procurement Phase.

Table 11.27: Top Ten Most Influential Activities on Process Innovation in the Procurement Phase

| Node | Reduced Production Cost |  | Meets Health and Safety Requirements |  | Achieved Industrial Standards |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| A1360 | - | - | - | - | 31 | 1 | 31 | 1 |
| A1280 | - | - | - | - | 29 | 1 | 29 | 1 |
| A1300 | - | - | - | - | 29 | 1 | 29 | 1 |
| A1320 | - | - | - | - | 29 | 1 | 29 | 1 |
| A1400 | - | - | - | - | 29 | 1 | 29 | 1 |
| A1420 | - | - | - | - | 29 | 1 | 29 | 1 |
| A1440 | - | - | - | - | 29 | 1 | 29 | 1 |
| A1380 | - | - | - | - | 21 | 1 | 21 | 1 |
| A1480 | - | - | - | - | 21 | 1 | 21 | 1 |
| A2600 | - | - | - | - | 20 | 1 | 20 | 1 |

Table 11.27 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.28 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.28: Top Ten Most Influential Activity on Product Innovation in the Procurement Phase - Summary

| Activity Nodes |  |  | Average Values |  |
| --- | --- | --- | --- | --- |
| Label | WBS Name | Description | Degree | Closen. |
| A1360 | Suction KO drum | Prepare and Issue MR | 31 | 1 |
| A1280 | Instrument Air Receiver | Prepare and Issue MR | 29 | 1 |
| A1300 | Nitrogen Receiver | Prepare and Issue MR | 29 | 1 |
| A1320 | Sales Gas Filter | Prepare and Issue MR | 29 | 1 |
| A1400 | IA Compressor Package | Prepare and Issue MR | 29 | 1 |
| A1420 | Flare package | Prepare and Issue MR | 29 | 1 |
| A1440 | EOT Cranes | Prepare and Issue MR | 29 | 1 |
| A1380 | Closed drain drum | Prepare and Issue MR | 21 | 1 |
| A1480 | Portable water tank | Prepare and Issue MR | 21 | 1 |
| A2600 | F&G Equipment | Prepare and Issue MR | 20 | 1 |

According to the results presented and based on the ranking used in this thesis, the most influential Activity in terms of Product Innovation is Activity A1360 – Suction KPO drum – prepare and Issue MR. This Activity presents a high centrality in the Procurement Phase Social Network as well as a high number of links to other nodes.

### Most Influential Activities on Product Innovation in the Construction Phase

Focusing on the Construction Phase, the results on Table 9.30 were expanded on Table 11.29. This table presents the Top 10 most influential Activities, considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Activities was based on the average value that each Activities node presented across the three Ego Networks of Product Innovation of the Construction Phase.

Table 11.29: Top Ten Most Influential Activities on Product Innovation in the Construction Phase

| Node | Reduced Production Cost |  | Meets Health and Safety Requirements |  | Achieved Industrial Standards |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| CC2120 | - | - | - | - | 46 | 0.54 | 46 | 0.54 |
| CC2130 | - | - | - | - | 43 | 0.38 | 43 | 0.38 |
| CC2320 | 33 | 1 | - | - | 39 | 1 | 36 | 1 |
| A4180 | 35 | 1 | - | - | 35 | 1 | 35 | 1 |
| CC1592 | 35 | 0.83 | - | - | 35 | 0.58 | 35 | 0.71 |
| A31720 | - | - | - | - | 35 | 0.43 | 35 | 0.43 |
| A4174 | 34 | 0.77 | - | - | 34 | 0.77 | 34 | 0.77 |
| CC1591 | 34 | 0.75 | - | - | 34 | 0.67 | 34 | 0.71 |
| CC1590C | 34 | 0.38 | - | - | 34 | 1 | 34 | 0.69 |
| CC1588A | 34 | 0.23 | - | - | 34 | 1 | 34 | 0.62 |

Table 11.29 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.30 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.30: Top Ten Most Influential Activity on Product Innovation in the Construction Phase - Summary

| Activity Nodes |  |  | Average Values |  |
| --- | --- | --- | --- | --- |
| Label | WBS Name | Description | Degree | Closen. |
| CC2120 | Mechanical (Equipment) | HIPS Installation | 46 | 0.54 |
| CC2130 | Mechanical (Equipment) | All Equipment Installation | 43 | 0.38 |
| CC2320 | Mechanical (Equipment) | All Equipment Installation | 36 | 1 |
| A4180 | PIPING | Hot Tap work (Preparation and Execution) | 35 | 1 |
| CC1592 | Mechanical (Equipment) | Fire water Tank - Final Testing (NDT, RT etc.) | 35 | 0.71 |
| A31720 | PIPING | Piping Pre-fabrication (CS 20" and above) | 35 | 0.43 |
| A4174 | PIPING | Pipeline laying and testing - 30 " - Field Welding Testing (NDT..RE etc.) | 34 | 0.77 |
| CC1591 | Mechanical (Equipment) | Fire water Tanks - Welding, Testing (NDT, RT etc.) - Level 5 | 34 | 0.71 |
| CC1590C | Mechanical (Equipment) | Fire water Tanks - Welding, Testing (NDT, RT etc.) - Level 2 | 34 | 0.69 |
| CC1588A | Mechanical (Equipment) | Fire water Tanks - Welding, Testing (NDT, RT etc.) - Baseplate | 34 | 0.62 |

The most influential Activity of the Construction Phase regarding Product Innovation is CC2120 – Mechanical (Equipment) – HIPS Installation. According to Table 11.30, this is the activity scoring higher in the ranking defined in this thesis. Once again, the Construction Phase “Mechanical (Equipment)” task plays a central role in Innovation, as it was observed in subsection 11.4.3. This WBS Task is indeed core to the development of an EPC Project for Oil and Gas, so it is the one that can present a higher influence towards Innovation.

### Most Influential Activities on Product Innovation in the EPC Project

Following the procedure of the previous subsections and focusing now on the whole EPC Project, the results on Table 10.32 were expanded on Table 11.31. This table presents the Top 10 most influential Activities considering that a high Degree Centrality along with a high Closeness Centrality allows a node to reach many other nodes and to have a central role in the whole network. The order of the Activities was based on the average value that each Activities node presented across the three Ego Networks of Product Innovation of the EPC Project.

Table 11.31: Top Ten Most Influential Activities on Product Innovation in the EPC Project

| Node | Reduced Production Cost |  | Meets Health and Safety Requirements |  | Achieved Industrial Standards |  | Average Values |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Label | Degree | Closen. | Degree | Closen. | Degree | Closen. | Degree | Closen. |
| EP1110 | - | - | 50 | 0.44 | 50 | 0.26 | 50 | 0.35 |
| CC2120 | - | - | - | - | 47 | 0.54 | 47 | 0.54 |
| CC2990 | - | - | - | - | 44 | 0 | 44 | 0 |
| CC2130 | - | - | - | - | 43 | 0.38 | 43 | 0.38 |
| CC2550 | - | - | - | - | 43 | 0 | 43 | 0 |
| EP1120 | - | - | 45 | 0.93 | 38 | 0.38 | 41.5 | 0.65 |
| A29520 | - | - | - | - | 40 | 0 | 40 | 0 |
| CC2320 | - | - | - | - | 39 | 1 | 39 | 1 |
| EP1100 | - | - | 38 | 0.56 | - | - | 38 | 0.56 |
| A31720 | - | - | - | - | 37 | 0.43 | 37 | 0.43 |

Table 11.31 presents the Labels of the nodes instead of their descriptions only to facilitate visualisation. Table 11.32 solves this issue, showing only the descriptions and the values considered for the ranking presented above.

Table 11.32: Top Ten Most Influential Activities on Product Innovation in the EPC Project - Summary

| Activity Nodes |  |  | Average Values |  |
| --- | --- | --- | --- | --- |
| Label | WBS Name | Description | Degree | Closen. |
| EP1110 |  | IPF (SIL Review) | 50 | 0.35 |
| CC2120 | Mechanical (Equipment) | HIPS Installation | 47 | 0.54 |
| CC2990 | Mechanical Completion Train 1 | Mechanical Completion | 44 | 0 |
| CC2130 | Mechanical (Equipment) | All Equipment Installation | 43 | 0.38 |
| CC2550 | Mechanical Completion Other Area | Mechanical Completion - Custody Transfer Area | 43 | 0 |
| EP1120 |  | 90% Model Review | 41.5 | 0.65 |
| A29520 | Mechanical (Static/Package unit) Balance Documents | Issue as IFC | 40 | 0 |
| CC2320 | Mechanical (Equipment) | All Equipment Installation | 39 | 1 |
| EP1100 |  | 60% Model Review | 38 | 0.56 |
| A31720 | Piping | Piping Pre-fabrication (CS 20" and above) | 37 | 0.43 |

Similar to what was observed in the Engineering Phase of this and of the previous section, Activity EP1110 – IPF (SIL Review) is also the most influential Activity on Product Innovation for the whole EPC Project.  This Activity ranked higher in Table 11.32 and presents a high number of connections and has a highly central position in the Network. That the most influential Activity is from the Engineering Phase confirms Yi et al. (2019) who describe that Phase as the most critical part of an EPC project with far reaching implications for the other phases because of its interfacing with all project stakeholders from the client, procurement, to construction. Further it is the Phase that deals with complying with industry safety standards.

### Summary

To summarise Research Question 4, it is important to note that the conclusions reached in the previous subsections point to cross-sectional Activities being the most influential in each of the three Phases and the EPC Project. This means in line with what was observed and explained in the previous sections for Stakeholder nodes, nodes which rank higher in the hierarchy of the EPC Project (in terms of decision making or cross-sectional activities) are also those which have higher influence in terms of Product Innovation. This confirms Scafuto et al. (2018) findings that Process Innovation can serve as a precursor to Product Innovation to an extent that the latter can be viewed as an outcome of the former.

The fact that the Activity EP1110 – IPF (SIL Review) is the most influential Activity on Product Innovation for the Engineering Phase and EPC Project makes it relevant for innovation. That nodes higher in the hierarchy have higher influence on Product Innovation confirms Kahn’s (2018) view that because of its connection to an organisation’s marketing strategy,  product innovation focuses on product effectiveness hence its involving cross-sectional activities.

## Research Question 5

“How to model the Stakeholder interaction of process innovation in EPC project?”

In a complex project as an Oil and Gas EPC Project, the number of Stakeholders and Activities and the number of connections between them is huge. This means that it is difficult to analyse the impact on innovation from considering the whole network created by those Stakeholders, Activities, and links between them. To try to circumvent this problem, a Social Network Analysis technique was utilised. This technique is the Ego Networks’ technique whereby for each of the nodes under analysis, a subset of the original Network is created, including all the nodes that share a connection to the one under analysis. This subset can be further expanded by including the nodes which are connected to the nodes which are linked to the original node, and so on. Ego Networks can therefore have several degrees of depth.

In the case of this thesis, it was chosen to study Ego Networks of depth two. The reason behind this choice is related to the scope of the thesis given its goal of focusing on Innovation and understanding the Activities and Stakeholders that can lead to Innovation. In order to study that, it was essential to bear in mind the type of interactions in an EPC Project Social Network. Typically, a Stakeholder interacts with an Activity (or more) as a way of starting an information flow that can end in Innovation. This means that the Ego Networks need to have a depth of two, to include both Activities and Stakeholder nodes, as well as the original nodes themselves, which are the Innovation Outcomes. Through these Ego Networks, it was then possible to focus on the behaviour of Stakeholder nodes. The modelling of this interaction with the other nodes in the Social Network itself was done through the analysis of some metrics like Degree, Closeness and Betweenness Centrality. These Social Network Analyses allowed the identification of the most influential Stakeholder as depicted in Table 11.33.

Table 11.33: Social Network Analysis Interpretation for Stakeholder nodes

| Social Network Metric | Social Network Analysis Metric Interpretation |
| --- | --- |
| Degree Centrality | The degree centrality of a Stakeholder node represents the number of nodes that are connected to it. This number indicates the connectivity of the Stakeholder in the network. As the number of degree centrality increases it indicates that the node can be considered a Hub in the network and thus present an ability to easily receive or send information to a significant number of nodes. |
| Closeness Centrality | The closeness centrality of a Stakeholder node indicates the importance of the component in terms of having a central position in the network. A high closeness centrality means that a node is very central and is practically close to every other node. For a Stakeholder node, a high closeness centrality means that it possesses a direct connection to many Activities, Stakeholders, and Innovation Outcomes. |
| Betweenness Centrality | The betweenness centrality of a Stakeholder node indicates the importance of the component in terms of connecting the components in the network. A high betweenness centrality means that a node can make bridges in the network, connecting nodes belonging to different parts of the graph. For a Stakeholder node, a high betweenness centrality means that it can influence Activities and Innovation Outcome nodes. |

Of the three metrics on Table 11.33, only the first two were used in the modelling of Stakeholder nodes for Process Innovation, since across all Ego Networks studied and due to the nature of Stakeholder nodes, Betweenness Centrality was always zero, as was mentioned before.

## Research Question 6

“How to model the Stakeholder interaction of product innovation in EPC project?”

The detailed explanation provided in the previous section is equally applied to Research Question 6, with the only difference being in the type of Innovation in which the study focuses. Across the four chapters of the analysis presented in this thesis, the methodology was the same both for Process and Product Innovation. In that regard, modelling of the Stakeholder interaction of Product Innovation in EPC Project was the same as that used for Process Innovation which involved focusing on Ego Networks of depth two of Innovation Outcome nodes related to Product Innovation and using Degree and Closeness Centrality.

## Research Question 7

“Can the network measures be used to better understand the EPC project complexity?”

Social Networks Analysis techniques were used in this thesis to study the influence of certain Stakeholders and Activities of the EPC Project on Innovation. In Chapter 6, a review of the literature was done to allow the understanding of how Social Network Analysis could help develop a methodology for a study like this. Besides, throughout this thesis, some explanations and interpretations of Social Network Analysis metrics were given, including in the first six sections of this chapter. Table 11.34 below allows a comparison of some of the Social Network Analysis metrics that were presented throughout this work.

Table 11.34: Ensemble of Social Network Analysis Metrics

| Social Network Metrics | Engineering Phase | Procurement Phase | Construction Phase | EPC Project |
| --- | --- | --- | --- | --- |
| Number of Nodes | 1684 | 1068 | 934 | 3419 |
| Number of Edges | 15335 | 7127 | 19930 | 42423 |
| Network Diameter | 28 | 8 | 16 | 38 |
| Graph Density | 0.005 | 0.006 | 0.022 | 0.004 |
| Average Path Length | ~5.33 | ~2.31 | ~5 | ~7.8 |
| Average Clustering Coefficient | 0.095 | 0.097 | 0.077 | 0.1 |
| Average Degree | ~9.1 | ~6.7 | ~21 | 12.41 |

Observing Table 11.34, it can be noticed that the metrics analysed allow the comparison of the different Networks studied in the previous chapters. These metrics include the number of nodes, edges and other specific Social Network metrics like Network Diameter and Graph Density. Besides these metrics for every project Phase and every Ego Network studied, others were also included such as “Degree Centrality”, “Betweenness Centrality” and “Closeness Centrality”.

## Summary

This chapter presented a discussion of the answers to all the seven Research Questions of this thesis. This discussion was divided into seven sections, each addressing a Research Question. The first four sections were then divided into five subsections: one focusing on each of the three phases of the EPC Project (Engineering, Procurement and Construction) and another for the EPC Project itself, followed by a summary subsection. After these five subsections, three other subsections were included to discuss Research Question 5, 6 and 7, which focused on Social Network Analysis techniques utilised throughout this work. The next chapter concludes this study and identifies areas for further research.

# Conclusion

## Introduction

The aim of this research is to uncover the complexity of interactions among project stakeholders, and product and process innovation in Oil and Gas EPC Projects. This is done by developing a framework for analysing the complexity of interaction among project stakeholders and product and process innovation in an EPC project in the downstream oil and gas sector in the United Arab Emirates (UAE).  It was achieved through employing Social Network Analysis to analyse stakeholder interaction in the case of United Arab Emirates based on Project Alpha. The study addressed the following objectives:

- To identify the most influential stakeholders on process innovation in EPC project during each phase of the project and during the entire project.

- To identify the most influential stakeholders on product innovation in EPC project during each phase of the project during the entire project.

- To identify the most influential activity on process innovation in EPC project during each phase of the project and during the entire project.

- To identify the most influential activity on product innovation in EPC project during each phase of the project and during the entire project.

- To determine how to model Stakeholder interaction of process innovation in EPC project.

- To determine how to model Stakeholder interaction of product innovation in EPC project.

- To determine whether network measures can be used to better understand the complexity of the EPC project.

This chapter presents the study’s outcome and a conclusive presentation on the main findings relating to each of the study’s objectives, its limitations, contribution to knowledge and suggestions for further research.

## Achievement of Research Objectives

Employing Social Network Analysis as a method of developing a framework for analysing the interaction among project stakeholders and process and product innovation outcomes in an EPC project answered the study’s research question by providing a framework for understanding the nexus of complex stakeholder interactions and process and product innovation in a downstream oil and gas sector EPC project. Social Network Analysis of the social networks formed by the project stakeholders and activities across the three phases and the entire EPC project; and  Ego Network Analysis of product and process innovation outcomes throughout the EPC project were successfully used to achieve the study’s objectives.  The study’s hypothesis that using social network analysis to map out the complex stakeholder interactions in a downstream oil and gas EPC project facilitates an enhanced understanding of process and product innovation occurring during the various phases of the project and throughout the project was therefore confirmed. The study’s meeting of the objectives is as summarised in 12.2.1 – 12.2.6.

### Objective 1 – Stakeholders and Process Innovation

Objective 1: To identify the most influential stakeholders on process innovation in the EPC project during each phase of the project and during the entire project

To identify the most influential stakeholders on process innovation in Project Alpha during each phase and during the entire project, Chapters 7 – 10 presented a social network based analysis of stakeholder linkages in each Phase of the EPC and in the entire EPC. The findings indicated that stakeholders with a high number of interactions occupied a central position in a Phase’s network, which enabled them to have a birds’ eye view of activities in the network, and to access information flowing through the network were associated with process innovation outcomes. In that regard the Engineering Manager was identified as the most influential Stakeholder on Process Innovation in the Engineering Phase (Section 11.2.1), the Cost Control Manager/ Procurement Engineer in the Procurement Phase (Section 11.2.2), and the Sr. Construction Engineer in the Construction Phase (Section 11.2.3). Considering the whole project, Engineering Manager was identified as the most influential Stakeholder node followed at close range by the Project Manager consistent with both positions’ being top decision makers in the EPC Project (Table 11.8). Influence on Process innovation was found to be higher from top decision makers in an EPC Project.

### Objective 2 –Stakeholders and Product Innovation

Objective 2: To identify the most influential stakeholders on product innovation in the EPC project during each phase of the project during the entire project

To identify the most influential stakeholders on product innovation in Project Alpha during each phase and during the entire project, the approach used for Process Innovation was also used for Product Innovation (Chapters 7 – 10).  Similar to the situation for process innovation, stakeholders with a high number of interactions occupied a central position and were associated with process innovation outcomes. The Engineering Manager was identified as the most influential Stakeholder in the Engineering Phase of Product innovation (Section 11.5.1), Cost Control Manager/Procurement Engineer in the Procurement Phase (Section 11.5.2) and Sr. QA/QC Engineer in the Construction Phase (Section 11.5.3) for similar reasons as those explained for the case of Process innovation. In the Procurement Phase Cost Control Manager/Procurement Engineer was followed closely by QA/QC Manage as a result of the criticality of quality issues in Product innovation. Considering the whole EPC project for Product Innovation, the Project Manager was identified as most influential Stakeholders because of the position’s important decision-making role in the entire EPC Project. Like in the case of Process Innovation, top decision makers have more influence on Product Innovation.

### Objective 3 - Activities and Process Innovation

Objective 3: To identify the most influential activity on process innovation in the EPC project during each phase of the project and during the entire project

The node EP1110 described as “IPF (SIL Review)” was identified as the most influential Activity node in the Engineering Phase of Process Innovation due to its having many connections with other nodes that give it access to important information flows and it’s not belonging to a specific WBS.  In the Procurement Phase, Activity node PM0005 related to WBS Task “Procurement Management” with the description “Weekly Procurement expediting meetings with Contractor and Vendors” was identified as the most influential on Process Innovation because it connects many Activities and Stakeholders. The Construction Phase was found to have Activity CC1592 – Fire water Tank – Final Testing (NDT, RT etc.) as the most influential in the Social Network because of its having the highest number of links to other nodes and high closeness in the Network. Most influential Activities on Process innovation in this phase were found to be related to Piping and Mechanical Equipment.

For the entire EPC project, Activity EP1110 – IPF (SIL Review) was identified as the most influential on Process Innovation because of its high number of connections and highly central Network position. Activities that cut across sections were found to be the most influential. Further, it is those nodes that are higher in the EPC Project decision making hierarchy that have the most influence.

### Objective 4 – Activities and Product Innovation

Objective 4: To identify the most influential activity on product innovation in the EPC project during each phase of the project and during the entire project

EP1110 - IPF (SIL Review), as was the case with Process Innovation and for the same reasons, was found to be the most influential Activity on Product Innovation in the Engineering Phase. In the Procurement Phase the most influential Activity on Product Innovation was identified as A1360 (Suction KO drum – prepare and Issue MR.) as it presented a high number of links to other nodes and centrality in the Procurement Phase Social Network. In the Construction Phase CC2120 – Mechanical (Equipment) – HIPS Installation was identified as most influential on Product Innovation because of its high activity score as per the ranking defined in this study.

Considering the entire EPC project, Activity EP1110 – IPF (SIL Review) was identified as the most influential Activity on Product Innovation for the whole EPC Project as it ranked higher than any other activity presenting a high number of connections and occupying a central position in the Network (Table 11.32). As was the situation for Process Innovation, Stakeholder nodes which rank higher in the hierarchy in terms of decision making and or having cross-sectional Activities were also found to be the most influential in the case of Product Innovation.

### Objective 5 and 6 – Modelling Process and Product Innovation

Objective 5: To determine how to model Stakeholder interaction of process innovation in the EPC project

and

Objective 6: To determine how to model Stakeholder interaction of process and product innovation in the EPC project

Given that Oil and Gas EPC projects are complex and have a multiplicity of Stakeholders, Activities and connections, the influence on innovation is difficult to analyse from the perspective of the whole network. Social Network Analysis focusing on Ego Networks and involving creating a subset of the original Network for each of the nodes under analysis and including those nodes that share a connection with it was found appropriate for modelling Stakeholder interaction of process and product innovation in the EPC project studied.

### Objective 7 – Applicability of Network Measures

Objective 7: To determine whether network measures can be used to better understand the complexity of the EPC project

The study illustrated that two network measures namely Degree Centrality and Closeness Centrality can be used to derive a better understanding of Project Alpha in terms of identifying process and product innovation influencers among the Stakeholders and Activities. The generated metrics (Table 11.34) facilitated making comparisons among the different Networks generated in the Findings chapters (Chapters 7 – 10).

## Study Generalizability

Although the study focused on a specific EPC project in the downstream oil and gas sector in UAE, the framework may be extended to other settings as detailed below. Further, since the framework was developed based on EPC projects data, it can also be applied, with some modifications, to non EPC projects given that the study conducted an individual analysis for each phase of the EPC project. Below are some of the settings and commonality the developed framework may be used in:

- Upstream EPC Projects:

While there are some operational differences between Downstream and Upstream EPC projects, the commonality between both sectors cannot be overlooked. In many Oil and Gas Companies, both sectors are operated and managed by the same mother company and the majority of the project stakeholders are common for both sectors. In addition most of EPC Contractors and Engineering Firms tend to work with both sectors and their engineering and constructions resources are shared among both sectors.  While some of the project deliverables are different for both sectors, the mandates, technical standards and safety regulations are common. Accordingly, the commonality is vast between the two sectors and the utilization of the developed framework may be extended to upstream operators with some minor adjustments related to the project deliverables.

- Engineering Consultancy Firms:

The Engineering in an EPC project is usually developed by Engineering Consultants, who are part of the overall analysed EPC stakeholders. In addition, the framework was developed for the engineering phase independently, therefore the framework may be adopted by engineering firms to assess their stakeholders’ engagement in EPC projects and provide them with a depth understanding of their role and involvement. This is significant as it can enable engineering firms to leverage aspects of stakeholder interactions or relations that are most associated with process and product innovation outcomes.

- Oil and Gas Construction Contractors:

Oil and Gas Construction Contractors may adopt the developed framework to assist their construction works. Since the developed framework assessed construction stakeholders’ impact on process and product innovation during the construction phase independently, construction firms may utilize the framework to better engage their stakeholders and ensure maximum utilization of their resources.

- Civil Construction Industry:

While there are some differences between Civil Construction and Oil and Gas Projects, as the latter tend to follow strict technical and safety regulations, there are many commonality that both sectors share. Both sectors tend to follow structured project management and planning. Both sectors give high priority to meeting the project’s schedule and cost parameters. Hence and with some tailor made modification, the civil construction industry may adopt the developed framework to support in meeting schedule and cost driven projects.

- Other industries:

Other industries may follow the sequence used in  developing the study’s  framework (e.g. identification of stakeholders and activities, creating dependency matrix, social network maps and running the model using social network software) to understand the impact of their internal and external stakeholders on project outcomes and accordingly enhance their engagement.

## Research Limitations

Notwithstanding the highlighted commonality and as tends to be the case with any research, this study had limitations relating to data collection, reporting style, guiding assumptions, time, and limited generalisability of the findings.

Limitations relating to data collection: Because data was gathered from official reports of a completed EPC project, the network is constructed from formal relationships or connections as depicted in reports and therefore disregards informal exchanges of information which could also influence innovation. The relationships analysed therefore only represent the official view while completely disregarding undocumented informal connections that existed as part of the project’s social network.

Limitation relating to reporting style: The reporting style of findings and their discussion tended to be repetitive as, in the interest of clarity and addressing the study objectives, the researcher had to report on each Phase following the same format to facilitate comparability of findings between Phases.

Limitations relating to assumptions about relationships: The study conclusions assume that the number of connections and position in a social network necessarily reflect value adding interactions and are therefore indicative of level of influence on innovation. In reality this is not always the case as having the highest number of links does not of itself reveal the quality of a link in terms of information flow.

Limitations relating to time: Like other studies of this nature, time was a major limiting factor that guided the choice of methods used to collect the data. Thus, although the researcher was aware of possible benefits to be derived from combining the documented network relationships with the informal undocumented ones, time constraints militated against such an approach.

Limitations relating to generalisability of the findings: The results are limited to Greenfield projects in the oil and gas downstream sector in UAE. Greenfield projects in other sectors or Brownfield projects in the same sector may present different results.

Further, the findings are specific to Project Alpha. While they may provide a glimpse into what may occur in similar projects, and therefore provide a template for use in other projects, that may need to be done with due adjustments as every EPC project is unique.

## Theoritical Contribution

Notwithstanding the highlighted limitations of this study, its theoretical contribution is at three levels: proposing a framework for mapping stakeholder interactions and resultant innovation, use of Social Network Analysis’ Ego Networks technique as an analysis tool for a complex network, and use of data grounded in a real-life project situation to anchor the proposed framework.

Social networks are widely recognised as instruments of innovation diffusion (Kolleck, 2013). However, it was observed that there was a limitation in the literature on utilizing Social Network Analysis to analyse stakeholder relationships within downstream oil and gas EPC projects for purposes of understanding within project product and process innovation. Therefore, this research attempts to fulfil the gap in the literature on utilization of social network in the context of EPC projects and innovation. It is anticipated that the adoption of social network will improve our understanding of the stakeholders’ impact on process and product innovation in EPC projects. The study main theoretical contributions are discussed below while the practical contribution will be presented in the next section.

The study’s first major contribution to theory is proposing a framework that can be used to understand and map out the relationship of the complex interactions between project stakeholders and process and product innovation in downstream oil and gas EPC projects, which could be applicable to projects in similar environments.  Although the study focused on a specific EPC project in the downstream oil and gas sector in UAE, the framework can be extended to similar settings. This was demonstrated by confirmation of the study’s findings by those of the quantitative survey that drew its participants from other EPC projects.  Further, although the framework was developed based on EPC projects data, it can also be applied, with some modifications, to non EPC projects given that the study conducted an individual analysis of each phase of the EPC project.

The second contribution to theory is the use of the Social Network Analysis’ Ego Networks as a technique to analyse a complex network with a large number of nodes and connections. The approach opens up possibilities for enhancing understanding of stakeholder relations and contribution not just in a downstream oil and gas project but in other complex social networks. Although other methods for collecting data such as interviews may have been used, using data derived from formal project documents, listing relevant activities and stakeholders, ensured that all formal connections of the network were analysed. Assessing innovation outcomes based on the document distribution matrix derived from stakeholders and activities data facilitated the identification of stakeholders’ impact on innovation outcomes. The approach employed that involved dissection of individual EPC project phase networks contributes a detail - oriented approach to understanding relationships and knowledge flow within phases which could be applied to EPC projects in other industry sectors.

The third contribution to theory is in the choice of the data collection method. Because the data in the study was collected from a subsisting project, the findings are therefore not hypothetical in as far as they depict actual relationships. In that regard the study contributes lessons that are grounded in a real-life situation that can be transferred to similar or related future EPC projects. The study’s focus on retrospective, detailed analysis of process and product innovation in a successfully completed EPC project, using formal data, provides indicators to how to extract and preserve innovation data as part of a contracting organisation’s institutional memory.

## Practice Contribution

By utilization of social network analysis in EPC projects, practitioners will be able to understand the level of influence, engagement and impact of stakeholders in EPC projects. Therefore the study first practical contribution is concentrated on the utilization of social network analysis to maximize the outcome of stakeholders’ engagement.

By understanding the activities that contribute most towards process and product innovation, practitioners will be able ensure maximum organisational benefit from an EPC project.  In addition, by understanding specific stakeholder contribution towards process and product innovation, the organisation will be able to priorities investment in the most critical or key stakeholders in order to achieve the maximum contribution.

By using the results of this study, project decision makers will be able understand the main contributors to project goals and will be able to increase the outcome of process and product innovation:

- By understanding the influence of stakeholders and activities on process innovation, project members will be able to increase the impact some stakeholders and activities will have on the project duration, improve the procurement process and reduce operational cost. More aid can be provided to these stakeholders to support their work and ensure maximum returns.

- By understanding the influence of stakeholders and activities on product innovation, project members will be able to reduce production cost, ensure fulfilling health and safety requirements and achieve the industrial standards. Accordingly, better engagement of the highest influencers can be attained to ensure meeting these goals.

## Recommendations for Further Research

This research focused on identifying the most influential stakeholders and activities to innovation outcomes in a specific downstream oil and gas EPC project using social network analysis. Future studies may seek to use the same methods of analysis to explore stakeholder influence on innovation in other related industries.

Deeper analysis of innovation only focusing on the social network of a single phase of an EPC project. Such an approach would allow for a more extensive investigation using both quantitative and qualitative approaches.  This would facilitate using a reporting style that is less repetitive as interviews-based data is likely to add depth in the process highlighting differences in areas which, at face value, seem similar.

This study analysed influence using social network theory having made assumptions concerning relationships based on data collected from formal connections of the network; future studies may focus on augmenting this with interviews to gain a better understanding of the type and quality of information moving through a network given that knowledge leading to innovation flows through networks of relationships.

# References

Aaltonen, K. and Kujala, J., 2016. Towards an improved understanding of project stakeholder landscapes. International Journal of Project Management, 34(8), pp.1537-1552.

Aaltonen, K., Kujala, J., Havela, L. and Savage, G., 2015. Stakeholder dynamics during the project front-end: the case of nuclear waste repository projects. Project Management Journal, 46(6), pp.15-41.

AL-Ali, W.A.H., 2017.  Diffusion of ICT innovations in UAE public schools and the role of stakeholder engagement. PhD thesis (The British University in Dubai). https://bspace.buid.ac.ae/bitstream/1234/1019/3/120097.pdf

Albaidhani, I. and Romero, A., 2018. When Project Meets Innovation:“PRO-INNOVA Conceptual Model”. The Journal of Modern Project Management, 5(3).

Alegre, J. and Chiva, R., 2008. Assessing the impact of organizational learning capability on product innovation performance: An empirical test. Technovation, 28(6), pp.315-326.

Alhaj, I., 2016. The impact of organisational context on innovation in Libyan's public and private oil sectors: the role of social capital and knowledge sharing (Doctoral dissertation, University of Plymouth).

Al-Husseini, S. and Elbeltagi, I., 2015. Knowledge sharing practices as a basis of product innovation: A case of higher education in Iraq. International Journal of Social Science and Humanity, 5(2), p.182.

Ali, I., Musawir, A.U. and Ali, M., 2018. Impact of knowledge sharing and absorptive capacity on project performance: the moderating role of social processes. Journal of Knowledge Management, 22(2), pp.453-477.

AN, A., ACIFIC, E., ICA, L. and ION, T., 2015. Downstream Project Management. http://petrominonline.com/pub/hcasia/mags/ha070915.pdf

Andersson, M., 2007. Entry costs and adjustments on the extensive margin-an analysis of how familiarity breeds exports(No. 81). Royal Institute of Technology, CESIS-Centre of Excellence for Science and Innovation Studies.

Andriof, J., Waddock, S., Husted, B. and Rahman, S.S., 2017. Unfolding stakeholder engagement. In Unfolding stakeholder thinking (pp. 19-42). Routledge.

Aragonés-Beltrán, P., García-Melón, M. and Montesinos-Valera, J., 2017. How to assess stakeholders' influence in project management? A proposal based on the Analytic Network Process. International Journal of Project Management, 35(3), pp.451-462.

Arain, F.M., 2011. Significant causes of changes in oil and gas construction projects in alberta, canada. International Journal of Construction Project Management, 3(2), p.145.

Arrouj, A., 2017. Frond-End Loading and its Impact on Cost Overruns in the Norwegian Public Sector (Master's thesis, University of Stavanger, Norway).

Assink, M., 2006. Inhibitors of disruptive innovation capability: a conceptual model. European Journal of Innovation Management, 9(2), pp.215-233.

Ayhan, M.B., Öztemel, E., Aydin, M.E. and Yue, Y., 2013. A quantitative approach for measuring process innovation: a case study in a manufacturing company. International Journal of Production Research, 51(11), pp.3463-3475.

Ayuso, S., Ángel Rodríguez, M., García-Castro, R. and Ángel Ariño, M., 2011. Does stakeholder engagement promote sustainable innovation orientation?. Industrial Management & Data Systems, 111(9), pp.1399-1417.

Azadeh, A., Shafiee, F., Yazdanparast, R., Heydari, J. and Fathabad, A.M., 2017. Evolutionary multi-objective optimization of environmental indicators of integrated crude oil supply chain under uncertainty. Journal of Cleaner Production, 152, pp.295-311.

Azim, S., Gale, A., Lawlor-Wright, T., Kirkham, R., Khan, A. and Alam, M., 2010. The importance of soft skills in complex projects. International Journal of Managing Projects in Business, 3(3), pp.387-401.

Baharuddin, H.E.A., Wilkinson, S. and Costello, S.B., 2013, May. Evaluating early stakeholder engagement (ESE) as a process for innovation. In CIB World Building Congress, Brisbane, Australia.

Bakker, M., Leenders, R.T.A., Gabbay, S.M., Kratzer, J. and Van Engelen, J.M., 2006. Is trust really social capital? Knowledge sharing in product development projects. The Learning Organization, 13(6), pp.594-605.

Barney, J., 1991. Firm resources and sustained competitive advantage. Journal of management, 17(1), pp.99-120.

Baron, H., 2010. The oil and gas engineering guide. Editions Technip.

Bastas, A. and Liyanage, K., 2018. Sustainable supply chain quality management: A systematic review. Journal of Cleaner Production, 181, pp.726-744.

Bastian, M., Heymann, S. and Jacomy, M., 2009, March. Gephi: an open source software for exploring and manipulating networks. In Third international AAAI conference on weblogs and social media.

Basu, R., 2017. Managing project supply chains. Routledge. DOIhttps://doi.org/10.4324/9781315249902

BERA, 2013. Oil and gas production. Available at: www.loc.gov/rr/business/BERA/issue5/production.html. [Accessed on 22 June 2019].

Bennett, L. & Nair, C. S. 2010. A recipe for effective participation rates for web‐based surveys. Assessment & Evaluation in Higher Education, 35, 357-365.

Berardi, U., 2013. Stakeholders’ influence on the adoption of energy-saving technologies in Italian homes. Energy policy, 60, pp.520-530.

Beringer, C., Jonas, D. and Kock, A., 2013. Behavior of internal stakeholders in project portfolio management and its impact on success. International Journal of Project Management, 31(6), pp.830-846.

Binsarra, F.A., 2016. Uncovering the structure and the dynamic of information propagation in building (Doctoral dissertation, University of Liverpool).

Biscotti, A.M., D’Amico, E. and Monge, F., 2018. Do environmental management systems affect the knowledge management process? The impact on the learning evolution and the relevance of organisational context. Journal of Knowledge Management, 22(3), pp.603-620.

Bjorvatn, T. and Wald, A., 2018. Project complexity and team-level absorptive capacity as drivers of project management performance. International Journal of Project Management, 36(6), pp.876-888.

Bjugn, R. and Casati, B., 2012. Stakeholder analysis: a useful tool for biobank planning. Biopreservation and biobanking, 10(3), pp.239-244.

Bonnal, P., Gourc, D. and Lacoste, G., 2002. The life cycle of technical projects. Project Management Journal, 33(1), pp.12-19.

Bontis, N., 1998. Intellectual capital: an exploratory study that develops measures and models. Management Decision, 36(2), pp.63-76.

Borgatti, S.P., Mehra, A., Brass, D.J. and Labianca, G., 2009. Network analysis in the social sciences. Science, 323(5916), pp.892-895.

Börjesson, S. and Elmquist, M., 2011. Developing innovation capabilities: a longitudinal study of a project at Volvo Cars. Creativity and Innovation Management, 20(3), pp.171-184.

Bourne, L. and Walker, D.H., 2005. Visualising and mapping stakeholder influence. Management decision, 43(5), pp.649-660..

Brettel, M. and Cleven, N.J., 2011. Innovation culture, collaboration with external partners and NPD performance. Creativity and Innovation Management, 20(4), pp.253-272.

Brion, S., Mothe, C. and Sabatier, M., 2010. The impact of organisational context and competences on innovation ambidexterity. International Journal of Innovation Management, 14(02), pp.151-178.

Brotherton, S.A., Fried, R.T. and Norman, E.S., 2008. Applying the work breakdown structure to the project management lifecycle. In PMI Global Congress Proceedings (pp. 1-15).

Browning, T.R., 2016. Design structure matrix extensions and innovations: a survey and new opportunities. IEEE Transactions on Engineering Management, 63(1), pp.27-52.

Bryant, P. and Rao, S., 2017.  The Oil & Gas Industry’s New Normal: Rethinking Innovation Priorities in the Age of Low Prices. Avaialbe at: https://blog.clareo.com/the-oil-gas-industrys-new-normal-rethinking-innovation-priorities-in-the-age-of-low-prices. [Accessed 16 October 2018].

Bryman, A., 1984. The debate about quantitative and qualitative research: a question of method or epistemology?. British journal of Sociology, pp.75-92.Butts, C.T., 2008. Social network analysis with sna. Journal of statistical software, 24(6), pp.1-51.

Butt, A., Naaranoja, M. and Savolainen, J., 2016. Project change stakeholder communication. International Journal of Project Management, 34(8), pp.1579-1595.

Cagliano, A.C., De Marco, A., Grimaldi, S. and Rafele, C., 2012. An integrated approach to supply chain risk analysis. Journal of risk research, 15(7), pp.817-840.

Cagno, E. and Micheli, G.J., 2011. Enhancing EPC supply chain competitiveness through procurement risk management. Risk Management, 13(3), pp.147-180.

Cameron, R. and Molina-Azorin, J.F., 2011. The acceptance of mixed methods in business and management research. International Journal of Organizational Analysis, 19(3), pp.256-271.

Camisón, C. and Villar López, A., 2010. An examination of the relationship between manufacturing flexibility and firm performance: The mediating role of innovation. International Journal of Operations & Production Management, 30(8), pp.853-878.

Cammarano, A., Caputo, M., Lamberti, E., & Michelino, F. (2017). R&D collaboration strategies for innovation: An empirical study through social network analysis. International Journal of Innovation and Technology Management, 14(01), 1740001

Carlson, M., Cori, K. A., Junghans, F., & Bredehoeft, P. (2007). Delivering to cost in an EPC world. Paper presented at PMI® Global Congress 2007—North America, Atlanta, GA. Newtown Square, PA: Project Management Institute.

Carroll, A.B. and Buchholtz, A.K., 2006. Business & Society: Ethics and Stakeholder Management. 6. painos. Mason: Thomson/South-Western.

Castro, F.A.D. and Mulama, B., 2018. Network Design Model for Fuel Retail. https://dspace.mit.edu/bitstream/handle/1721.1/117611/Castro_Mulama_2018_Capstone.pdf?sequence=1

Chaudhary, A.K. and Radhakrishna, R.B., 2018. Social network analysis: A methodology for exploring diversity and reach among extension programs and stakeholders. Journal of Extension, 56(6), p.6FEA1.

Chesbrough, H.W., 2011. The Era of Open Innovation. Top 10 Lessons on the New Business of Innovation, p.35.

Chitsazan, H., Bagheri, A. and Yusefi, A., 2017. Intellectual, Psychological, and Social Capital and Business Innovation: The Moderating Effect of Organizational Culture. Iranian Journal of Management Studies, 10(2), pp.307-333.

Cohen, L., Manion, L. and Morrison, K., 2017. Research methods in education. routledge.

Creswell, J. W., 2014. Research design: qualitative quantitative and mixed methods approaches. 4 ed. Thousand Oaks: Sage.

Crossley, N., 2010. The social world of the network. Combining qualitative and quantitative elements in social network analysis. Sociologica, 4(1), pp.0-0.

Daiss, T.,  2019. What’s Behind Saudi Arabia’s New Downstream Strategy? Available at: https://oilprice.com/Energy/Energy-General/Whats-Behind-Saudi-Arabias-New-Downstream-Strategy.html [Accessed on 25 June 2019].

Dal Mas, M., Giarola, S., Zamboni, A. and Bezzo, F., 2010. Capacity planning and financial optimization of the bioethanol supply chain under price uncertainty. In Computer Aided Chemical Engineering (Vol. 28, pp. 97-102). Elsevier.

Damanpour, F. and Aravind, D., 2011. Managerial Innovation: Conceptions, Processes, and Antecedents. Management and Organization Review, 8(2), pp.423-454.

Damanpour, F., Walker, R.M. and Avellaneda, C.N., 2009. Combinative effects of innovation types and organizational performance: A longitudinal study of service organizations. Journal of management studies, 46(4), pp.650-675.

Davcheva, M., 2019. Oil and gas industry overview. Available at: www.schedulereader.com/blog/oil-and-gas-industry-overview [Accessed on 22 June 2019].

Davies, R., 2009. The use of social network analysis tools in the evaluation of social change communications. Communication for social change consortium.

De Brún, A. and McAuliffe, E., 2018. Social Network Analysis as a methodological approach to explore health systems: A case study exploring support among senior managers/executives in a hospital network. International journal of environmental research and public health, 15(3), p.511.

de Oliveira, G.F. and Rabechini Jr, R., 2019. Stakeholder management influence on trust in a project: A quantitative study. International Journal of Project Management, 37(1), pp.131-144.

Delice, A., 2010. The Sampling Issues in Quantitative Research. Educational Sciences: Theory and Practice, 10(4), pp.2001-2018.

Derakhshan, R., Turner, R. and Mancini, M., 2019. Project governance and stakeholders: a literature review. International Journal of Project Management, 37(1), pp.98-116.

Dew, N. and Sarasvathy, S.D., 2007. Innovations, stakeholders & entrepreneurship. Journal of Business Ethics, 74(3), pp.267-283.

Di Maddaloni, F. and Davis, K., 2017. The influence of local community stakeholders in megaprojects: Rethinking their inclusiveness to improve project performance. International Journal of Project Management, 35(8), pp.1537-1556.

Díaz-García, C., González-Moreno, A. and Jose Sáez-Martínez, F., 2013. Gender diversity within R&D teams: Its impact on radicalness of innovation. Innovation, 15(2), pp.149-160.

Digital Promise, n.d. Planning a social network analysis. http://digitalpromise.org/wp-content/uploads/2018/09/SNA-Toolkit.pdf

Dipaola, A. 2018. Saudi Looks to Petrochemicals for Its Next Big Projects.   www.bloomberg.com/news/articles/2018-10-10/saudis-look-past-crude-with-100-billion-in-downstream-projects

Dipaola, A. and Gamal El-Din, Y., 2018. Saudi Aramco to Invest $100B in Chemicals. www.rigzone.com/news/wire/saudi_aramco_to_invest_100b_in_chemicals-26-nov-2018-157562-article/

Donaldson, T. and Preston, L.E., 1995. The stakeholder theory of the corporation: Concepts, evidence, and implications. Academy of management Review, 20(1), pp.65-91.

Drucker, P., 2014. Innovation and entrepreneurship. Routledge.

Du, J. and El-Gafy, M., 2014. Using Agent-Based Modeling to Investigate Goal Incongruence Issues in Proposal Development: Case Study of an EPC Project. Journal of Management in Engineering, 31(6), p.05014025.

Du, J. and El-Gafy, M., 2015. Human computation enabled organizational learning in the face of deep uncertainty: example of conceptual estimating. Journal of Information Technology in Construction (ITcon), 20(18), pp.275-294.

Dziallas, M. and Blind, K., 2018. Innovation indicators throughout the innovation process: an extensive literature analysis. Technovation.

Easterby-Smith, M. and Thorpe, R., Lowe (1991) Management Research: an introduction. Sage Publication.

Ebers, M. and Maurer, I., 2014. Connections count: How relational embeddedness and relational empowerment foster absorptive capacity. Research Policy, 43(2), pp.318-332.

Edwards, G., 2010. Mixed-method approaches to social network analysis. http://eprints.ncrm.ac.uk/842/1/Social_Network_analysis_Edwards.pdf

Ellonen, H.K., Wikström, P. and Jantunen, A., 2009. Linking dynamic-capability portfolios and innovation outcomes. Technovation, 29(11), pp.753-762.

Elsetouhi, A., Elbeltagi, I. and Haddoud, M.Y., 2015. Intellectual capital and innovations: is organisational capital a missing link in the service sector?. International Journal of Innovation Management, 19(02), p.1550020.

Eppinger, S.D., 2001. Innovation at the speed of information. Harvard business review, 79(1), pp.149-158.

Erkul, M., Yitmen, I. and Çelik, T., 2016. Stakeholder Engagement in Mega Transport Infrastructure Projects. Procedia Engineering, 161, pp.704-710.

Erna, E., Surachman, S., Sunaryo, S. and Djajuli, A., 2019. Integration between radical innovation and incremental innovation to expedite supply chain performance through collaboration and open-innovation: A case study of Indonesian logistic companies. Uncertain Supply Chain Management, 7(2), pp.191-202.

Eskerod, P. and Larsen, T., 2018. Advancing project stakeholder analysis by the concept ‘shadows of the context’. International Journal of Project Management, 36(1), pp.161-169.

Eskerod, P. and Vaagaasar, A.L., 2014. Stakeholder management strategies and practices during a project course. Project Management Journal, 45(5), pp.71-85.

Eskerod, P., Huemann, M. and Ringhofer, C., 2015. Stakeholder inclusiveness: Enriching project management with general stakeholder theory. Project Management Journal, 46(6), pp.42-53.

Eyiah-Botwe, E., Aigbavboa, C. and Thwala, W.D., 2016. Managing consultants as key construction stakeholders for enhanced stakeholder management and project delivery. https://ujcontent.uj.ac.za/vital/access/services/Download/uj:20167/SOURCE1

Feital, T., Lima, P., Pinto, J.C., de Souza, M.B., Xavier, G., Lima, M.J. and Joly, M., 2013. Rethinking petroleum products certification. Journal of Petroleum Engineering, 2013.

Feng, W., Crawley, E.F., de Weck, O.L., Keller, R. and Robinson, B., 2010. Dependency structure matrix modelling for stakeholder value networks. https://dspace.mit.edu/openaccess-disseminate/1721.1/81156

Fernandes, A.C., Sampaio, P., Sameiro, M. and Truong, H.Q., 2017. Supply chain management and quality management integration: A conceptual model proposal. International Journal of Quality & Reliability Management, 34(1), pp.53-67.

Fernandes, L.J., Relvas, S. and Barbosa-Póvoa, A.P., 2013. Strategic network design of downstream petroleum supply chains: single versus multi-entity participation. Chemical Engineering Research and Design, 91(8), pp.1557-1587.

Fernandes, L.J., Relvas, S. and Barbosa-Póvoa, A.P., 2014. Collaborative design and tactical planning of downstream petroleum supply chains. Industrial & Engineering Chemistry Research, 53(44), pp.17155-17181.

Fischer, B.B., 2015. On the contributions of knowledge-intensive business-services multinationals to laggard innovation systems. BAR-Brazilian Administration Review, 12(2), pp.150-168.

Freeman, L., 2004. The development of social network analysis. A Study in the Sociology of Science, 1.

Freeman, R.E., Harrison, J.S., Wicks, A.C., Parmar, B.L. and De Colle, S., 2010. Stakeholder theory: The state of the art. Cambridge University Press.

Fynes, B., Coughlan, P., Milewski, S.K., Fernandes, K.J. and Mount, M.P., 2015. Exploring technological process innovation from a lifecycle perspective. International Journal of Operations & Production Management.

Gambatese, J.A. and Hallowell, M., 2011. Enabling and measuring innovation in the construction industry. Construction Management and Economics, 29(6), pp.553-567.

Gao, J., 2018. Sustainable Design and Optimization of Shale Gas Energy Systems. PhD thesis. Cornell.

Garcia, M.M. and Hawes, S. 2019. United Arab Emirates: Oil and Gas Regulation 2019. https://iclg.com/practice-areas/oil-and-gas-laws-and-regulations/united-arab-emirates

Garcia, D.J. and You, F., 2015. Supply chain design and optimization: Challenges and opportunities. Computers & Chemical Engineering, 81, pp.153-170.

Gault, F., 2016, September. Defining and measuring innovation in all sectors of the economy: policy relevance. In Proceedings of the OECD Blue Sky Forum III, Ghent, Belgium(pp. 19-21).

Gawlik, J. and Kiełbus, A., 2010. Chosen aspects of innovative projects management. Archives of foundry engineering, 10(3), p.175.

Gebhardt, K., Riel, A., & Maes, T. (2020, September). Integrating Stakeholder and Social Network Analysis into Innovation Project Management. In European Conference on Software Process Improvement (pp. 794-804). Springer, Cham.

Ghaithan, A.M., Attia, A. and Duffuaa, S.O., 2017. Multi-objective optimization model for a downstream oil and gas supply chain. Applied Mathematical Modelling, 52, pp.689-708.

Gibson, C.B. and Birkinshaw, J., 2004. The antecedents, consequences, and mediating role of organizational ambidexterity. Academy of management Journal, 47(2), pp.209-226.

Giorgos Cheliotis, 2010. Social network analysis.  www.slideshare.net/gcheliotis/social-network-analysis-3273045

Globerson, S., 1994. Impact of various work-breakdown structures on project conceptualization. International Journal of Project Management, 12(3), pp.165-171.

Gnana, J. 2018. Adnoc to invest Dh165bn with partners in downstream. www.thenational.ae

Gnyawali, D.R. and Srivastava, M.K., 2013. Complementary effects of clusters and networks on firm innovation: A conceptual model. Journal of Engineering and Technology Management, 30(1), pp.1-20.

Godenhjelm, S. and Johanson, J.E., 2018. The effect of stakeholder inclusion on public sector project innovation. International Review of Administrative Sciences, 84(1), pp.42-62.

Gonzalez, R., Llopis, J. and Gasco, J., 2013. Innovation in public services: The case of Spanish local government. Journal of Business Research, 66(10), pp.2024-2033.

Gould, R.W. (2012). 'Open Innovation and Stakeholder Engagement.' Journal of Technology Management & Innovation, 7(3).

Grönlund, J., Sjödin, D.R. and Frishammar, J., 2010. Open innovation and the stage-gate process: A revised model for new product development. California management review, 52(3), pp.106-131.

Gürtler, M.R. and Lindemann, U., Situative open innovation–a model for selecting the right external actors and involving them in an efficient way. https://www.researchgate.net/profile/Matthias_Guertler/publication/289610235_Situative_Open_Innovation_-_A_model_for_selecting_the_right_external_actors_and_involving_them_in_an_efficient_way/links/58b92c06a6fdcc2d14d9aec9/Situative-Open-Innovation-A-model-for-selecting-the-right-external-actors-and-involving-them-in-an-efficient-way.pdf

Haar, P.T., 2018. Measuring innovation: A state of the science review of existing approaches. Intangible Capital, 14(3), pp.409-428.

Habibi, M., Kermanshachi, S. and Rouhanizadeh, B., 2019. Identifying and Measuring Engineering, Procurement, and Construction (EPC) Key Performance Indicators and Management Strategies. Infrastructures, 4(2), p.14. doi:10.3390/infrastructures4020014

Haji-Kazemi, S., Andersen, B. and Krane, H.P., 2013. Identification of early warning signs in front-end stage of projects, an aid to effective decision making. Procedia-Social and Behavioral Sciences, 74, pp.212-222.

Hanneman, R.A. and Riddle, M., 2005. Introduction to social network methods. University of California, Riverside. CA (Online book).

Harrison, H., Birks, M., Franklin, R. and Mills, J., 2017, January. Case Study Research: Foundations and Methodological Orientations. In Forum Qualitative Sozialforschung/Forum: Qualitative Social Research (Vol. 18, No. 1).

Hassani, H., Silva, E.S. and Al Kaabi, A.M., 2017. The role of innovation and technology in sustaining the petroleum and petrochemical industry. Technological Forecasting and Social Change, 119, pp.1-17.

Hau, Y.S., Kim, B., Lee, H. and Kim, Y.G., 2013. The effects of individual motivations and social capital on employees’ tacit and explicit knowledge sharing intentions. International Journal of Information Management, 33(2), pp.356-366.

Hein, A.M., Jankovic, M., Feng, W., Farel, R., Yune, J.H. and Yannou, B., 2017. Stakeholder power in industrial symbioses: A stakeholder value network approach. Journal of cleaner production, 148, pp.923-933.

Hejazi, R., Ghanbari, M. and Alipour, M., 2016. Intellectual, Human and Structural Capital Effects on Firm Performance as Measured by Tobin's Q. Knowledge and Process Management, 23(4), pp.259-273.

Helper R.P. (n.d.). A template for EPC project management and execution. Available at: http://www.rphconsultingltd.com/index_files/PM2237Slides.pdf. [Accessed on 5 December 2018].

Henriksen, L., 2018. Application of Project Management principles to improve innovation. International Journal of Project & Technology Management ,Volume 1, Issue 1, July 2018 http://www.ptmfonline.com/doc/Application%20of%20Project%20Management%20principles%20to%20improve%20innovation.pdf

Hermans, F., Sartas, M., Van Schagen, B., van Asten, P., & Schut, M. (2017). Social network analysis of multi-stakeholder platforms in agricultural research for development: Opportunities and constraints for innovation and scaling. PloS one, 12(2), e0169634.

Hollstein, B., 2014. Mixed methods social networks research: An introduction. Mixed methods social networks research: Design and applications, pp.3-34.

Homer, J., Sterman, J., Greenwood, B. and Perkola, M., 1993. Delivery time reduction in pulp and paper mill construction projects: A dynamic analysis of alternatives. In Proceedings of the 1993 International System Dynamics Conference (pp. 212-221). Cancun, Mexico: Monterey Institute of Technology.

Hörisch, J., Freeman, R.E. and Schaltegger, S., 2014. Applying stakeholder theory in sustainability management: Links, similarities, dissimilarities, and a conceptual framework. Organization & Environment, 27(4), pp.328-346.

Inkinen, H., 2015. Review of empirical research on intellectual capital and firm performance. Journal of Intellectual capital, 16(3), pp.518-565.

Janger, J., Schubert, T., Andries, P., Rammer, C. and Hoskens, M., 2017. The EU 2020 innovation indicator: A step forward in measuring innovation outputs and outcomes?. Research Policy, 46(1), pp.30-42.

Jansson, T. and Ljung, L., 2010. New times, new projects, new tools required. In Proceedings of the 24th IPMA World Congress 1-3 November, 2010, in Istanbul. International Project Management Association.

Jansson, T. and Ljung, L., 2013. Strategic project archetypes for effective project steering. Procedia-Social and Behavioral Sciences, 74, pp.112-122.

Jaskyte, K., 2011. Predictors of administrative and technological innovations in nonprofit organizations. Public Administration Review, 71(1), pp.77-86.

Jean, R.J.B., Kim, D. and Sinkovics, R.R., 2012. Drivers and performance outcomes of supplier innovation generation in customer–supplier relationships: The role of power‐dependence. Decision Sciences, 43(6), pp.1003-1038.

Jiménez-Jiménez, D. and Sanz-Valle, R., 2011. Innovation, organizational learning, and performance. Journal of Business Research, 64(4), pp.408-417.

Jogulu, U. D. and Pansiri, J., 2011. Mixed methods: A research design for management doctoral dissertations. Management Research Review, 34(6), pp. 687-701.

Johnson, R. B. and Onwuegbuzie, A. J., 2004. Mixed methods research: A research paradigm whose time has come. Educational Researcher, 33(7), pp. 14-26.

Johnsson, M., 2016. Innovation enablers and their importance for innovation teams (Doctoral dissertation, Blekinge Tekniska Högskola).

Jonas, J.M., Boha, J., Sörhammar, D. and Moeslein, K.M., 2018. Stakeholder engagement in intra-and inter-organizational innovation: Exploring antecedents of engagement in service ecosystems. Journal of Service Management. https://www.emeraldinsight.com/doi/pdfplus/10.1108/JOSM-09-2016-0239

Joslin, R. and Müller, R., 2015. Relationships between a project management methodology and project success in different project governance contexts. International Journal of Project Management, 33(6), pp.1377-1392.

Kahn, K.B., 2018. Understanding innovation. Business Horizons, 61(3), pp.453-460.

Kamaşak, R. and Bulutlar, F., 2010. The influence of knowledge sharing on innovation. European Business Review, 22(3), pp.306-317.

Kavin, L. and Narasimhan, R., 2018. An Investigation of Contextual Influences on Innovation in Complex Projects. Innovation and Supply Chain Management: Relationship, Collaboration and Strategies, pp.51-77.

Kazemi, Y. and Szmerekovsky, J., 2015. Modeling downstream petroleum supply chain: the importance of multi-mode transportation to strategic planning. Transportation Research Part E: Logistics and Transportation Review, 83, pp.111-125.

Kazemi, Y. and Szmerekovsky, J., 2016. An optimisation model for downstream petroleum supply chain incorporating geographic information system (GIS). International Journal of Integrated Supply Management, 10(2), pp.151-172.

Kazemi, Y., 2016. Modeling Petroleum Supply Chain: Multimodal Transportation, Disruptions and Mitigation Strategies (Doctoral dissertation, North Dakota State University).

Keegan, A. and Turner, J.R., 2002. The management of innovation in project-based firms. Long range planning, 35(4), pp.367-388.

Keupp, M.M., Palmié, M. and Gassmann, O., 2012. The strategic management of innovation: A systematic review and paths for future research. International Journal of Management Reviews, 14(4), pp.367-390.

Killen, C.P., Jugdev, K., Drouin, N. and Petit, Y., 2012. Advancing project and portfolio management research: Applying strategic management theories. International Journal of Project Management, 30(5), pp.525-538.

Kim, D.Y., Kumar, V. and Kumar, U., 2012. Relationship between quality management practices and innovation. Journal of operations management, 30(4), pp.295-315.

Kobarg, S., Stumpf-Wollersheim, J. and Welpe, I.M., 2019. More is not always better: Effects of collaboration breadth and depth on radical and incremental innovation performance at the project level. Research Policy, 48(1), pp.1-10.

Kolleck, N., 2013. Social network analysis in innovation research: using a mixed methods approach to analyze social innovations. European Journal of Futures Research, 1(1), p.25.

Kolleck, N. (2013). Social network analysis in innovation research: using a mixed methods approach to analyze social innovations. European Journal of Futures Research, 1(1), 1-9.

Kong, M.T., 2002. Downstream oil products supply chain optimisation. https://spiral.imperial.ac.uk/bitstream/10044/1/7714/1/Ming-Teck_Kong-2002-PhD-Thesis.pdf

Kucharska, W. and Kowalczyk, R., 2016. Trust, collaborative culture and tacit knowledge sharing in project management–A relationship model. https://www.researchgate.net/profile/Wioleta_Kucharska3/publication/309284422_Trust_Collaborative_Culture_and_Tacit_Knowledge_Sharing_in_Project_Management_-_a_Relationship_Model/links/580794ab08ae07cbaa54301f.pdf

Kuczmarski, T.D., 1996. Fostering an innovation mindset. Journal of consumer marketing, 13(6), pp.7-13.

Laradi, M.F., 2017. Evaluation of Supply Chain Risk Management for Material Procurement in Libyan Oil Industry(Doctoral dissertation, Coventry University).

Leal-Rodríguez, A.L., Roldán, J.L., Ariza-Montes, J.A. and Leal-Millán, A., 2014. From potential absorptive capacity to innovation outcomes in project teams: The conditional mediating role of the realized absorptive capacity in a relational learning context. International Journal of Project Management, 32(6), pp.894-907.

Leedy, P.D. and Ormrod, J.E., 2005. Practical research. Pearson Custom.

Liao, S.H., Chang, W.J., Hu, D.C. and Yueh, Y.L., 2012. Relationships among organizational culture, knowledge acquisition, organizational learning, and organizational innovation in Taiwan's banking and insurance industries. The International Journal of Human Resource Management, 23(1), pp.52-70.

Lima, C., Relvas, S. and Barbosa-Povoa, A., 2018. Stochastic programming approach for the optimal tactical planning of the downstream oil supply chain. Computers & Chemical Engineering, 108, pp.314-336.

Lima, C., Relvas, S. and Barbosa-Póvoa, A.P.F., 2016. Downstream oil supply chain management: A critical review and future directions. Computers & Chemical Engineering, 92, pp.78-92.

Lima, C., Relvas, S., Barbosa-Póvoa, A.P. and Morales, J.M., 2018. Oil product distribution planning via robust optimization. In Computer Aided Chemical Engineering (Vol. 43, pp. 949-954). Elsevier.

Lohmühler, B., 2003. Drivers of product innovation: an investigation of German manufacturing companies (Doctoral dissertation, Cranfield University).

Lombardi, M., Lopolito, A., Andriano, A. M., Prosperi, M., Stasi, A., & Iannuzzi, E. (2020). Network impact of social innovation initiatives in marginalised rural communities. Social Networks, 63, 11-20.

Magalhaes, M.V. and Shah, N., 2003, January. Crude oil scheduling. In Proceedings of the 4th Conference on Foundations of Computer-Aided Process Operations (pp. 323-326).

Mahmoud-Jouini, S.B., Midler, C. and Garel, G., 2004. Time-to-market vs. time-to-delivery: Managing speed in Engineering, Procurement and Construction projects. International Journal of Project Management, 22(5), pp.359-367.

Marafi, A., 2017, January. Impact of Crude Oil Quality on Downstream Refining Processes. In 22nd World Petroleum Congress. World Petroleum Congress.

Marcel, J.O.L.Y. and Miyake, M.Y., 2017. Lessons learned from developing and implementing refinery production scheduling technologies. Frontiers of Engineering Management, 4(3), pp.325-337.

Marcell, J.O.L.Y., 2012. Refinery production planning and scheduling: the refining core business. Brazilian Journal of Chemical Engineering, 29(2), pp.371-384.

Marin, A. and Wellman, B., 2011. Social network analysis: An introduction. The SAGE handbook of social network analysis, 11.

Marzi, G., Dabić, M., Daim, T. and Garces, E., 2017. Product and process innovation in manufacturing firms: a 30-year bibliometric analysis. Scientometrics, 113(2), pp.673-704.

Mathur, V.N., Price, A. and Austin, S., 2008. Conceptualizing stakeholder engagement in the context of sustainability and its assessment. Construction Management and Economics, 26(6), pp.601-609.

Mazur, A.K. and Pisarski, A., 2015. Major project managers' internal and external stakeholder relationships: The development and validation of measurement scales. International Journal of Project Management, 33(8), pp.1680-1691.

Meng, X. and Boyd, P., 2017. The role of the project manager in relationship management. International Journal of Project Management, 35(5), pp.717-728.

Micheli, G.J. and Cagno, E., 2016. The role of procurement in performance deviation recovery in large EPC projects. International Journal of Engineering Business Management, 8, pp.1-17.

Miller, G., Furneaux, C., Davis, P., Love, P. and O‘Donnell, A., 2009. Built Environment Procurement Practice: Impediments to Innovation and Opportunities for Changes. Report commissioned by the Built Environment Industry Innovation Council, Canberra. http://www.academia.edu/download/30906270/Furneaux_-_BEIIC_Procurement_Report.pdf

Milza, R. 2016. Developing Multi-Attributes Portfolio Selection Model of downstream oil & gas projects. PM World Journal, V (9), September. https://pmworldjournal.net/article/developing-multi-attributes-portfolio-selection-model-downstream-oil-gas-projects/

Missonier, S. and Loufrani-Fedida, S., 2014. Stakeholder analysis and engagement in projects: From stakeholder relational perspective to stakeholder relational ontology. International Journal of Project Management, 32(7), pp.1108-1122.

Mitchell, R.K., Agle, B.R. and Wood, D.J., 1997. Toward a theory of stakeholder identification and salience: Defining the principle of who and what really counts. Academy of management review, 22(4), pp.853-886.

Mohnen, P. and Hall, B.H., 2013. Innovation and productivity: An update. Eurasian Business Review, 3(1), pp.47-65.

Mok, K.Y., Shen, G.Q. and Yang, J., 2015. Stakeholder management studies in mega construction projects: A review and future directions. International Journal of Project Management, 33(2), pp.446-457.

Mothe, C. and Uyen Nguyen Thi, T., 2010. The link between non-technological innovations and technological innovation. European Journal of Innovation Management, 13(3), pp.313-332.

Muriana, C. and Vizzini, G., 2017. Project risk management: A deterministic quantitative technique for assessment and mitigation. International Journal of Project Management, 35(3), pp.320-340.

Neale, R. 2016. Recovering downstream market yields opportunity. Downstream Business, December.

Nguyen, D.Q., 2018. The impact of intellectual capital and knowledge flows on incremental and radical innovation: Empirical findings from a transition economy of Vietnam. Asia-Pacific Journal of Business Administration, 10(2/3), pp.149-170.

Nijland, F. 2018. Successful innovation in the oil and gas industry how it works. Available at: https://www2.deloitte.com/nl/nl/pages/energy-and-resources/articles/successful-innovation-in-the-oil-and-gas-industry-how-it-works.html

Nonaka, I., Von Krogh, G. and Voelpel, S., 2006. Organizational knowledge creation theory: Evolutionary paths and future advances. Organization studies, 27(8), pp.1179-1208.

Norman, D.A. and Verganti, R., 2014. Incremental and radical innovation: Design research vs. technology and meaning change. Design issues, 30(1), pp.78-96.

OECD (Organization for Economic Cooperation and Development)/Eurostat 2005. Guidelines for Collecting and Interpreting Innovation Data — The Oslo Manual, 3rd edn. Paris: OECD

Oil Gas Authority, 2017.  Lessons Learned from UKCS Oil and Gas Projects 2011-2016. Available at: https://www.ogauthority.co.uk/news-publications/publications/2017/lessons-learned-from-ukcs-oil-and-gas-projects-2011-2016/

Olander, S. and Landin, A., 2005. Evaluation of stakeholder influence in the implementation of construction projects. International journal of project management, 23(4), pp.321-328.

O’Riordan, L. and Fairbrass, J., 2014. Managing CSR stakeholder engagement: A new conceptual framework. Journal of Business Ethics, 125(1), pp.121-145.

Otte, E. and Rousseau, R., 2002. Social network analysis: a powerful strategy, also for the information sciences. Journal of information Science, 28(6), pp.441-453.

Ouakouak, M.L. and Ouedraogo, N., 2017. Antecedents of employee creativity and organisational innovation: an empirical study. International Journal of Innovation Management, 21(07), p.1750060.

Oxford Business Group, 2016. Saudi Arabia moves to extend its downstream industrial reach. https://oxfordbusinessgroup.com/analysis/go-flow-saudi-arabia-looking-both-east-and-west-extend-its-downstream-reach

Öztas, A., and Ökmen, Ö., 2004. Risk analysis in fixed-price design-build construction projects. Build. Environ. 39 (2), pp. 229–237. https://doi.org/10.1016/j.buildenv.2003.08.018.

Ozorhon, B., 2012. Analysis of construction innovation process at project level. Journal of Management in Engineering, 29(4). DOI: 10.1061/(ASCE)ME.1943-5479.0000157

Palangkaraya, A., 2012. The link between innovation and export: Evidence from Australia’s small and medium enterprises. ERIA Discussion Paper, 8.

Pan, L., 2007. Effective and efficient methodologies for social network analysis (Doctoral dissertation, Virginia Tech).

Parraguez, P., Eppinger, S. and Maier, A., 2016. Characterizing design process interfaces as organization networks: Insights for engineering systems management. Systems Engineering, 19(2), pp.158-173.

Parraguez, P., Eppinger, S.D. and Maier, A.M., 2015. Information flow through stages of complex engineering design projects: a dynamic network analysis approach. IEEE Transactions on Engineering Management, 62(4), pp.604-617.

Pektaş, Ş.T. and Pultar, M., 2006. Modelling detailed information flows in building design with the parameter-based design structure matrix. Design Studies, 27(1), pp.99-122.

Pellé, S. and Reber, B., 2015. Responsible innovation in the light of moral responsibility. Journal on Chain and Network Science, 15(2), pp.107-117.

Penide, T., Gourc, D., Pingaud, H. and Peillon, P., 2013. Innovative process engineering: a generic model of the innovation process. International Journal of Computer Integrated Manufacturing, 26(3), pp.183-200.

Persaud, A.C., 2007. Innovation and performance: the case of the upstream petroleum sector (Doctoral dissertation, Carleton University).

Phillips, R.A., Berman, S.L., Elms, H. and Johnson-Cramer, M.E., 2010. Strategy, Stakeholders and Managerial Discretion. Strategic Organization, 8(2), pp.176-183.

Pipeline Oil and Gas News, 2018. ADNOC launches Taweelah gas compression plant. www.pipelineoilandgasnews.com/regionalinternational-news/regional-news/2018/november/adnoc-launches-taweelah-gas-compression-plant

Poazi, F.D.W., Tamunosiki-Amadi, J.O. and Fems, M., 2017. The Resource-Base View of Organization and Innovation: Recognition of Significant Relationship in an Organization. World Academy of Science, Engineering and Technology, International Journal of Social, Behavioral, Educational, Economic, Business and Industrial Engineering, 11(3), pp.692-699.

Preble J.F. 2005. Toward a comprehensive model of stakeholder management. Business and Society Review, 110(4), pp. 407 – 431.

Prester, J., Podrug, N. and Daraboš, M., 2016, May. Four-Component Model of Intellectual Capital and Its Impact on Process and Product Innovations. In ECIC 8th European Conference on Intellectual Capital.

Priemus, H., 2009. Do Design & Construct contracts for infrastructure projects stimulate innovation? The case of the Dutch high speed railway. Transportation planning and technology, 32(4), pp.335-353.

Protenders, 2019. Shah gas development sour gas expansion plant. protenders.com/projects/shah-gas-development-sour-gas-plant-expansion

Rahimi, M., Kenworthy, T.P. and Balakrishnan, J., 2018. An Analysis of Innovation in Oil and Gas Projects. Project Management Journal, 49(5), pp.64-84.

Rajablu, M., Marthandan, G. and Yusoff, W.F.W., 2014. Managing for stakeholders: the role of stakeholder-based management in project success. Asian social science, 11(3), p.111.

Reed, D., 1999. Stakeholder management theory: A critical theory perspective. Business Ethics Quarterly, 9(3), pp.453-483.

Reichstein, T. and Salter, A., 2006. Investigating the sources of process innovation among UK manufacturing firms. Industrial and Corporate change, 15(4), pp.653-682.

Render, C., 2016. The Benefits of Good Front-End Loading. Available at:  http://www.otctoolkits.com/the-benefits-of-good-front-end-loading/ . [Accessed on 15 October 2018].

Ritsche, F. 2014. Project management handbook for EPC. Available at: www.project-team.org. [Accessed on 15 October 2018].

Roberts, D.L. and Candi, M., 2014. Leveraging social network sites in new product development: Opportunity or hype?. Journal of Product Innovation Management, 31, pp.105-117.

Rogers, E.M., 2003. Diffusion of Innovations. 5th ed New York NY Free Press.

Rolstadås, A. and Schiefloe, P.M., 2017. Modelling project complexity. International Journal of Managing Projects in Business, 10(2), pp.295-314.

Rowley, T.J., 1997. Moving beyond dyadic ties: A network theory of stakeholder influences. Academy of management Review, 22(4), pp.887-910.

Ruggiero, S., Onkila, T. and Kuittinen, V., 2014. Realizing the social acceptance of community renewable energy: A process-outcome analysis of stakeholder influence. Energy Research & Social Science, 4, pp.53-63.

Rui, Z., Peng, F., Ling, K., Chang, H., Chen, G. and Zhou, X., 2017. Investigation into the performance of oil and gas projects. Journal of Natural Gas Science and Engineering, 38, pp.12-20.

Safapour, E. and Kermanshachi, S., 2019, June. Investigation and Analysis of Human, Organizational, and Project Based Rework Indicators in Construction Projects. In Proceedings of the ASCE International Conference on Computing in Civil Engineering, Atlanta, GA, USA (pp. 17-19).

Sahebi, H., Nickel, S. and Ashayeri, J., 2014. Strategic and tactical mathematical programming models within the crude oil supply chain context—A review. Computers & Chemical Engineering, 68, pp.56-77.

Salazar-Aramayo, J.L., Rodrigues-da-Silveira, R., Rodrigues-de-Almeida, M. and de Castro-Dantas, T.N., 2013. A conceptual model for project management of exploration and production in the oil and gas industry: The case of a Brazilian company. International journal of project management, 31(4), pp.589-601.

Sangle, S. and Babu, P.R., 2007. Evaluating sustainability practices in terms of stakeholders' satisfaction. International Journal of Business Governance and Ethics, 3(1), pp.56-76.

Saudi Arabian Oil Company, 2016. Saudi Arabia’s downstream industry can spur a new era. Available at:  https://www.saudiaramco.com/en/news-media/news/2016/downstream-industry-spur-a-new-era

Saunders, M., Lewis, P. and Thornhill, A., 2012. Research Methods for Business Students, 6th edition. Harlow, UK: Pearson.

Savage, G.T., Dunkin, J.W. and Ford, D.M., 2004. Responding to a crisis: A stakeholder analysis of community health organizations. Journal of health and human services administration, pp.383-414.

Sawhney, M., Wolcott, R.C. and Arroniz, I., 2006. The 12 different ways for companies to innovate. MIT Sloan Management Review, Spring, pp. 75-78.

Scafuto, I.C., Belfort, A.C., dos Santos Teixeira, G.C. and Maccari, E.A., 2018. Process Innovation: a surfing manufacturer case study. International Journal of Innovation: IJI Journal, 6(1), pp.16-32.

Schmidt, T. and Rammer, C., 2007. Non-technological and technological innovation: strange bedfellows?. ZEW-Centre for European Economic Research Discussion Paper, (07-052).

Scholes, E. and Clutterbuck, D., 1998. Communication with stakeholders: An integrated approach. Long Range Planning, 31(2), pp.227-238.

Schumpeter, J.A., 1983. Business cycles: a theoretical, historical, and statistical analysis of the capitalist process. McGraw-Hill Book Company.

Scott, J., 1988. Social network analysis. Sociology, 22(1), pp.109-127.

Senghore, F., Campos-Nanez, E., Fomin, P. and Wasek, J.S., 2014. Using Social Network Analysis to Investigate the Potential of Innovation Networks: Lessons Learned from NASA's International Space Apps Challenge. Procedia computer science, 28, pp.380-388.

Shen, W., Choi, B., Lee, S., Tang, W. and Haas, C.T., 2018. How to Improve Interface Management Behaviors in EPC Projects: Roles of Formal Practices and Social Norms. Journal of Management in Engineering, 34(6), p.04018032.

Shen, W., Tang, W., Wang, S., Duffield, C.F., Hui, F.K.P. and You, R., 2017. Enhancing trust-based interface management in international engineering-procurement-construction projects. Journal of Construction Engineering and Management, 143(9), p.04017061.https://doi.org/10.1061/(ASCE)CO.1943-7862.0001351.

Shlopak, M., Emblemsvåg, J. and Oterhals, O., 2014. Front end loading as an integral part of the project execution model in lean shipbuilding. In Proceedings of the 22nd Annual Conference of the International Group for Lean Construction, Akademika forlag, Oslo.

Shokri, S., Ahn, S., Lee, S., Haas, C.T. and Haas, R.C.G., 2015. Current status of interface management in construction: Drivers and effects of systematic interface management. Journal of Construction Engineering and Management, 142(2), p.04015070.

Singh, A.R. and Tiwari, S., 2015. EPC: an innovative tool for mega project construction. International Journal in IT and Engineering, 3(7), pp.21-28.

Sjödin, D.R. and Eriksson, P.E., 2010. Procurement procedures for supplier integration and open innovation in mature industries. International Journal of Innovation Management, 14(04), pp.655-682. https://doi.org/10.1142/S1363919610002817

Sjödin, D.R., 2011. Buyer-supplier collaboration in operational projects: Towards' Open Operation'. In International Product Development Management Conference: 05/06/2011-07/06/2011.

Škerlavaj, M., Song, J.H. and Lee, Y., 2010. Organizational learning culture, innovative culture and innovations in South Korean firms. Expert systems with applications, 37(9), pp.6390-6403.

Slater, S.F., Mohr, J.J. and Sengupta, S., 2014. Radical product innovation capability: Literature review, synthesis, and illustrative research propositions. Journal of Product Innovation Management, 31(3), pp.552-566.

Stake, R.E., 1995. The Art of Case Study Research, (Thousand Oaks, CA, Sage, 1995),

Stewart, T. and Ruckdeschel, C., 1998. Intellectual capital: The new wealth of organizations. Performance Improvement, 37(7), pp.56-59.

Storbacka, K., Brodie, R.J., Böhmann, T., Maglio, P.P. and Nenonen, S., 2016. Actor engagement as a microfoundation for value co-creation. Journal of Business Research, 69(8), pp.3008-3017.

Strauss, A. and Corbin, J., 1998. Basics of qualitative research techniques. Thousand Oaks, CA: Sage publications.

Stretton, A., 2017. A commentary on project classifications. PM World Journal, VI (X), pp. 1 – 9. Available online at: https://pmworldjournal.net. [Accessed on 15 October 2018].

Susnienė, D. and Purvinis, O., 2015. Empirical insights on understanding stakeholder influence. Journal of Business Economics and Management, 16(4), pp.845-860.

Swart, A., 2016. Innovation in oil and gas: Canada 2016. Monitor Deloitte.,

Swift, P.E. and Hwang, A., 2013. The impact of affective and cognitive trust on knowledge sharing and organizational learning. The Learning Organization, 20(1), pp.20-37.

Taebi, B., Correlje, A., Cuppen, E., Dignum, M. and Pesch, U., 2014. Responsible innovation as an endorsement of public values: The need for interdisciplinary research. Journal of Responsible Innovation, 1(1), pp.118-124.

Terry Kim, T., Lee, G., Paek, S. and Lee, S., 2013. Social capital, knowledge sharing and organizational performance: what structural relationship do they have in hotels?. International Journal of Contemporary Hospitality Management, 25(5), pp.683-704.

Tian, M., Deng, P., Zhang, Y. and Salmador, M.P., 2018. How does culture influence innovation? A systematic literature review. Management Decision, 56(5), pp.1088-1107.

Tidd, J. and Bessant, J., 2018. Innovation management challenges: from fads to fundamentals. International Journal of Innovation Management, 22(05), p.1840007.

Trott, P., 2008. Exploring Knowledge Flows and Losses in the ‘Open Innovation’Age. In Determinants of Innovative Behaviour (pp. 126-150). Palgrave Macmillan, London.

Trott, P. and Hartmann, D.A.P., 2009. Why'open innovation'is old wine in new bottles. International journal of innovation management, 13(04), pp.715-736.

Turner, P. and Turner, S., 2009. Triangulation in practice. Virtual Reality, 13(3), pp.171-181.

U.S.-U.A.E. Business Council, 2019. The U.A.E. oil and gas sector: Recent updates. http://usuaebusiness.org/wp-content/uploads/2019/01/U.A.E.-Oil-and-Gas-Sector.pdf

ul Musawir, A., Serra, C.E.M., Zwikael, O. and Ali, I., 2017. Project governance, benefit management, and project success: Towards a framework for supporting organizational strategy implementation. International Journal of Project Management, 35(8), pp.1658-1672.

Un, C. A. and Asakawa, K., 2015. Types of R&D Collaborations and Process Innovation: The Benefit of Collaborating Upstream in the Knowledge Chain. Journal of Product Innovation Management, 32(1), 138-153.

Uribe, D.F., Ortiz-Marcos, I. and Uruburu, Á., 2018. What Is Going on with Stakeholder Theory in Project Management Literature? A Symbiotic Relationship for Sustainability. Sustainability, 10(4), pp.1-23.

Vaccaro, I.G., Jansen, J.J., Van Den Bosch, F.A. and Volberda, H.W., 2012. Management innovation and leadership: The moderating role of organizational size. Journal of Management Studies, 49(1), pp.28-51.

Van de Ven, A.H., 1986. Central problems in the management of innovation. Management science, 32(5), pp.590-607.

Van Der Valk, T., & Gijsbers, G. (2010). The use of social network analysis in innovation studies: Mapping actors and technologies. Innovation, 12(1), 5-17.

Vargo, S.L., Wieland, H. and Akaka, M.A., 2015. Innovation through institutionalization: A service ecosystems perspective. Industrial Marketing Management, 44, pp.63-72.

Wagner Mainardes, E., Alves, H. and Raposo, M., 2012. A model for stakeholder classification and stakeholder relationships. Management decision, 50(10), pp.1861-1879.

Walker, D.H., Bourne, L.M. and Shelley, A., 2008. Influence, stakeholder mapping and visualization. Construction Management and Economics, 26(6), pp.645-658.

Walstrom, K. A. & Wilson R. L. 1997. An examination of executive information system (EIS) users. Information & Management, 32, 75-83.

Wallace, D., 1995. Environmental policy and industrial innovation: Strategies in Europe, the USA and Japan. Earthscan.

Wang, C.L. and Ahmed, P.K., 2004. The development and validation of the organisational innovativeness construct using confirmatory factor analysis. European journal of innovation management.

Wang, T. and Chen, Y., 2018. Capability stretching in product innovation. Journal of Management, 44(2), pp.784-810.

Wang, Z. and Wang, N., 2012. Knowledge sharing, innovation and firm performance. Expert systems with applications, 39(10), pp.8899-8908.

Watson, R., Wilson, H.N., Smart, P. and Macdonald, E.K., 2018. Harnessing Difference: A Capability‐Based Framework for Stakeholder Engagement in Environmental Innovation. Journal of Product Innovation Management, 35(2), pp.254-279.

Weiss, M., Hoegl, M. and Gibbert, M., 2011. Making virtue of necessity: The role of team climate for innovation in resource‐constrained innovation projects. Journal of Product Innovation Management, 28(s1), pp.196-207.

Wellman, B. 1983. Network analysis: Some basic principles. Sociological Theory 1: 155–200.

West, J. and Bogers, M., 2014. Leveraging external sources of innovation: a review of research on open innovation. Journal of Product Innovation Management, 31(4), pp.814-831.

Williams, T. and Samset, K., 2010. Issues in front‐end decision making on projects. Project Management Journal, 41(2), pp.38-49.

Windapo, A.O., Oyewobi, L. and Zwane, Z., 2014. Investigation of stakeholders' awareness and adoption of Inherently Safer Design (ISD) principles in South African utility industry projects. Journal of Loss Prevention in the Process Industries, 32, pp.152-160.

Wolf, T.E. (2010). A Generalized EPC Schedule Tool. http://prjmgrcap.com/images/17-04-10_Schedule_Article.pdf

Woodland, R.H., Barry, S. and Roohr, K.C., 2014. Using social network analysis to promote schoolwide instructional innovation: A case study. Journal of School Leadership, 24(1), pp.114-145.

World Energy Council, 2014. Gas in United Arab Emirates. www.worldenergy.org/data/resources/country/united-arab-emirates/gas/

Wu, J. and Chiclana, F., 2014. A social network analysis trust–consensus based approach to group decision-making problems with interval-valued fuzzy reciprocal preference relations. Knowledge-Based Systems, 59, pp.97-107.

Xiao, R. and Chen, T., 2010. Research on design structure matrix and its applications in product development and innovation: an overview. International Journal of Computer Applications in Technology, 37(3/4), pp.218-229.

Xue, X., Zhang, R., Yang, R. and Dai, J., 2014. Innovation in construction: a critical review and future research. International Journal of Innovation Science, 6(2), pp.111-126.

Yang, C.C. and Lin, C.Y.Y., 2009. Does intellectual capital mediate the relationship between HRM and organizational performance? Perspective of a healthcare industry in Taiwan. The International Journal of Human Resource Management, 20(9), pp.1965-1984.

Yassine, A., 2004. An introduction to modeling and analyzing complex product development processes using the design structure matrix (DSM) method. Urbana, 51(9), pp.1-17.

Yeşil, S. and Hırlak, B., 2013. An empirical investigation into the influence of knowledge sharing barriers on knowledge sharing and individual innovation behaviour. International Journal of Knowledge Management (IJKM), 9(2), pp.38-61.

Yi, D., Lee, E.B. and Ahn, J., 2019. Onshore Oil and Gas Design Schedule Management Process Through Time-Impact Simulations Analyses. Sustainability, 11(6), p.1613.

Yin, R.K., 2003. Case Study Research, Design and Methods, 3rd Ed., Beverley Hills, CA: Sage.

Yokura, Y., Matsubara, H., & Sternberg, R. (2013). R&D networks and regional innovation: a social network analysis of joint research projects in Japan. Area, 45(4), 493-503.

Yousefi-Babadi, A., Tavakkoli-Moghaddam, R., Bozorgi-Amiri, A. and Seifi, S., 2017. Designing a reliable multi-objective queuing model of a petrochemical supply chain network under uncertainty: a case study. Computers & Chemical Engineering, 100, pp.177-197.

Yu, H., Solvang, W.D. and Li, S., 2014, November. An integrated optimization model for single-product supply chain network design considering supplier selection. In Cognitive Infocommunications (CogInfoCom), 2014 5th IEEE Conference on (pp. 443-448). IEEE.

YuTeck Chuong PE, C.C.E., 2007. Project estimate reviews for oil and gas projects. AACE International Transactions, p.ES71.

Zhao, S. and Li, Z., 2015. Integrated Distribution-Transportation Planning for the Raw Material Supply Chain Management. In Proceedings of the Ninth International Conference on Management Science and Engineering Management (pp. 255-265). Springer, Berlin, Heidelberg.

Zhou, K.Z. and Li, C.B., 2012. How knowledge affects radical innovation: Knowledge base, market knowledge acquisition, and internal knowledge sharing. Strategic management journal, 33(9), pp.1090-1102.

Zhu, F., Sun, X., Xu, X. and Haider, Z., 2014. A knowledge integration framework of EPC project based on KBS and stakeholder networks. International Journal of Innovative Computing, Information and Control, 10(2), pp.703-715.

Zulkafli, N.I. and Kopanos, G.M., 2018. A general optimization framework for the design and planning of energy supply chain networks: Techno-economic and environmental analysis. Chemical Engineering Research and Design, 131, pp.214-233.

# Appendices

Activities Distribution Matrix - Engineering

Activities Distribution Matrix - Procurement

- Appendix C
Activities Distribution Matrix - Construction

- Appendix D
Questionnaire

Questionnaire

Q1 - In an EPC Project, please rate the below Stakeholders (from 0 to 100) in terms of their influence/impact in Reducing the Project Duration. 0 is having the least and 100 is having the highest Impact:

| # | Field | Minimum | Maximum | Mean | Std Deviation | Variance | Count |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Manager | 30.00 | 100.00 | 78.08 | 15.68 | 245.88 | 62 |
| 2 | Engineering Manager | 15.00 | 100.00 | 75.40 | 21.75 | 473.06 | 63 |
| 3 | Sr. QA/QC Engineer | 0.00 | 100.00 | 50.56 | 21.18 | 448.57 | 62 |
| 4 | Sr. Piping/ Pipeline Engineer | 10.00 | 90.00 | 48.61 | 23.12 | 534.53 | 62 |
| 5 | Sr. Process Engineer | 16.00 | 100.00 | 59.00 | 17.81 | 317.29 | 62 |

Q2 - In an EPC Project, please rate the below Stakeholders (from 0 to 100) in terms of their influence/impact in Improving the Procurement Activities. 0 is having the least and 100 is having the highest Impact:

| # | Field | Minimum | Maximum | Mean | Std Deviation | Variance | Count |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Manager | 0.00 | 100.00 | 74.44 | 19.34 | 374.12 | 63 |
| 2 | Engineering Manager | 10.00 | 100.00 | 73.98 | 22.33 | 498.75 | 63 |
| 3 | Sr. QA/QC Engineer | 14.00 | 95.00 | 54.06 | 21.64 | 468.37 | 64 |
| 4 | Sr. Process Engineer | 0.00 | 98.00 | 52.90 | 22.79 | 519.40 | 61 |
| 5 | Sr. Piping/ Pipeline Engineer | 0.00 | 90.00 | 42.78 | 24.04 | 578.07 | 60 |

Q3 - In an EPC Project, please rate the below Stakeholders (from 0 to 100) in terms of their influence/impact in Reducing the Project (unit) Operational Cost. 0 is having the least and 100 is having the highest Impact:

| # | Field | Minimum | Maximum | Mean | Std Deviation | Variance | Count |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Manager | 0.00 | 100.00 | 70.70 | 22.02 | 484.72 | 63 |
| 2 | Engineering Manager | 10.00 | 100.00 | 73.60 | 23.00 | 529.16 | 63 |
| 3 | Sr. Quality Engineer | 5.00 | 97.00 | 49.31 | 23.09 | 533.20 | 59 |
| 4 | Sr. Process Engineer | 10.00 | 100.00 | 61.80 | 21.52 | 462.98 | 61 |
| 5 | Sr. Piping/ Pipeline Engineer | 5.00 | 97.00 | 44.02 | 25.05 | 627.64 | 59 |

Q4 - In an EPC Project, please rate the below Stakeholders (from 0 to 100) in terms of their influence/impact in Reducing Production (Manufacturing & Execution) Cost. 0 is having the least and 100 is having the highest Impact:

| # | Field | Minimum | Maximum | Mean | Std Deviation | Variance | Count |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Manager | 10.00 | 100.00 | 74.68 | 23.13 | 535.19 | 62 |
| 2 | Engineering Manager | 5.00 | 100.00 | 58.94 | 23.96 | 574.03 | 62 |
| 3 | QA/QC Manager | 14.00 | 100.00 | 59.80 | 19.47 | 378.91 | 61 |
| 4 | Cost Control Manager/Procurement Engineer | 7.00 | 100.00 | 57.00 | 30.34 | 920.35 | 62 |
| 5 | Sr. QA/QC Engineer | 15.00 | 97.00 | 62.26 | 18.06 | 326.00 | 61 |

Q5 - In an EPC Project, please rate the below Stakeholders (from 0 to 100) in terms of their influence/impact in Meeting Health & Safety Requirements. 0 is having the least and 100 is having the highest Impact:

| # | Field | Minimum | Maximum | Mean | Std Deviation | Variance | Count |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Manager | 23.00 | 100.00 | 83.83 | 16.45 | 270.55 | 64 |
| 2 | Engineering Manager | 13.00 | 100.00 | 57.02 | 24.99 | 624.73 | 62 |
| 3 | QA/QC Manager | 9.00 | 100.00 | 56.02 | 23.76 | 564.40 | 63 |
| 4 | Sr. QA/QC Engineer | 5.00 | 100.00 | 61.74 | 22.23 | 493.96 | 61 |
| 5 | Cost Control Manager/ Procurement Engineer | 4.00 | 100.00 | 43.90 | 25.88 | 669.96 | 59 |

Q6 - In an EPC Project, please rate the below Stakeholders (from 0 to 100) in terms of their influence/impact in achieving the Industry Standards. 0 is having the least and 100 is having the highest Impact

| # | Field | Minimum | Maximum | Mean | Std Deviation | Variance | Count |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project Manager | 11.00 | 100.00 | 78.43 | 18.19 | 330.94 | 63 |
| 2 | Engineering Manager | 19.00 | 100.00 | 70.25 | 23.57 | 555.33 | 63 |
| 3 | QA/QC Manager | 29.00 | 100.00 | 69.98 | 21.22 | 450.11 | 63 |
| 4 | Sr. QA/QC Engineer | 48.00 | 100.00 | 75.08 | 15.54 | 241.43 | 62 |
| 5 | Cost Control Manager/ Procurement Engineer | 6.00 | 100.00 | 50.24 | 24.96 | 623.05 | 62 |